## Connection Project List
Project Information | [7 empty] | Energization 1 |  |  | Energization 2 |  |  | Energization 3
Project Name | Planning Area | Cluster | Project Type | MW Type | Stage | Inclusion | Applied On | STS MW | DTS MW | ISD | STS MW | DTS MW | ISD | STS MW | DTS MW | ISD
Processed For Cluster (See Note 1)
P2698 East Camrose 285S DER Solar Battery | 31-Wetaskiwin | EDM-01 | BTF | Solar + Storage | 0 | No | 2023-04-03 14:28 | 18.9 | 0 | 2025-08-31
P2700 Springbrook West MPC Solar | 35-Red Deer | CNTL-01 | Connection | Solar | 0 | No | 2023-04-20 | 300 | 1.5 | 2027-10-01
P2701 Oyen Wind Phase II | 42-Hanna | CNTL-01 | BTF | Wind | 0 | No | 2023-04-26 13:41 | 216 | 0 | 2026-09-01
P2703 Pinnacle 1 & 2 MPC Gas | 40-Wabamun | EDM-01 | Connection | Gas | 0 | No | 2023-04-27 13:52 | 44.6 | 1 | 2025-03-01
P2704 Western MPC Solar | 06-Calgary | SW-CAL-01 | Connection | Solar | 0 | No | 2023-05-04 | 150 | 1 | 2026-09-01
P2707 Sounding Creek Solar Battery | 42-Hanna | CNTL-01 | Connection | Solar + Storage | 0 | No | 2023-05-12 13:26 | 250 | 50 | 2026-12-01
P2708 Diamond MPC Solar Battery | 44-Seebe | SW-CAL-01 | Connection | Solar + Storage | 0 | No | 2023-05-15 10:06 | 60 | 0.5 | 2027-06-01
P2710 Cypress North DER Solar | 48-Empress | SE-01 | BTF | Solar | 0 | No | 2023-05-23 14:34 | 14.8 | 0 | 2025-12-01
P2711 Tent Mountain MPC Pumped Hydro | 53-Fort Macleod | SW-CAL-01 | Connection | Pumped Hydro Storage | 0 | No | 2023-05-25 14:31 | 400 | 400 | 2028-05-01
P2712 UK LS5 MPC Solar | 23-Valleyview | NW-01 | Connection | Solar | 0 | No | 2023-05-31 14:02 | 25.3 | 0.1 | 2026-01-01
P2713 UK LS1 MPC Solar | 23-Valleyview | NW-01 | Connection | Solar | 0 | No | 2023-06-01 12:01 | 448 | 1 | 2026-01-01
P2715 Ellis Energy Centre MPC Gas | 35-Red Deer | CNTL-01 | Connection | Gas | 0 | No | 2023-06-05 08:21 | 178 | 3 | 2026-07-01
P2718 Ponoka 331S DER Solar Battery | 31-Wetaskiwin | EDM-01 | BTF | Solar + Storage | 0 | No | 2023-06-07 12:40 | 18.2 | 0 | 2023-08-31
P2719 Westlock 438S DER Solar Battery | 27-Athabasca/Lac La Biche | NE-01 | BTF | Solar + Storage | 0 | No | 2023-06-09 14:30 | 22.45 | 0 | 2025-08-01
P2721 Alderson Solar & Wind | 04-Medicine Hat | SE-01 | Connection | Wind | 0 | No | 2023-06-16 10:39 | 450 | 1.5 | 2025-06-30
P2722 Sturgeon 734S DER Solar | 23-Valleyview | NW-01 | BTF | Solar | 0 | No | 2023-06-16 11:38 | 20 | 0 | 2026-01-01
P2724 Paintearth MPC Solar Battery | 36-Alliance/Battle River | CNTL-01 | Connection | Solar + Storage | 0 | No | 2023-06-26 14:22 | 330 | 300 | 2027-03-01
P2725 Sheerness MPC Solar Battery | 43-Sheerness | SE-01 | Connection | Solar + Storage | 0 | No | 2023-06-26 14:14 | 310 | 410 | 2027-03-01
P2735 Lethbridge Three Solar | 54-Lethbridge | SE-01 | Connection | Solar | 0 | No | 2023-07-19 14:18 | 140 | 0.35 | 2026-05-01
P2742 Alsike Energy Centre MPC Gas | 30-Drayton Valley | CNTL-01 | Connection | Gas | 0 | No | 2023-07-26 10:56 | 178 | 3 | 2026-07-01
P2743 Gilby Energy Centre MPC Gas | 35-Red Deer | CNTL-01 | Connection | Gas | 0 | No | 2023-07-26 11:03 | 178 | 3 | 2023-07-26
P2744 Prentiss Energy Centre MPC Gas | 35-Red Deer | CNTL-01 | Connection | Gas | 0 | No | 2023-07-26 11:15 | 178 | 3 | 2026-07-01
P2745 Eagle Butte Wind | 04-Medicine Hat | SE-01 | Connection | Wind | 0 | No | 2023-07-28 15:25 | 200 | 1 | 2026-03-16
Active
P0693 Wild Rose 2 Wind Farm | 04-Medicine Hat |  | Connection | Wind | 5 | Yes | 2007-05-01 10:00 | 192 | 4 | 2023-09-30
P1567 EDPR Sharp Hills Wind Farm | 42-Hanna |  | Connection | Wind | 6 | Yes | 2014-06-04 | 0 | 0.5 | 2023-02-10 | 288.9 | 0 | 2023-09-20
P1649 EPCOR Garneau Area Upgrade | 60-Edmonton |  | Connection | Load | 5 | Yes | 2015-02-20 10:00 | 0 | 0 | 2022-04-08 | 0 | 0 | 2022-06-14 | 0 | 0 | 2023-05-29
P1704 Paintearth Wind Power | 42-Hanna |  | Connection | Wind | 5 | Yes | 2015-10-08 10:00 | 0 | 1 | 2023-10-06 | 150 | 0 | 2023-11-08
P1756 TPG Canyon Creek PHES Storage Project | 29-Hinton/Edson |  | Connection | Pumped Hydro Storage | 3 | Yes | 2016-03-02 10:00 | 0 | 64 | 2025-12-01 | 75 | 0 | 2026-05-01
P1824 Lone Pine MPC Wind | 42-Hanna |  | Connection | Wind | 3 | Yes | 2016-07-28 10:00 | 466 | 1 | 2024-12-01
P1828 hep Energy Alderson MPC Solar | 04-Medicine Hat |  | Connection | Solar | 3 | Yes | 2016-07-29 10:00 | 100 | 1 | 2024-12-02
P1853 Fortis Buffalo Atlee Cluster 1 WAGF | 48-Empress |  | BTF | Wind | 3 | Yes | 2016-08-30 10:00 | 12.3 | 0 | 2023-10-27
P1862 Fortis Spring Coulee 385S Solar DG | 55-Glenwood |  | BTF | Solar | 5 | Yes | 2016-09-28 10:00 | 28.5 | 0 | 2023-12-01
P1885 Northern Lights WAGF | 26-Swan Hills |  | Connection | Wind | 2 | Yes | 2016-11-01 10:00 | 400 | 3 | 2025-09-30
P1892 Fortis Buffalo Atlee Cluster 3 WAGF DER | 48-Empress |  | BTF | Wind | 3 | Yes | 2016-11-15 10:00 | 4.6 | 0 | 2023-10-27
P1926 Solar Krafte Vauxhall | 52-Vauxhall |  | Connection | Solar | 3 | Yes | 2017-03-23 10:00 | 60 | 0.375 | 2024-06-01
P1978 ATCO Michichi DER Solar | 42-Hanna |  | BTF | Solar | 5 | Yes | 2017-06-20 10:00 | 61 | 0 | 2023-11-01
P1984 FortisAlberta Gleichen DG Solar | 45-Strathmore/Blackie |  | BTF | Solar | 5 | Yes | 2017-07-17 10:00 | 11.9 | 0 | 2024-05-01
P1987 Rainier MPC Solar | 47-Brooks |  | Connection | Solar | 3 | Yes | 2017-07-28 10:00 | 450 | 1.12 | 2024-12-15
P2031 ATCO M.D. of Greenview Load | 22-Grande Cache |  | Connection | Load | 3 | No | 2018-01-02 10:00 | 0 | 33.2 | 2024-12-01
P2032 Cascade Combined Cycle | 29-Hinton/Edson |  | Connection | Gas | 6 | Yes | 2018-01-02 10:00 | 0 | 0 | 2022-03-01 | 0 | 11.5 | 2022-12-11 | 900 | 0 | 2023-09-21
P2034 Cold Lake Area Energy Centre | 28-Cold Lake |  | Connection | Cogen | 3 | Yes | 2018-01-02 10:00 | 100 | 3 | 2025-04-01
P2076 ATCO Thornton 2091S Contract Change | 22-Grande Cache |  | Contract | DTS | 3 | Yes | 2018-04-09 10:00 | 0 | 12.1 | 2025-10-01
P2082 Suncor Base Plant Cogen | 25-Fort McMurray |  | Connection | Cogen | 5 | Yes | 2018-04-24 10:00 | 0 | -130 | 2023-09-02 | 0 | 0 | 2023-10-20 | 0 | 0 | 2023-11-29
P2091 edp Renewables Blue Bridge Solar | 48-Empress |  | Connection | Solar | 3 | Yes | 2018-05-22 10:00 | 150 | 5 | 2025-08-01
P2102 EPC East Calgary Area Reliability | 06-Calgary |  | Connection | Load | 5 | Yes | 2018-06-07 10:00 | 0 | 26 | 2024-10-28
P2136 FortisAlberta Brazeau Area Reliability | 30-Drayton Valley |  | Connection | Load | 2 | No | 2018-08-09 10:00 | 0 | 5.4 | 2025-11-14
P2137 Enerfin Winnifred MPC Wind | 04-Medicine Hat |  | Connection | Wind | 5 | Yes | 2018-08-10 10:00 | 90 | 1 | 2024-10-01
P2192 ENMAX FMC Change | 06-Calgary |  | BTF | Cogen | 5 | Yes | 2019-01-02 10:00 | 4.99 | 0 | 2024-04-07
P2195 FortisAlberta Bassano 435S DER Solar | 47-Brooks |  | BTF | Solar | 5 | Yes | 2019-01-07 10:00 | 9.25 | 0 | 2023-12-10
P2196 Grand Prairie MPC Gas | 20-Grande Prairie |  | Connection | Gas | 3 | Yes | 2019-01-11 10:00 | 400 | 5 | 2024-06-01
P2199 FortisAlberta Buffalo Atlee Cluster 2 | 48-Empress |  | BTF | Wind | 3 | Yes | 2019-01-28 10:00 | 13.8 | 0 | 2023-10-27
P2201 ENMAX SS-1 Substation Change | 06-Calgary |  | BTF | Equipment Change | 5 | Yes | 2019-01-30 10:00 | 0 | 0 | 2024-04-15
P2218 ENGIE Duchess Solar | 47-Brooks |  | Connection | Solar | 3 | Yes | 2019-04-01 10:00 | 90 | 0.11 | 2025-09-01
P2232 ENGIE Buffalo Trail North Wind | 04-Medicine Hat |  | Connection | Wind | 5 | Yes | 2019-05-03 10:00 | 200 | 6 | 2028-01-15
P2237 RESC Forty Mile MPC Wind | 04-Medicine Hat |  | Connection | Wind | 5 | Yes | 2019-05-09 10:00 | 0 | 0 | 2023-11-01 | 266 | 10 | 2024-07-18
P2247 Buffalo Plains MPC Wind | 47-Brooks |  | Connection | Wind | 5 | Yes | 2019-06-28 10:00 | 466 | 2 | 2024-07-01
P2248 ATCO Michichi Creek 802S DER Solar | 42-Hanna |  | BTF | Solar + Storage | 5 | Yes | 2019-06-26 10:00 | 13.5 | 0 | 2023-05-01 | 0 | 0 | 2023-11-17
P2256 ATCO Poplar Hill Load | 20-Grande Prairie |  | Connection | Load | 2 | No | 2019-07-11 10:00 | 0 | 62.4 | 2025-11-26
P2259 FortisAlberta Metiskow 648S DER Solar | 37-Provost |  | BTF | Solar + Storage | 5 | Yes | 2019-07-17 10:00 | 22 | 0 | 2024-12-13
P2279 CNRL Primrose East 641S Gas | 28-Cold Lake |  | BTF | Gas | 5 | Yes | 2019-09-19 10:00 | 0 | 0 | 2024-06-30
P2289 Heartland Scotford Change | 33-Fort Saskatchewan |  | BTF | Equipment Change | 6 | Yes | 2019-10-23 10:00 | 0 | 0 | 2025-06-15
P2292 FortisAlberta Killarney Lake 267S DER Solar/Battery Storage | 37-Provost |  | BTF | Solar + Storage | 5 | Yes | 2019-10-28 10:00 | 18 | 0 | 2025-01-31
P2296 ATCO Willow Lake 2009S Contract Change | 25-Fort McMurray |  | Contract | DTS | 6 | Yes | 2019-11-22 10:00 | 0 | 25.6 | 2025-01-01
P2334 TCE Saddlebrook Solar Storage | 46-High River |  | Connection | Solar + Storage | 5 | Yes | 2020-03-20 10:00 | 81 | 0.2 | 2023-10-16 | 0 | 0 | 2024-02-01
P2335 Fortis Vulcan 255S DER Solar | 49-Stavely |  | BTF | Solar | 5 | Yes | 2020-03-09 10:00 | 12.6 | 0 | 2024-06-01
P2337 Dunmore Solar | 04-Medicine Hat |  | Connection | Solar | 5 | Yes | 2020-03-16 10:00 | 216 | 0.5 | 2024-12-01
P2342 EDF Bull Trail Wind | 04-Medicine Hat |  | Connection | Wind | 3 | Yes | 2020-03-30 10:00 | 300 | 4 | 2025-05-30
P2347 Forty Mile Granlea Solar Phase 2 | 04-Medicine Hat |  | BTF | Solar | 5 | Yes | 2020-04-24 10:00 | 220 | 0.5 | 2023-11-17
P2348 BluEarth Wheatcrest MPC Solar | 52-Vauxhall |  | Connection | Solar | 5 | Yes | 2020-05-04 10:00 | 50 | 0.15 | 2023-10-24
P2352 ATCO Ethel Lake 717S DER Wasteheat | 28-Cold Lake |  | BTF | Wasteheat | 5 | Yes | 2020-05-07 10:00 | 0 | 0 | 2024-09-01
P2354 ENMAX FMC DER Cogen | 06-Calgary |  | BTF | Cogen | 5 | Yes | 2020-05-21 10:00 | 0 | 0 | 2023-11-30 | 4.99 | 0 | 2024-04-07
P2356 RESC Oyen MPC Wind | 42-Hanna |  | Connection | Wind | 3 | Yes | 2020-06-18 10:00 | 250 | 1 | 2026-02-02
P2369 ATCO Anderson 801S DER Solar | 43-Sheerness |  | BTF | Solar | 3 | Yes | 2020-08-04 10:00 | 9.8 | 0 | 2024-06-01
P2378 RESC Nova MPC Solar | 45-Strathmore/Blackie |  | Connection | Solar | 4 | Yes | 2020-09-08 10:00 | 150 | 1 | 2025-01-31
P2390 Fortis Gulf Robb 414S Contract Change | 29-Hinton/Edson |  | Contract | DTS | 3 | No | 2020-10-14 10:00 | 0 | -0.93 | 2025-11-01
P2396 Georgetown Solar | 45-Strathmore/Blackie |  | Connection | Solar | 4 | Yes | 2020-11-12 10:00 | 230 | 1 | 2025-04-30
P2405 Sollair Solar | 57-Airdrie |  | Connection | Solar | 5 | Yes | 2020-11-30 10:00 | 75 | 0.5 | 2023-12-01
P2407 Fortis Kirby 651S Contract Change | 27-Athabasca/Lac La Biche |  | Contract | DTS | 3 | No | 2020-12-11 10:00 | 0 | -5 | 2026-01-01
P2411 Greengate Jurassic MPC Solar Battery | 48-Empress |  | Connection | Solar + Storage | 5 | Yes | 2021-01-04 10:00 | 300 | 1.5 | 2023-12-31
P2412 Fortis Buffalo Atlee Cluster 4 DER Wind | 48-Empress |  | BTF | Wind | 5 | Yes | 2021-01-11 10:00 | 4.6 | 0 | 2023-10-27
P2418 Greencells Estuary Solar | 48-Empress |  | Connection | Solar | 3 | Yes | 2021-01-28 10:00 | 200 | 1.5 | 2025-06-30
P2421 RESC Big Sky Solar | 48-Empress |  | Connection | Solar | 5 | Yes | 2021-02-10 10:00 | 0 | 0 | 2024-03-15 | 140 | 1 | 2024-08-01
P2422 EER Foothills MPC Solar | 46-High River |  | Connection | Solar | 3 | Yes | 2021-02-12 10:00 | 150 | 1 | 2025-09-30
P2424 ATCO Oyen 767S DER Solar | 42-Hanna |  | BTF | Solar | 5 | Yes | 2021-03-05 10:00 | 12.6 | 0 | 2024-04-01
P2432 Suncor TG1 & TG2 Modification | 25-Fort McMurray |  | BTF | Equipment Change | 5 | Yes | 2021-03-26 10:00 | 0 | 0 | 2024-07-15 | 0 | 0 | 2022-02-07
P2441 Capital Power Halkirk 2 Wind | 36-Alliance/Battle River |  | Connection | Wind | 3 | Yes | 2021-04-23 10:00 | 150 | 1 | 2024-07-01
P2445 Kiwetinohk Homestead MPC Solar | 53-Fort Macleod |  | Connection | Solar | 4 | Yes | 2021-05-03 10:00 | 400 | 1.5 | 2024-11-01
P2446 Fortis Tilley 498S DER Solar | 47-Brooks |  | BTF | Solar + Storage | 5 | Yes | 2021-05-07 10:00 | 19.6 | 0 | 2024-02-29
P2447 Luna MPC Solar Battery | 47-Brooks |  | Connection | Solar + Storage | 3 | Yes | 2021-05-13 10:00 | 465 | 1.5 | 2024-12-01
P2451 Georgetown Battery Addition | 45-Strathmore/Blackie |  | Connection | Battery Storage | 2 | No | 2021-06-10 10:00 | 0 | 101 | 2024-08-01
P2452 ATCO Poplar Hill 790S DER Gas | 20-Grande Prairie |  | BTF | Gas | 5 | Yes | 2021-06-10 10:00 | 0 | 0 | 2023-12-01
P2453 EDTI Edmonton 3 H2 Plant Cogen | 60-Edmonton |  | Connection | Cogen | 4 | Yes | 2021-06-16 10:00 | 20 | 50 | 2024-11-01
P2454 Kiwetinohk Flipi MPC Gas | 30-Drayton Valley |  | Connection | Gas | 3 | Yes | 2021-06-15 10:00 | 466 | 2.5 | 2025-08-07
P2456 Kiwetinohk Opal Gas | 24-Fox Creek |  | Connection | Gas | 3 | Yes | 2021-06-21 10:00 | 98.5 | 0.4 | 2024-12-01
P2457 Fortis Moon Lake DER Solar | 30-Drayton Valley |  | BTF | Solar | 5 | Yes | 2021-06-23 10:00 | 16.75 | 0 | 2024-05-29
P2458 Capital Power Whitla MPC Solar | 04-Medicine Hat |  | Connection | Solar | 2 | Yes | 2021-06-24 10:00 | 88 | 1 | 2024-09-01
P2460 ABO Fox Meadows Wind | 37-Provost |  | Connection | Wind | 3 | Yes | 2021-06-30 10:00 | 150 | 3.15 | 2023-12-01
P2461 Aira Solar | 04-Medicine Hat |  | Connection | Solar | 3 | Yes | 2021-07-07 10:00 | 450 | 1 | 2024-12-20
P2462 Fortis Stony Plain 434S DER Solar | 40-Wabamun |  | BTF | Solar | 5 | Yes | 2021-07-14 10:00 | 12.2 | 0 | 2024-05-29
P2464 Sunnynook Solar Battery | 43-Sheerness |  | Connection | Solar + Storage | 3 | Yes | 2021-07-21 10:00 | 280 | 100 | 2024-08-01
P2465 Enerfin Winnifred Wind Modification | 04-Medicine Hat |  | BTF | Wind | 3 | Yes | 2021-07-22 10:00 | 60 | 0 | 2024-10-01
P2466 PR Prominence Solar | 54-Lethbridge |  | Connection | Solar | 3 | Yes | 2021-07-22 10:00 | 80 | 1 | 2025-09-05
P2467 Pteragen Peace Butte Wind | 04-Medicine Hat |  | Connection | Wind | 3 | Yes | 2021-08-03 10:00 | 120 | 0.1 | 2025-08-31
P2468 ATCO Briker 880S DER Gas | 13-Lloydminster |  | BTF | Gas | 3 | No | 2021-08-09 10:00 | 3.58 | 0 | 2024-08-01
P2469 ATCO Vermilion 710S DER Gas | 13-Lloydminster |  | BTF | Gas | 5 | Yes | 2021-08-09 10:00 | 0 | 0 | 2024-07-01
P2472 Fortis Olds 55S DER Gas | 39-Didsbury |  | BTF | Gas | 5 | Yes | 2021-08-13 10:00 | 4.9 | 0 | 2024-07-01
P2474 Fortis Sylvan Lake 580S DER Gas | 35-Red Deer |  | BTF | Gas | 5 | Yes | 2021-08-13 10:00 | 1.4 | 0 | 2024-06-01
P2488 NGCI Ermineskin Cree Nation Solar | 31-Wetaskiwin |  | Connection | Solar | 2 | Yes | 2021-09-07 10:00 | 80 | 0.5 | 2026-10-31
P2490 TransAlta Tempest MPC Wind | 54-Lethbridge |  | Connection | Wind | 3 | Yes | 2021-09-20 10:00 | 100 | 1 | 2024-09-20
P2499 Kiwetinohk Black Bear Gas | 26-Swan Hills |  | Connection | Gas | 2 | Yes | 2021-10-08 10:00 | 466 | 2.5 | 2025-07-01
P2503 Willow Ridge Wind Battery | 53-Fort Macleod |  | Connection | Wind + Storage | 3 | Yes | 2021-10-15 10:00 | 250 | 1 | 2025-11-28
P2506 Luna 2 MPC Solar Battery | 47-Brooks |  | Connection | Solar + Storage | 3 | Yes | 2021-10-21 10:00 | 465 | 1.5 | 2025-12-01
P2509 Kiwetinohk Granum MPC Solar | 53-Fort Macleod |  | Connection | Solar | 2 | Yes | 2021-10-29 10:00 | 400 | 1.5 | 2024-11-01
P2510 Capital Power Aldersyde MPC Solar | 46-High River |  | Connection | Solar | 2 | Yes | 2021-10-29 10:00 | 200 | 1 | 2025-05-13
P2511 COL Chinook 181S DER Solar | 54-Lethbridge |  | BTF | Solar | 3 | Yes | 2021-11-08 10:00 | 8.75 | 0 | 2024-05-01
P2517 Enfinite Bowmanton MPC Battery | 04-Medicine Hat |  | Connection | Battery Storage | 2 | Yes | 2022-01-20 10:00 | 500 | 500 | 2024-09-02
P2520 Enfinite Foothills MPC Battery | 46-High River |  | Connection | Battery Storage | 2 | Yes | 2022-01-20 10:00 | 400 | 400 | 2024-09-02
P2524 Shell SR Scotford Solar | 33-Fort Saskatchewan |  | BTF | Solar | 5 | Yes | 2021-11-29 10:00 | 0 | 0 | 2023-12-31
P2527 TA Alberta Hydro WaterCharger Battery | 44-Seebe |  | Connection | Battery Storage | 2 | Yes | 2021-12-08 10:00 | 180 | 10 | 2023-12-01
P2528 Fortis Edmonton 95S Contract Change | 60-Edmonton |  | Contract | DTS | 3 | No | 2021-12-16 10:00 | 0 | 7 | 2024-04-01
P2533 Greenlight MPC Gas | 33-Fort Saskatchewan |  | Connection | Gas | 3 | Yes | 2022-01-14 | 466 | 20 | 2025-01-20
P2537 Fortis Duchess 339S DER Solar Battery | 47-Brooks |  | BTF | Solar + Storage | 2 | Yes | 2022-01-25 10:00 | 16.3 | 0 | 2024-09-01
P2540 Cache Rising Sun MPC Solar | 37-Provost |  | Connection | Solar | 2 | Yes | 2022-02-04 10:00 | 125 | 1 | 2024-09-30
P2543 EDTI Castle Downs Load Reliability | 60-Edmonton |  | Connection | Load | 3 | No | 2022-02-14 10:00 | 0 | 14.58 | 2024-09-30
P2548 ATCO Irish Creek 706S DER Gas | 13-Lloydminster |  | BTF | Gas | 3 | Yes | 2022-02-22 10:00 | 0.66 | 0 | 2024-09-01
P2552 Kneehill MPC Solar | 42-Hanna |  | Connection | Solar | 2 | Yes | 2022-03-04 10:00 | 450 | 2 | 2025-07-01
P2553 Dolcy Solar Battery | 37-Provost |  | Connection | Solar + Storage | 2 | Yes | 2022-03-04 10:00 | 200 | 102 | 2025-02-01
P2554 ATCO Goodfare 815S DER Battery | 20-Grande Prairie |  | BTF | Battery Storage | 5 | Yes | 2022-03-02 10:00 | 15.7 | 0 | 2023-11-01
P2555 CP Rolling Hills MPC Wind | 37-Provost |  | Connection | Wind | 2 | Yes | 2022-03-04 10:00 | 190 | 1 | 2025-06-13
P2557 Fortis Lundbreck 513S Contract Change | 53-Fort Macleod |  | Contract | DTS | 3 | No | 2022-03-10 10:00 | 0 | -1.317 | 2024-02-28
P2558 Fortis Hartell 512S Contract Change | 46-High River |  | Contract | DTS | 3 | No | 2022-03-10 10:00 | 0 | -2.1 | 2024-02-28
P2559 Fortis Yarrow Rangeland 995S Contract Change | 55-Glenwood |  | Contract | DTS | 3 | No | 2022-03-10 10:00 | 0 | -2.21 | 2024-02-28
P2560 ATCO Wapiti 823S DER Battery | 20-Grande Prairie |  | BTF | Battery Storage | 5 | Yes | 2022-03-17 10:00 | 31.8 | 0 | 2023-10-01
P2562 Paintearth Wind Phase 2 | 42-Hanna |  | BTF | Wind | 5 | Yes | 2022-03-23 10:00 | 40 | 0.7 | 2023-11-08
P2564 ATCO Bullpound 803S DER Solar | 43-Sheerness |  | BTF | Solar | 3 | Yes | 2022-04-07 10:00 | 14.3 | 0 | 2024-06-01
P2566 Eastervale Solar Battery | 37-Provost |  | Connection | Solar + Storage | 3 | Yes | 2022-04-08 10:00 | 300 | 200 | 2025-03-01
P2568 Aura Peace Butte Solar Battery | 04-Medicine Hat |  | Connection | Solar + Storage | 2 | Yes | 2022-04-15 10:00 | 230 | 1 | 2024-04-01
P2571 Forty Mile Granlea Modification | 04-Medicine Hat |  | BTF | Wind | 5 | Yes | 2022-05-16 10:00 | 25 | 0 | 2023-12-01
P2573 BluEarth Prairie Yarrow MPC Wind | 37-Provost |  | Connection | Wind | 2 | Yes | 2022-05-25 10:00 | 75 | 0.5 | 2024-09-01
P2574 Fortis Aura Provost DER Solar | 37-Provost |  | BTF | Solar | 2 | Yes | 2022-06-01 10:00 | 20.7 | 0 | 2024-11-01
P2581 TransAlta Red Rock MPC Wind | 04-Medicine Hat |  | Connection | Wind | 2 | Yes | 2022-06-10 10:00 | 100 | 3 | 2025-07-31
P2582 Woodcroft Reliability | 60-Edmonton |  | Connection | Equipment Change | 3 | No | 2022-06-16 10:00 | 0 | 0 | 2026-03-25
P2587 Sunhills Solar | 40-Wabamun |  | Connection | Solar | 2 | Yes | 2022-07-07 08:03 | 130 | 1 | 2024-12-31
P2592 Big Rock Solar Battery | 46-High River |  | Connection | Solar + Storage | 2 | Yes | 2022-07-25 10:22 | 100 | 40 | 2025-06-01
P2593 Forty Mile Wind Phase 2 | 04-Medicine Hat |  | BTF | Wind | 2 | Yes | 2022-07-22 10:33 | 134 | 0 | 2025-09-01
P2602 Little Flipi MPC Gas | 35-Red Deer |  | Connection | Gas | 2 | Yes | 2022-08-31 16:30 | 117 | 0.5 | 2025-09-01
P2603 Flatbush 500S Contract Change | 27-Athabasca/Lac La Biche |  | Contract | DTS | 1 | No | 2022-09-08 10:39 | 0 | -1.6 | 2024-06-01
P2611 UK Solar East MPC | 42-Hanna |  | Connection | Solar | 2 | Yes | 2022-09-22 15:29 | 400 | 1 | 2025-01-15
P2614 Dow Fort Sask. Load | 33-Fort Saskatchewan |  | Connection | Wasteheat | 2 | No | 2022-09-28 14:50 | 0 | 231 | 2026-08-15
P2616 Jumbo Solar Battery | 53-Fort Macleod |  | Connection | Solar + Storage | 2 | Yes | 2022-10-11 13:43 | 218 | 1 | 2025-07-10
P2619 Sweetgrass MPC Solar Battery | 53-Fort Macleod |  | Connection | Solar + Storage | 2 | Yes | 2022-10-19 08:39 | 315 | 2 | 2025-07-18
P2627 Sundre 575S DER Solar | 38-Caroline |  | BTF | Solar | 2 | Yes | 2022-11-07 13:23 | 12.6 | 0 | 2024-10-24
P2628 Foster Creek Load | 28-Cold Lake |  | Contract | DTS | 1 | No | 2022-11-07 15:41 | 0 | 41 | 2024-01-01
P2629 Taber Solar | 52-Vauxhall |  | BTF | Solar | 3 | Yes | 2022-11-09 11:11 | 45 | 0 | 2024-10-01
P2630 Berland River Load | 29-Hinton/Edson |  | Connection | Load | 2 | No | 2022-11-14 14:09 | 0 | 37 | 2025-12-17
P2631 Smoky River MPC Wind | 19-Peace River |  | Connection | Wind | 2 | Yes | 2022-11-14 11:26 | 160 | 1 | 2025-10-01
P2635 Coaldale 254S DER Battery | 54-Lethbridge |  | BTF | Battery Storage | 1 | No | 2022-11-18 14:44 | 0 | 0 | 2023-09-22
P2637 Horizon 842S Contract Change | 25-Fort McMurray |  | Contract | STS | 1 | No | 2022-11-28 11:16 | 120 | 0 | 2023-12-01
P2656 Edmonton CCUS Gas | 60-Edmonton |  | Connection | Gas | 2 | Yes | 2023-01-04 11:02 | 115 | 0 | 2026-07-01
P2658 Rimbey 297S DER Gas | 35-Red Deer |  | BTF | Gas | 2 | Yes | 2023-01-04 15:25 | 12.5 | 0 | 2024-03-15
P2659 SCL G3 Modification | 25-Fort McMurray |  | BTF | Equipment Change | 5 | Yes | 2023-01-10 15:46 | 0 | 0 | 2023-10-16
P2666 Base Plant STG4 Modification | 25-Fort McMurray |  | BTF | Equipment Change | 5 | Yes | 2023-02-09 11:47 | 0 | 0 | 2023-10-30
P2667 Grassland 282S Modification | 27-Athabasca/Lac La Biche |  | BTF | Equipment Change | 1 | No | 2023-02-09 10:40 | 0 | 0 | 2023-11-15
P2669 Mannix MPC Solar Battery | 36-Alliance/Battle River |  | Connection | Solar + Storage | 2 | Yes | 2023-02-10 13:46 | 59 | 34 | 2024-06-01
P2674 Foster Creek Modification | 28-Cold Lake |  | BTF | Equipment Change | 1 | No | 2023-02-15 12:02 | 0 | 0 | 2024-07-01
P2676 Kaybob South 3 Cogen | 24-Fox Creek |  | Connection | Cogen | 2 | Yes | 2023-02-22 09:38 | 25 | 0 | 2025-03-01
P2678 SS-37 DER Gas | 06-Calgary |  | BTF | Gas | 2 | No | 2023-02-24 11:55 | 1.1 | 0 | 2025-06-30
P2690 Harvest Sky MPC Solar Battery | 42-Hanna |  | Connection | Solar + Storage | 2 | Yes | 2023-03-28 09:41 | 15 | 14 | 2024-06-01
P2697 Springbrook MPC Solar | 35-Red Deer |  | Connection | Solar | 2 | Yes | 2023-03-29 14:55 | 300 | 1.5 | 2025-11-01
P2709 Cheviot 101S Contract Change | 29-Hinton/Edson |  | Contract | DTS | 1 | No | 2023-05-18 08:46 | 0 | 2 | 2023-12-15
P2714 NRG3 Modification | 26-Swan Hills |  | BTF | Equipment Change | 2 | No | 2023-06-05 08:12 | 0 | 0 | 2024-11-09
P2716 Wapiti 823S Load | 20-Grande Prairie |  | Connection | Load | 1 | No | 2023-06-07 13:22 | 0 | 21.3 | 2026-03-01
P2717 Chin CH9 Modification | 54-Lethbridge |  | BTF | Equipment Change | 1 | No | 2023-06-07 12:56 | 0 | 0 | 2025-01-31
P2723 Wapiti 823S DER Gas | 20-Grande Prairie |  | BTF | Gas | 1 | No | 2023-06-26 14:28 | 0 | 0 | 2024-04-01
P2741 Great Plains Load | 25-Fort McMurray |  | Connection | Load | 1 | No | 2023-07-21 15:37 | 0 | 34 | 2026-02-01
ISD Under Review
P1927 Solar Krafte Brooks (RWE Beargrass) | 47-Brooks |  | Connection | Solar | 5 | Yes | 2017-03-23 10:00 | 360 | 0.99 | Under Review
P2300 Enterprise MPC Solar | 49-Stavely |  | Connection | Solar | 5 | Yes | 2019-11-21 10:00 | 65 | 1 | Under Review
P2314 FortisAlberta Joffre 535S DER Solar 1 | 35-Red Deer |  | BTF | Solar | 5 | Yes | 2020-01-17 10:00 | 22.8 | 0 | Under Review
P2315 FortisAlberta Joffre 535S DER Solar 2 | 35-Red Deer |  | BTF | Solar | 5 | Yes | 2020-01-17 10:00 | 18 | 0 | Under Review
P2383 CP Genesee Unit 6 Gas | 40-Wabamun |  | Connection | Gas | 5 | Yes | 2020-09-17 10:00 | 411 | 0 | Under Review
P2389 CP Genesee Unit 1 Repower ST | 40-Wabamun |  | BTF | Gas | 5 | Yes | 2020-10-13 10:00 | -100 | 0 | Under Review
P2391 Old Elm Wind | 55-Glenwood |  | Connection | Wind | 2 | Yes | 2020-10-14 10:00 | 60 | 0.5 | Under Review
P2409 CP Genesee Unit 7 Gas | 40-Wabamun |  | Connection | Gas | 5 | Yes | 2021-01-04 10:00 | 411 | 3 | Under Review
P2410 CP Genesee 2 Repower ST | 40-Wabamun |  | BTF | Gas | 5 | Yes | 2021-01-04 10:00 | -100 | 0 | Under Review
P2471 Fortis Buford 538S DER Solar | 31-Wetaskiwin |  | BTF | Solar | 3 | Yes | 2021-08-11 10:00 | 15.1 | 0 | Under Review
P2481 TransAlta Riplinger MPC Wind | 55-Glenwood |  | Connection | Wind | 3 | Yes | 2021-08-17 10:00 | 300 | 3 | Under Review
P2482 TransAlta Willow Creek 1 MPC Wind | 53-Fort Macleod |  | Connection | Wind | 2 | Yes | 2021-08-17 10:00 | 70 | 3 | Under Review
P2483 TransAlta Willow Creek 2 MPC Wind | 53-Fort Macleod |  | Connection | Wind | 2 | Yes | 2021-08-17 10:00 | 70 | 3 | Under Review
P2491 Phoenix MPC Solar | 35-Red Deer |  | Connection | Solar | 3 | Yes | 2021-09-17 10:00 | 299 | 1 | Under Review
P2513 Shell Scotford Substation Reliability | 33-Fort Saskatchewan |  | Connection | Other | 3 | No | 2021-11-17 10:00 | 0 | 0 | Under Review
P2514 Sunrise Solar | 53-Fort Macleod |  | Connection | Solar | 3 | Yes | 2021-11-19 10:00 | 75 | 0.5 | Under Review
P2546 Fortis Albchem Beaverhill Creek Load | 33-Fort Saskatchewan |  | Connection | Load | 2 | No | 2022-02-17 10:00 | 0 | 90 | Under Review
P2588 Albright & Wilson 752S Contract Change | 20-Grande Prairie |  | Contract | DTS | 1 | No | 2022-06-30 08:37 | 0 | -32.908 | Under Review
P2615 Datacenters Balzac Load | 57-Airdrie |  | Connection | Load | 2 | No | 2022-10-05 11:43 | 0 | 75 | Under Review
P2632 Monarch 492S DER Battery | 54-Lethbridge |  | BTF | Battery Storage | 1 | No | 2022-11-16 13:56 | 0 | 0 | Under Review
P2634 Vulcan 255S DER Battery | 49-Stavely |  | BTF | Battery Storage | 1 | No | 2022-11-18 14:36 | 0 | 0 | Under Review
P2639 Kearl 9900S Load | 25-Fort McMurray |  | Connection | Load | 1 | No | 2022-11-28 14:31 | 0 | 50 | Under Review
P2705 Jumping Pound 271S Contract Change | 44-Seebe |  | Contract | DTS | 1 | No | 2023-05-01 | 0 | -1.5 | Under Review
On Hold
P2227 FortisAlberta Mearns Area Load | 60-Edmonton |  | Connection | Load | 2 | No | 2019-04-23 10:00 | 0 | 24.1 | On Hold
P2228 FortisAlberta Sangudo Area Load | 40-Wabamun |  | Connection | Load | 2 | No | 2019-04-23 10:00 | 0 | 26 | On Hold
P2229 FortisAlberta Whitecourt Area Load | 26-Swan Hills |  | Connection | Load | 2 | No | 2019-04-23 10:00 | 0 | 20 | On Hold
P2238 Pembina CDH Load | 33-Fort Saskatchewan |  | Connection | Load | 2 | No | 2019-06-03 10:00 | 0 | 27.5 | On Hold
P2538 EDTI Inland Cement Load and Reliability | 60-Edmonton |  | Connection | Load | 2 | No | 2022-02-01 10:00 | 0 | 7.5 | On Hold
Recently Energized
P1719 Stirling WAGF Project | 54-Lethbridge |  | Connection | Wind | 5 | Yes | 2015-10-30 | 113 | 1 | 2023-06-30
P2233 FortisAlberta Jenner 275S Change | 48-Empress |  | BTF | Equipment Change | 5 | Yes | 2019-05-07 10:00 | 0 | 0 | 2021-05-25 | 0 | 0 | 2023-06-02
P2249 FortisAlberta Empress 394S DER Solar 1 | 48-Empress |  | BTF | Solar | 6 | Yes | 2019-06-28 10:00 | 22 | 0 | 2023-06-21
P2250 FortisAlberta Empress 394S DER Solar 2 | 48-Empress |  | BTF | Solar | 6 | Yes | 2019-06-28 10:00 | 15.5 | 0 | 2023-06-21
P2346 ATCO Vilna 777S DER Solar | 56-Vegreville |  | BTF | Solar | 6 | Yes | 2020-04-09 10:00 | 2.7 | 0 | 2023-06-01
P2361 ATCO Youngstown 772S DER Solar | 42-Hanna |  | BTF | Solar | 5 | Yes | 2020-07-15 10:00 | 5.8 | 0 | 2023-07-25
P2371 Fortis High River 65S DER Gas | 46-High River |  | BTF | Gas | 5 | Yes | 2020-08-12 10:00 | 6.9 | 0 | 2023-06-21
P2475 EPC SS-24 DER Solar | 06-Calgary |  | BTF | Solar | 6 | Yes | 2021-08-13 10:00 | 32 | 0 | 2023-07-14
P2515 Fortis Rimbey 297S DER Gas | 35-Red Deer |  | BTF | Gas | 5 | Yes | 2021-11-29 10:00 | 7.25 | 0 | 2023-08-21
P2530 Fortis Nilrem 574S DER Battery | 32-Wainwright |  | BTF | Battery Storage | 5 | Yes | 2022-01-04 10:00 | 38.2 | 0 | 2023-08-23
P2532 Shell ALS1 Modification | 33-Fort Saskatchewan |  | BTF | Equipment Change | 6 | Yes | 2022-01-04 10:00 | 0 | 0 | 2023-06-06
P2608 Fort Macleod 15S Contract Change | 53-Fort Macleod |  | Contract | DTS | 6 | Yes | 2022-09-13 11:10 | 0 | -4.8 | 2023-06-01
P2650 Mercer Hill 728S Contract Change | 20-Grande Prairie |  | Contract | DTS | 6 | Yes | 2022-12-02 08:36 | 0 | -2 | 2023-07-01
Recently Cancelled
P1500 Renewable Energy Service WAGF | 53-Fort Macleod |  | Connection | Wind | 5 | No | 2013-11-18 10:00 | 47 | 1 | Cancelled
P1864 BowArk Drywood Gas | 55-Glenwood |  | Connection | Gas | 5 | No | 2016-09-30 10:00 | 33.9 | 1 | Cancelled
P2008 Greengate Lathom MPC Solar | 47-Brooks |  | Connection | Solar | 3 | No | 2017-10-20 10:00 | 120 | 0.5 | Cancelled
P2140 PBC Paul Band Solar | 40-Wabamun |  | Connection | Solar | 2 | No | 2018-08-20 10:00 | 37 | 0.5 | Cancelled
P2177 FortisAlberta Red Deer 63S DER Solar | 35-Red Deer |  | BTF | Solar | 3 | No | 2018-10-31 09:00 | 18.3 | 0 | Cancelled
P2318 EDF North Slope Solar | 04-Medicine Hat |  | Connection | Solar | 2 | No | 2020-01-29 10:00 | 200 | 3 | Cancelled
P2323 Fortis Taber 83S DER Solar 1 | 52-Vauxhall |  | BTF | Solar | 2 | No | 2020-02-06 10:00 | 16.2 | 0 | Cancelled
P2324 Fortis Taber 83S DER Solar 2 | 52-Vauxhall |  | BTF | Solar | 2 | No | 2020-02-06 10:00 | 14.9 | 0 | Cancelled
P2325 Fortis Taber 83S DER Solar 3 | 52-Vauxhall |  | BTF | Solar | 2 | No | 2020-02-06 10:00 | 11.7 | 0 | Cancelled
P2326 Fortis Taber 83S DER Solar 4 | 52-Vauxhall |  | BTF | Solar | 2 | No | 2020-02-06 10:00 | 13.4 | 0 | Cancelled
P2373 Kirkcaldy MPC Solar | 49-Stavely |  | Connection | Solar | 3 | No | 2020-08-14 10:00 | 350 | 2 | Cancelled
P2416 Potentia Stirling WAGF Phase 2 | 54-Lethbridge |  | BTF | Wind | 2 | No | 2021-01-18 10:00 | 39 | 0 | Cancelled
P2417 Sol Aurora Solar | 33-Fort Saskatchewan |  | Connection | Solar | 3 | No | 2021-01-20 10:00 | 200 | 0 | Cancelled
P2430 Greengate Midnight MPC Solar Battery | 04-Medicine Hat |  | Connection | Solar + Storage | 2 | No | 2021-03-26 10:00 | 465 | 1.5 | Cancelled
P2434 Fortis Blackmud DER Solar | 60-Edmonton |  | BTF | Solar | 3 | No | 2021-04-01 10:00 | 20.3 | 0 | Cancelled
P2435 Fortis Leduc DER Solar | 60-Edmonton |  | BTF | Solar | 3 | No | 2021-04-01 10:00 | 61.9 | 0 | Cancelled
P2436 Fortis Devon DER Solar | 60-Edmonton |  | BTF | Solar | 3 | No | 2021-04-01 10:00 | 20.2 | 0 | Cancelled
P2438 Federation Marguerite Lake CAE Storage | 28-Cold Lake |  | Connection | Compressed Air Energy Storage | 2 | No | 2021-04-07 10:00 | 320 | 125 | Cancelled
P2442 Saamis Solar Park | 04-Medicine Hat |  | Connection | Solar | 3 | No | 2021-04-23 10:00 | 325 | 1 | Cancelled
P2494 Fortis Bullshead 523S DER Solar | 04-Medicine Hat |  | BTF | Solar | 2 | No | 2021-09-23 10:00 | 22.3 | 0 | Cancelled
P2504 SPWC Willow Ridge Battery | 53-Fort Macleod |  | Connection | Battery Storage | 3 | No | 2021-10-15 10:00 | 50 | 50 | Cancelled
P2525 CP Genesee Battery BTF | 40-Wabamun |  | BTF | Battery Storage | 2 | No | 2021-12-01 10:00 | 0 | 5 | Cancelled
P2529 EER Foothills Solar II | 46-High River |  | BTF | Solar | 2 | No | 2022-01-04 10:00 | 100 | 1 | Cancelled
P2535 EDF Bull Trail 2 Wind | 04-Medicine Hat |  | Connection | Wind | 1 | No | 2022-01-14 10:00 | 200 | 2.74 | Cancelled
P2544 PRD Halsbury Solar | 48-Empress |  | BTF | Solar | 2 | No | 2022-02-17 10:00 | 84 | 1 | Cancelled
P2545 EDF Red Rock Wind | 04-Medicine Hat |  | Connection | Wind | 1 | No | 2022-02-22 10:00 | 250 | 3.6 | Cancelled
P2556 Fortis High River 65S DER Solar Battery | 46-High River |  | BTF | Solar + Storage | 2 | No | 2022-03-04 10:00 | 17.1 | 0 | Cancelled
P2563 EDF Pe Na Koyim Wind | 54-Lethbridge |  | Connection | Wind | 2 | No | 2022-03-30 10:00 | 200 | 2.88 | Cancelled
P2565 ATCO Three Hills 770S DER Solar | 42-Hanna |  | BTF | Solar | 3 | No | 2022-04-07 10:00 | 14 | 0 | Cancelled
P2569 Westbridge Red Willow Solar Battery | 36-Alliance/Battle River |  | Connection | Solar + Storage | 2 | No | 2022-04-27 10:00 | 225 | 100 | Cancelled
P2576 Greengate Lacuna MPC Battery | 47-Brooks |  | Connection | Battery Storage | 1 | No | 2022-06-03 10:00 | 465 | 465 | Cancelled
P2584 KALiNA Energy Centre Bluesky MPC Gas | 19-Peace River |  | Connection | Gas | 1 | No | 2022-06-28 15:40 | 466 | 3 | Cancelled
P2585 MIL Generation MPC Gas | 26-Swan Hills |  | Connection | Gas | 2 | No | 2022-06-29 10:00 | 465 | 25 | Cancelled
P2586 KALiNA Energy Centre Mitsue Gas | 21-High Prairie |  | Connection | Gas | 1 | No | 2022-06-29 10:00 | 466 | 3 | Cancelled
P2590 Sunland MPC Solar Battery | 32-Wainwright |  | Connection | Solar + Storage | 1 | No | 2022-07-21 15:40 | 230 | 100 | Cancelled
P2595 CastorWest Solar | 42-Hanna |  | Connection | Solar | 2 | No | 2022-07-29 15:49 | 47 | 0.75 | Cancelled
P2598 Legal Solar | 60-Edmonton |  | Connection | Solar | 1 | No | 2022-08-25 15:14 | 125 | 0.75 | Cancelled
P2600 Spruce Grove North Solar | 60-Edmonton |  | Connection | Solar | 1 | No | 2022-08-25 15:58 | 220 | 0.75 | Cancelled
P2601 Heritage MPC Wind | 53-Fort Macleod |  | Connection | Wind | 1 | No | 2022-08-30 16:05 | 300 | 3 | Cancelled
P2612 Hand Hills Battery | 42-Hanna |  | BTF | Battery Storage | 2 | No | 2022-09-22 09:32 | 10 | 0 | Cancelled
P2620 Hays 421S DER Solar | 52-Vauxhall |  | BTF | Solar | 1 | No | 2022-10-21 10:39 | 19 | 0 | Cancelled
P2621 Hays 421S DER Solar | 52-Vauxhall |  | BTF | Solar | 1 | No | 2022-10-21 11:01 | 20.6 | 0 | Cancelled
P2625 Hays Solar 2 Battery | 52-Vauxhall |  | Connection | Solar + Storage | 2 | No | 2022-11-04 12:43 | 185 | 0.2 | Cancelled
P2626 Strachan 263S DER Gas | 38-Caroline |  | BTF | Gas | 2 | No | 2022-11-07 13:10 | 6.4 | 0 | Cancelled
P2646 Wood Lily MPC Solar | 39-Didsbury |  | Connection | Solar | 1 | No | 2022-12-01 14:11 | 60 | 1 | Cancelled
P2657 St. Albert Solar | 60-Edmonton |  | Connection | Solar | 2 | No | 2023-01-05 13:58 | 400 | 0.75 | Cancelled
P2661 Riverbend 618S DER Solar | 54-Lethbridge |  | BTF | Solar | 1 | No | 2023-01-20 14:42 | 15.4 | 0 | Cancelled
P2668 Sheerness MPC Solar Battery | 43-Sheerness |  | Connection | Solar + Storage | 1 | No | 2023-02-10 11:38 | 310 | 410 | Cancelled
P2670 Paintearth MPC Solar Battery | 36-Alliance/Battle River |  | Connection | Solar + Storage | 1 | No | 2023-02-10 14:40 | 330 | 300 | Cancelled
P2672 Blackfalds 198S DER Gas | 35-Red Deer |  | BTF | Gas | 1 | No | 2023-02-15 11:00 | 7.2 | 0 | Cancelled
P2673 Blackfalds 198S DER Gas | 35-Red Deer |  | BTF | Gas | 1 | No | 2023-02-15 11:16 | 7.7 | 0 | Cancelled
P2675 Huso Cogen | 33-Fort Saskatchewan |  | BTF | Cogen | 1 | No | 2023-01-17 10:55 | 62 | 0 | Cancelled
P2679 High River 65S DER Gas | 46-High River |  | BTF | Gas | 1 | No | 2023-02-24 13:31 | 11 | 0 | Cancelled
P2727 Compass Datacenters Load | 06-Calgary |  | Connection | Load | 1 | No | 2023-07-12 12:18 | 0 | 20 | Cancelled
Status N/A
P1770 NextEra Red Deer Battery Energy Storage System | 42-Hanna |  | Connection | Battery Storage
P1772 Ghost Pine Battery Energy Storage System | 42-Hanna |  | BTF | Battery Storage
P1891 Archer Piikani Solar | 53-Fort Macleod |  | Connection | Solar
P1913 Glenridge Wind | 48-Empress |  | Connection | Wind
P1928 RealPart Calgary Area Solar | 06-Calgary |  | Connection | Solar
P2007 Chiniki Solar | 44-Seebe |  | Connection | Solar
P2068 Four Rivers Wind | 04-Medicine Hat |  | Connection | Wind
P2124 Northland Bow City MPC Solar | 47-Brooks |  | Connection | Solar
P2138 Quill Rocky Mountain Gas | 30-Drayton Valley |  | Connection | Gas
P2176 FortisAlberta Acheson 305S DER Solar | 60-Edmonton |  | BTF | Solar
P2211 ENGIE Buffalo Trail South MPC Wind | 04-Medicine Hat |  | Connection | Wind
P2269 Sunset Solar | 52-Vauxhall |  | Connection | Solar
P2290 ATCO Bridge Creek 798S DER Gas | 20-Grande Prairie |  | BTF | Gas
P2297 FortisAlberta Burdett 368S DER Solar Battery Storage | 52-Vauxhall |  | BTF | Solar + Storage
P2316 Pembina Duvernay Cogen | 24-Fox Creek |  | Connection | Cogen
P2340 TransAlta Sundance Unit 5 Gas | 40-Wabamun |  | Connection | Gas
P2380 ATCO Updike 886S DER Gas | 20-Grande Prairie |  | BTF | Gas
P2386 ATCO Ksituan River 754S DER Gas | 20-Grande Prairie |  | BTF | Gas
P2463 BluEarth Bindloss MPC Solar Battery | 48-Empress |  | Connection | Solar + Storage
P2470 Fortis West Brooks 28S DER Solar | 47-Brooks |  | BTF | Solar
P2636 The Rock MPC Solar | 39-Didsbury |  | Connection | Solar
P2653 SET1 Gas | 60-Edmonton |  | BTF | Gas
P2692 Plains Solar Battery | 04-Medicine Hat |  | Connection | Solar + Storage
Note 1: Only projects that have an accepted SASR and have paid the processing fee show up on the Connection Project List in the category titled “Processed For Cluster”. In addition to the projects shown above in the category titled "Processed for Cluster", the AESO has received 121 additional SASRs for Cluster 1. The AESO is continuing to review these SASRs.