## Instructions
TRANSMISSION PROJECT COST ESTIMATE TEMPLATE NOTES
Tab Name | Description | Facility Owner action | General comments
PCP 0 | Summarizes the original budget and changes in estimates. | PCP tab with cost data is linked to other tabs; the Facility Owner is not required to enter any data in this tab. In the column L "Status"; the Facility Owner must pick the current status for each PCP. For example: If the Facility Owner is reporting PCP #1 to AESO, then the PCP #1 status will be "Current" 1. Original Budget: Original Service Proposal estimate 2. Authorized Changes: Original Budget plus approved change proposals 3. Pending PCPs: change proposals not processed 3. Current PCP: current change proposal being submitted 4. Rejected PCP: rejected change proposals 5. PCP Numbering: For properly sequenced, submit all non-cost changes with an updated spreadsheet; assigning a PCP #; and indicated "non-cost change" or "ISD change only" in the comments | 1. Any new number or change to an old number is colour coded in blue 2. To insert a new line - copy an exiting row and use "insert copied cells" function to paste the formula 3. Columns can be closed or opened by "group" function for easy operation 4. If the formula is already replaced, to retrieve the formula copy and paste the formula from a previous related cell 5.The rejected PCP claim will not be carried over to next PCP total, the claimed changes remain in "Change" columns only 6. If additional rows are required, always "COPY" and "INSERT" the copied, otherwise the internal links between spreadsheets will be broken 7. The Risk Simulation analysis section in Tab 7 is hidden. Unhide if required.
Sum 1 | The data in summary sheet is linked to respective detailed tabs. For example: substation summary cost is automatically calculated from the "Substation-Tab3" Note that Other costs do not have detailed tabs; thus, these costs must input in this tab. The terms of "AFUDC", "IDC", "E&S" and "Overhead" are provided in dropdown lists for users' discretion | To enter a new change proposal 1. Cells A-E is the original Service Proposal budget and will not change 2. Cell "G2" enter the change proposal number 3. Cell "H2" enter the estimate type 3. The cost change details are entered in either "system change" or "participant change" column or both. The spreadsheet automatically calculates the new total of system and participant costs.
Line(OH) 2a Line(UG) 2b Subs 3 Tcom 4 | Enter the project details in each of the facility tabs. Enter the project escalation in Escn 8 | The Facility Owner will need to provide a change proposal, estimate update and final cost details for each facility if applicable; and will need to enter the information in all tabs similar to how the initial service proposal estimate was entered
Owrs 5
Labor 6
Cont (Sys) 7a Cont (Part) 7b
Escn 8
Salv 9
Proc 10 | Report the major procurement either sole sourced or competitive
Capital Mtnc 11 | Input capital maintenance cost if applicable
ISO Tariff 12 | Input Replacement Cost New if applicable | Replacement Cost New (ISO Tariff 12 Tab) Usage and Instructions Replacement Cost New (RCN) The actual project costs for a connection project are not necessarily what is ultimately paid by an MP. As an example, an MP doesn’t pay book value for a used transformer. The ISO Tariff tab is used for calculating additional costs arising from the application of the ISO tariff regarding the following to be charged to the MP as a construction contribution: 1. Replacement Cost New (RCN). The tariff dictates that the connection project costs must be based on the RCN value of equipment, which is the current cost of similar new equipment. 2. Breaker and a half schemes. When there are two breakers at an existing substation and a new project proposes to add one breaker for an MP, the additional cost of half of a breaker (installed) is charged to the MP. 3. Any other costs as deemed appropriate by the AESO. 4. Enter the RCN and Book Value in the appropriate tabs, ensure the book value costs are the same as in the main estimate tabs (Line(OH) / Subs). 5. These are manual entries for RCN and Book Value columns, the total additional costs are calculated.
ID Service Proposal | https://www.aeso.ca/assets/Information-Documents/2015-002R-Service-Proposals-and-Cost-Estimating-2022-03-04.pdf | TFO and Market Participant are required to follow the ID
Version Control | This template is to be used for all classes of estimates and final costs, including NID and OOM estimates. Note that it is only the service proposal estimate and all other cost updates that follow that would be included in this consolidated template. | Submit all the estimates including the following in the file name: Service Proposal, Project Change Proposal, Service Proposal P&L, Final Cost Estimate and Final Cost Report #; i.e. "P1234 Service Proposal Cost Estimate V1.xlsx"
Version | aeso cost template.v5.xlsx
Date Issued | 2023-04-21

## PCP 0
| 3 | 4 | 5 | 6 | 5 | [8 empty] | 3 | 9 | 17 | 25 | 33 | 41 | 49 | 57 | 65 | 73 | 81 | 89 | 97 | 105 | 113 | 121 | 129 | 137 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | #REF! | #REF! | #REF! | #REF! | #REF!
Select the base point | [13 empty] | Original Estimate | PCP #1 | PCP #2 | PCP #3 | PCP #4 | PCP #5 | PCP #6 | PCP #7 | PCP #8 | PCP #9 | PCP #10 | PCP #11 | PCP #12 | Final Cost Report #13 | PCP #14 | PCP #15 | PCP #16 | PCP #17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
TRANSMISSION PROJECT BUDGET SUMMARY
| Original Budget (based off of estimate) | Authorized Changes (Total accepted changes) | All previous Pending Changes | Rejected PCPs | Current PCP | Revised Authorized Budget (Original + Authorized) | Revised Budget with Pending Changes | Difference (from Original Budget) | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
[9 empty] | Reports | Status | Summary Change | Date |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF!
TRANSMISSION LINE | [8 empty] | Original Estimate |  | 0 |  | TRANSMISSION LINE
Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PCP #1 |  | 0 |  | Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
Labour | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PCP #2 |  | 0 |  | Labour | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
Supply & Install | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PCP #3 |  | 0 |  | Supply & Install | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
TOTAL TRANSMISSION LINE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PCP #4 |  | 0 |  | TOTAL TRANSMISSION LINE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
SUBSTATION | [8 empty] | PCP #5 |  | 0 |  | SUBSTATION
Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PCP #6 |  | 0 |  | Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
Labour | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PCP #7 |  | 0 |  | Labour | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
Supply & Install | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PCP #8 |  | 0 |  | Supply & Install | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
TOTAL SUBSTATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PCP #9 |  | 0 |  | TOTAL SUBSTATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
TELECOMMUNICATION | [8 empty] | PCP #10 |  | 0 |  | TELECOMMUNICATION
Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PCP #11 |  | 0 |  | Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
Labour | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PCP #12 |  | 0 |  | Labour | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
Supply & Install | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Final Cost Report #13 |  | 0 |  | Supply & Install | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
TOTAL TELECOMMUNCATIONS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PCP #14 |  | 0 |  | TOTAL TELECOMMUNCATIONS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
OWNERS | [8 empty] | PCP #15 |  | 0 |  | OWNERS
Pre-SP Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PCP #16 |  | 0 |  | Pre-PPS cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
Service Proposal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PCP #17 |  | 0 |  | Proposal to Provide Service | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
Facility Applications | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Facility Applications | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
Regulatory & Compliance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Regulatory & Compliance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
Land Rights - Easements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Land Rights - Easements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
Land - Damage Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Land - Damage Claims | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
Land - Acquisitions | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Land - Acquisitions | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
Land - Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Land - Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
TOTAL OWNERS COST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | TOTAL OWNERS COST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
DISTRIBUTED | [8 empty] | 0 |  | 0 |  | DISTRIBUTED
Procurement Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Procurement Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
Project Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Project Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
Construction Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Construction Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
Contingency | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Contingency | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
Escalation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Escalation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
TOTAL DISTRIBUTED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | TOTAL DISTRIBUTED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
SALVAGE | [12 empty] | SALVAGE
Transmission Line Labour | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Transmission Line Labour | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
Substation Labour | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Substation Labour | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
Telecom Labour | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Telecom Labour | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
Land Remediation and Reclamation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Land Remediation and Reclamation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
TOTAL SALVAGE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | TOTAL SALVAGE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
OTHER COSTS | [12 empty] | OTHER COSTS
AFUDC (IDC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | AFUDC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
E&S/Overhead | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | E&S/Overhead | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
TOTAL OTHER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | TOTAL OTHER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
TOTAL PROJECT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | TOTAL PROJECT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
Version | aeso cost template.v5.xlsx
Date Issued | 2023-04-21
[14 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37
Note on B2: Base point for Original Budget Empty if it is the Original PPS Estimate
Note on C2: Approved Change Proposal
Note on D2: Previous submitted Change Proposal
Note on E2: Jahnavi Gopi Krishnan: Rejected CP
Note on F2: Current Change Proposal

## Sum 1
TRANSMISSION PROJECT COST SUMMARY | [9 empty] | XX UPGRADE | PXXXX | 0 |  |  |  |  | XX UPGRADE | PXXXX | 0 |  |  |  |  | XX UPGRADE | PXXXX | 0 |  |  |  |  | XX UPGRADE | PXXXX | 0 |  |  |  |  | XX UPGRADE | PXXXX | 0 |  |  |  |  | XX UPGRADE | PXXXX | 0 |  |  |  |  | XX UPGRADE | PXXXX | 0 |  |  |  |  | XX UPGRADE | PXXXX | 0 |  |  |  |  | XX UPGRADE | PXXXX | 0 |  |  |  |  | XX UPGRADE | PXXXX | 0 |  |  |  |  | XX UPGRADE | PXXXX | 0 |  |  |  |  | XX UPGRADE | PXXXX | 0 |  |  |  |  | XX UPGRADE | PXXXX | 0 |  |  |  |  | XX UPGRADE | PXXXX | 0 |  |  |  |  | XX UPGRADE | PXXXX | 0 |  |  |  |  | XX UPGRADE | PXXXX | 0 |  |  |  |  | XX UPGRADE | PXXXX | 0
AESO Project Name & No. | XX UPGRADE |  | PXXXX |  |  | 1 | PCP | PCP #1 | 0 | PCP # 1 |  | 11 | 2 | PCP | PCP #2 | 0 | PCP # 2 |  | 18 | 3 | PCP | PCP #3 | 0 | PCP # 3 |  | 25 | 4 | PCP | PCP #4 | 0 | PCP # 4 |  | 32 | 5 | PCP | PCP #5 | 0 | PCP # 5 |  | 39 | 6 | PCP | PCP #6 | 0 | PCP # 6 |  | 46 | 7 | PCP | PCP #7 | 0 | PCP # 7 |  | 53 | 8 | PCP | PCP #8 | 0 | PCP # 8 |  | 60 | 9 | PCP | PCP #9 | 0 | PCP # 9 |  | 67 | 10 | PCP | PCP #10 | 0 | PCP # 10 |  | 74 | 11 | PCP | PCP #11 | 0 | PCP # 11 |  | 81 | 12 | PCP | PCP #12 | 0 | PCP # 12 |  | 88 | 13 | Final Cost Report | Final Cost Report #13 | 0 | Final Cost Report # 13 |  | 95 | 14 | PCP | PCP #14 | 0 | PCP # 14 |  | 102 | 15 | PCP | PCP #15 | 0 | PCP # 15 |  | 109 | 16 | PCP | PCP #16 | 0 | PCP # 16 |  | 116 | 17 | PCP | PCP #17 | 0 | PCP # 17 |  | 123
Prepared by: | [6 empty] | -2 | -1 | 0 | 2 | 3 | 10 |  | -2 | -1 | 0 | 2 | 3 | 17 |  | -2 | -1 | 0 | 2 | 3 | 24 |  | -2 | -1 | 0 | 2 | 3 | 31 |  | -2 | -1 | 0 | 2 | 3 | 38 |  | -2 | -1 | 0 | 2 | 3 | 45 |  | -2 | -1 | 0 | 2 | 3 | 52 |  | -2 | -1 | 0 | 2 | 3 | 59 |  | -2 | -1 | 0 | 2 | 3 | 66 |  | -2 | -1 | 0 | 2 | 3 | 73 |  | -2 | -1 | 0 | 2 | 3 | 80 |  | -2 | -1 | 0 | 2 | 3 | 87 |  | -2 | -1 | 0 | 2 | 3 | 94 |  | -2 | -1 | 0 | 2 | 3 | 101 |  | -2 | -1 | 0 | 2 | 3 | 108 |  | -2 | -1 | 0 | 2 | 3 | 115 |  | -2 | -1 | 0 | 2 | 3 | 122
AACE Class: |  | Estimate Basis |  |  |  |  | -2 | -1 | 0 | 2 | 3 | 10 |  | -2 | -1 | 0 | 2 | 3 | 17 |  | -2 | -1 | 0 | 2 | 3 | 24 |  | -2 | -1 | 0 | 2 | 3 | 31 |  | -2 | -1 | 0 | 2 | 3 | 38 |  | -2 | -1 | 0 | 2 | 3 | 45 |  | -2 | -1 | 0 | 2 | 3 | 52 |  | -2 | -1 | 0 | 2 | 3 | 59 |  | -2 | -1 | 0 | 2 | 3 | 66 |  | -2 | -1 | 0 | 2 | 3 | 73 |  | -2 | -1 | 0 | 2 | 3 | 80 |  | -2 | -1 | 0 | 2 | 3 | 87 |  | -2 | -1 | 0 | 2 | 3 | 94 |  | -2 | -1 | 0 | 2 | 3 | 101 |  | -2 | -1 | 0 | 2 | 3 | 108 |  | -2 | -1 | 0 | 2 | 3 | 115 |  | -2 | -1 | 0 | 2 | 3 | 122
High Range |  | Low Range |  |  |  |  | -1 | 12 | -1 |  |  | 13 |  | -1 | 15 | -1 |  |  | 16 |  | -1 | 18 | -1 |  |  | 19 |  | -1 | 21 | -1 |  |  | 22 |  | -1 | 24 | -1 |  |  | 25 |  | -1 | 27 | -1 |  |  | 28 |  | -1 | 30 | -1 |  |  | 31 |  | -1 | 33 | -1 |  |  | 34 |  | -1 | 36 | -1 |  |  | 37 |  | -1 | 39 | -1 |  |  | 40 |  | -1 | 42 | -1 |  |  | 43 |  | -1 | 45 | -1 |  |  | 46 |  | -1 | 48 | -1 |  |  | 49 |  | -1 | 51 | -1 |  |  | 52 |  | -1 | 54 | -1 |  |  | 55 |  | -1 | 57 | -1 |  |  | 58 |  | -1 | 60 | -1 |  |  | 61
Date of Estimate: |  | Base Year $ |  |  |  |  | -1 | 0 | 1 | 2 | 3 | 10 |  | -1 | 0 | 1 | 2 | 3 | 18 |  | -1 | 0 | 1 | 2 | 3 | 26 |  | -1 | 0 | 1 | 2 | 3 | 34 |  | -1 | 0 | 1 | 2 | 3 | 42 |  | -1 | 0 | 1 | 2 | 3 | 50 |  | -1 | 0 | 1 | 2 | 3 | 58 |  | -1 | 0 | 1 | 2 | 3 | 66 |  | -1 | 0 | 1 | 2 | 3 | 74 |  | -1 | 0 | 1 | 2 | 3 | 82 |  | -1 | 0 | 1 | 2 | 3 | 90 |  | -1 | 0 | 1 | 2 | 3 | 98 |  | -1 | 0 | 1 | 2 | 3 | 106 |  | -1 | 0 | 1 | 2 | 3 | 114 |  | -1 | 0 | 1 | 2 | 3 | 122 |  | -1 | 0 | 1 | 2 | 3 | 130 |  | -1 | 0 | 1 | 2 | 3 | 138
In Service Date |  | In Service Year $
| SYSTEM | PARTICIPANT | TOTAL | ASSUMPTIONS |  |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | COMMENT ON CHANGE |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | COMMENT ON CHANGE |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | COMMENT ON CHANGE |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | COMMENT ON CHANGE |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | COMMENT ON CHANGE |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | COMMENT ON CHANGE |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | COMMENT ON CHANGE |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | COMMENT ON CHANGE |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | COMMENT ON CHANGE |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | COMMENT ON CHANGE |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | COMMENT ON CHANGE |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | COMMENT ON CHANGE |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | COMMENT ON CHANGE |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | COMMENT ON CHANGE |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | COMMENT ON CHANGE |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | COMMENT ON CHANGE |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | COMMENT ON CHANGE
TRANSMISSION LINE |  |  |  |  | To be filled in on Tab 2
Material | 0 | 0 | 0 |  |  | s_LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Labour | 0 | 0 | 0 |  |  | s_LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Supply & Install | 0 | 0 | 0 |  |  | s_LS | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
TOTAL TRANSMISSION LINE | 0 | 0 | 0 |  |  | s_LT | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
SUBSTATION |  |  |  |  | To be filled in on Tab 3
Material | 0 | 0 | 0 |  |  | s_SM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Labour | 0 | 0 | 0 |  |  | s_SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Supply & Install | 0 | 0 | 0 |  |  | s_SLS | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
TOTAL SUBSTATION | 0 | 0 | 0 |  |  | s_ST | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
TELECOMMUNICATION |  |  |  |  | To be filled in on Tab 4
Material | 0 | 0 | 0 |  |  | s_TM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Labour | 0 | 0 | 0 |  |  | s_TL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Supply & Install | 0 | 0 | 0 |  |  | s_TS | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
TOTAL TELECOMMUNCATIONS | 0 | 0 | 0 |  |  | s_TT | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
OWNERS
Pre-SP Cost | 0 | 0 | 0 |  | Provide an explanation of the cost breakdown for deliverables in Stages 0,1,2,3; i.e. Functional Spec, Study Scope, ESR, Connection Plan. | s_PS | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Service Proposal | 0 | 0 | 0 |  |  | s_SP | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Facility Applications | 0 | 0 | 0 |  |  | s_FA | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Regulatory & Compliance | 0 | 0 | 0 |  | Regularory costs include: Information Requests, Cost Oversight Manager activities, Compliance or Performance audits, etc. | s_RC | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Land Rights - Easements | 0 | 0 | 0 |  |  | s_LE | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Land - Damage Claims | 0 | 0 | 0 |  | Break down by facility if possible | s_LDC | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Land - Acquisitions | 0 | 0 | 0 |  |  | s_LA | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Land - Other | 0 | 0 | 0 |  | TFO or AESO to consolidate Land costs (acquisition, damage claims, easements) into Other category, if deemed an issue. | s_LO | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
TOTAL OWNERS COST | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
DISTRIBUTED
Procurement Management | 0 | 0 | 0 |  | To be filled in on Tab 6 | s_PR | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Project Management | 0 | 0 | 0 |  | To be filled in on Tab 6 | s_PM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Construction Management | 0 | 0 | 0 |  | To be filled in on Tab 6 | s_CM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Contingency | 0 | 0 | 0 |  | To be filled in on Tab 7 (Customer and System Risk allocated based on prorated customer and system costs) |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Escalation | 0 | 0 | 0 |  | To be filled in on Tab 8 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
TOTAL DISTRIBUTED | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
SALVAGE
Transmission Line Labour | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Substation Labour | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Telecom Labour | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Land Remediation and Reclamation |  |  | 0 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
TOTAL SALVAGE | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
OTHER COSTS
AFUDC |  |  | 0 |  | AFUDC applies to project costs that are not funded through construction contribution. |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
E&S |  |  | 0 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
TOTAL OTHER | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
TOTAL PROJECT | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Replacement Cost New Items |  |  | 0
Additional Particpant Costs |  |  | 0
Other Connection |  |  | 0
Grand Total |  |  | 0
Version | aeso cost template.v5.xlsx
Date Issued | 2023-04-21
0 | [5 empty] | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 5 | [6 empty] | 6 | [6 empty] | 7 | [6 empty] | 8 | [6 empty] | 9 | [6 empty] | 10 | [6 empty] | 11 | [6 empty] | 12 | [6 empty] | 13 | [6 empty] | 14 | [6 empty] | 15 | [6 empty] | 16 | [6 empty] | 17

## Line(OH) 2a
TRANSMISSION LINE OVERHEAD SUMMARY | [6 empty] | 1 | PCP | PCP #1 | 0 | PCP # 1 |  |  | 2 | PCP | PCP #2 | 0 | PCP # 2 |  |  | 3 | PCP | PCP #3 | 0 | PCP # 3 |  |  | 4 | PCP | PCP #4 | 0 | PCP # 4 |  |  | 5 | PCP | PCP #5 | 0 | PCP # 5 |  |  | 6 | PCP | PCP #6 | 0 | PCP # 6 |  |  | 7 | PCP | PCP #7 | 0 | PCP # 7 |  |  | 8 | PCP | PCP #8 | 0 | PCP # 8 |  |  | 9 | PCP | PCP #9 | 0 | PCP # 9 |  |  | 10 | PCP | PCP #10 | 0 | PCP # 10 |  |  | 11 | PCP | PCP #11 | 0 | PCP # 11 |  |  | 12 | PCP | PCP #12 | 0 | PCP # 12 |  |  | 13 | Final Cost Report | Final Cost Report #13 | 0 | Final Cost Report # 13 |  |  | 14 | PCP | PCP #14 | 0 | PCP # 14 |  |  | 15 | PCP | PCP #15 | 0 | PCP # 15 |  |  | 16 | PCP | PCP #16 | 0 | PCP # 16 |  |  | 17 | PCP | PCP #17 | 0 | PCP # 17
|  | SYSTEM | PARTICIPANT | TOTAL | ASSUMPTIONS |  |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments
Line <Line#, Location - from substation to substation> | [9 empty] | 5 | Line <Line#, Location - from substation to substation> | [5 empty] | 11 | Line <Line#, Location - from substation to substation> | [5 empty] | 18 | Line <Line#, Location - from substation to substation> | [5 empty] | 25 | Line <Line#, Location - from substation to substation> | [5 empty] | 32 | Line <Line#, Location - from substation to substation> | [5 empty] | 39 | Line <Line#, Location - from substation to substation> | [5 empty] | 46 | Line <Line#, Location - from substation to substation> | [5 empty] | 53 | Line <Line#, Location - from substation to substation> | [5 empty] | 60 | Line <Line#, Location - from substation to substation> | [5 empty] | 67 | Line <Line#, Location - from substation to substation> | [5 empty] | 74 | Line <Line#, Location - from substation to substation> | [5 empty] | 81 | Line <Line#, Location - from substation to substation> | [5 empty] | 88 | Line <Line#, Location - from substation to substation> | [5 empty] | 95 | Line <Line#, Location - from substation to substation> | [5 empty] | 102 | Line <Line#, Location - from substation to substation> | [5 empty] | 109 | Line <Line#, Location - from substation to substation> | [5 empty] | 116 | Line <Line#, Location - from substation to substation>
MATERIALS
Foundations |  | 0 | 0 | 0 |  | Include: Concrete | s_LMF | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Screwpiles | quantity |  |  | 0 |  |  | LMF | 0 | 0 | 0 |  |  |  | LMF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Driven Piles | quantity |  |  | 0 |  |  | LMF | 0 | 0 | 0 |  |  |  | LMF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Caisson Piles | quantity |  |  | 0 |  |  | LMF | 0 | 0 | 0 |  |  |  | LMF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other type | quantity |  |  | 0 |  |  | LMF | 0 | 0 | 0 |  |  |  | LMF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other type | quantity |  |  | 0 |  |  | LMF | 0 | 0 | 0 |  |  |  | LMF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structures |  | 0 | 0 | 0 |  |  | s_LMS | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Structure Type | list all angles and quantities |  |  | 0 |  | Include Structure Type/Family (Lattice Tower, Steel Pole, Wood Pole, H-frame, etc.) | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structure Type | list all angles and quantities |  |  | 0 |  | Include Angle (Tangent, Light Angle, Dead end, etc.) | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structure Type | list all angles and quantities |  |  | 0 |  | Explain structure, family, breakdown. | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structure Type | list all angles and quantities |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structure Type | list all angles and quantities |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structure Type | list all angles and quantities |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Hardware |  | 0 | 0 | 0 |  |  | s_LMH | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Hardware |  |  |  | 0 |  |  | LMH | 0 | 0 | 0 |  |  |  | LMH | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Transmission Wires |  | 0 | 0 | 0 |  |  | s_LMW | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Conductor | type, size, bundle |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Conductor | type, size, bundle |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Shield Wire | type, size |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
OPGW | type, size |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL MATERIALS |  | 0 | 0 | 0 |  |  | s_LM | 0 | 0 | 0 | 0 | 0 |  | L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
LABOUR
Detailed Engineering |  | 0 | 0 | 0 |  |  | s_LLE | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Line |  |  |  | 0 |  |  | LLE | 0 | 0 | 0 |  |  |  | LLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Civil |  |  |  | 0 |  |  | LLE | 0 | 0 | 0 |  |  |  | LLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Geotechnical |  |  |  | 0 |  |  | LLE | 0 | 0 | 0 |  |  |  | LLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Survey |  | 0 | 0 | 0 |  |  | s_LLS | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Survey - ROW and structures |  |  |  | 0 |  |  | LLS | 0 | 0 | 0 |  |  |  | LLS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Right of Way |  | 0 | 0 | 0 |  |  | s_LLR | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Site Preparation | ha |  |  | 0 |  | Include: clearing, brushing, earthworks, grading | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Environment Management |  |  |  | 0 |  | Include: wash station, erosion control. May be included here or under Distributed Labour - Construction Management (Tab 5). | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Road(s) | km |  |  | 0 |  | Include: permanent and temporary roads | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Matting Rental | type, quantity, duration |  |  | 0 |  |  | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Matting Lay/Removal | hours |  |  | 0 |  |  | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Construction |  | 0 | 0 | 0 |  |  | s_LLC | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Foundation |  |  |  | 0 |  | Include soil type assumption | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structure Installation |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Stringing - Shieldwires & Conductor |  |  |  | 0 |  | Include: line conductors and OHSW & OPGW | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
AC Mitigation |  |  |  | 0 |  | Mitigation of a Transmission AC circuit (current) corroding a parallel metallic object; i.e. pipeline, railway | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Major Equipment Rental | type, number, duration |  |  | 0 |  | Include: only major or special type of rental; i.e. helicopter, large cranes | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Field Supervision |  |  |  | 0 |  | Include: field supervisors, managers. May be included here or in Distributed Labour - Construction Managmeent (Tab 5) | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Indirects |  |  |  | 0 |  | Includes: trailers, fences, water, porta potties, etc. May be included here or under Distributed Labour - Construction Management (Tab 5). | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Mobilization / demobilization | number and size |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Yards | number and size |  |  | 0 |  | Include: assembly, lay-down, fly, storage yards, security | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Camp Services & Catering | size and duration |  |  | 0 |  | Include: camp services, security, etc. | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Commissioning |  | 0 | 0 | 0 |  |  | s_LLM | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Commissioning |  |  |  | 0 |  |  | LLM | 0 | 0 | 0 |  |  |  | LLM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL LABOUR |  | 0 | 0 | 0 |  |  | s_LL | 0 | 0 | 0 | 0 | 0 |  | L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
SUPPLY & INSTALL
Supply & Install | type / quality |  |  | 0 |  |  | LS | 0 | 0 | 0 |  |  |  | LS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | LS | 0 | 0 | 0 |  |  |  | LS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | LS | 0 | 0 | 0 |  |  |  | LS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL SUPPLY & INSTALL |  | 0 | 0 | 0 |  |  | s_LS | 0 | 0 | 0 | 0 | 0 |  | L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
SUBTOTAL LINE (1) |  | 0 | 0 | 0 |  |  | LT | 0 | 0 | 0 | 0 | 0 |  | LT | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Line <Line#, Location - from substation to substation> | [10 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation>
MATERIALS
Foundations |  | 0 | 0 | 0 |  | Include: Concrete | s_LMF | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Screwpiles | quantity |  |  | 0 |  |  | LMF | 0 | 0 | 0 |  |  |  | LMF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Driven Piles | quantity |  |  | 0 |  |  | LMF | 0 | 0 | 0 |  |  |  | LMF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Caisson Piles | quantity |  |  | 0 |  |  | LMF | 0 | 0 | 0 |  |  |  | LMF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other type | quantity |  |  | 0 |  |  | LMF | 0 | 0 | 0 |  |  |  | LMF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other type | quantity |  |  | 0 |  |  | LMF | 0 | 0 | 0 |  |  |  | LMF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structures |  | 0 | 0 | 0 |  |  | s_LMS | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Structure Type | list all angles and quantities |  |  | 0 |  | Include Structure Type/Family (Lattice Tower, Steel Pole, Wood Pole, H-frame, etc.) | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structure Type | list all angles and quantities |  |  | 0 |  | Include Angle (Tangent, Light Angle, Dead end, etc.) | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structure Type | list all angles and quantities |  |  | 0 |  | Explain structure, family, breakdown. | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structure Type | list all angles and quantities |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structure Type | list all angles and quantities |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structure Type | list all angles and quantities |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Hardware |  | 0 | 0 | 0 |  |  | s_LMH | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Hardware |  |  |  | 0 |  |  | LMH | 0 | 0 | 0 |  |  |  | LMH | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Transmission Wires |  | 0 | 0 | 0 |  |  | s_LMW | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Conductor | type, size, bundle |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Conductor | type, size, bundle |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Shield Wire | type, size |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
OPGW | type, size |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL MATERIALS |  | 0 | 0 | 0 |  |  | s_LM | 0 | 0 | 0 | 0 | 0 |  | L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
LABOUR
Detailed Engineering |  | 0 | 0 | 0 |  |  | s_LLE | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Line |  |  |  | 0 |  |  | LLE | 0 | 0 | 0 |  |  |  | LLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Civil |  |  |  | 0 |  |  | LLE | 0 | 0 | 0 |  |  |  | LLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Geotechnical |  |  |  | 0 |  |  | LLE | 0 | 0 | 0 |  |  |  | LLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Survey |  | 0 | 0 | 0 |  |  | s_LLS | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Survey - ROW and structures |  |  |  | 0 |  |  | LLS | 0 | 0 | 0 |  |  |  | LLS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Right of Way |  | 0 | 0 | 0 |  |  | s_LLR | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Site Preparation | ha |  |  | 0 |  | Include: clearing, brushing, earthworks, grading | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Environment Management |  |  |  | 0 |  | Include: wash station, erosion control. May be included here or under Distributed Labour - Construction Management (Tab 5). | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Road(s) | km |  |  | 0 |  | Include: permanent and temporary roads | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Matting Rental | type, quantity, duration |  |  | 0 |  |  | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Matting Lay/Removal | hours |  |  | 0 |  |  | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Construction |  | 0 | 0 | 0 |  |  | s_LLC | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Foundation |  |  |  | 0 |  | Include soil type assumption | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structure Installation |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Stringing - Shieldwires & Conductor |  |  |  | 0 |  | Include: line conductors and OHSW & OPGW | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
AC Mitigation |  |  |  | 0 |  | Mitigation of a Transmission AC circuit (current) corroding a parallel metallic object; i.e. pipeline, railway | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Major Equipment Rental | type, number, duration |  |  | 0 |  | Include: only major or special type of rental; i.e. helicopter, large cranes | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Field Supervision |  |  |  | 0 |  | Include: field supervisors, managers. May be included here or in Distributed Labour - Construction Managmeent (Tab 5) | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Indirects |  |  |  | 0 |  | Includes: trailers, fences, water, porta potties, etc. May be included here or in Distributed Labour - Construction Managmeent (Tab 5). | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Mobilization / Demobilization | number and size |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Yards | number and size |  |  | 0 |  | Include: assembly, lay-down, fly, storage yards | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Camp Services & Catering | size and duration |  |  | 0 |  | Include: camp services, security, etc. | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Commissioning |  | 0 | 0 | 0 |  |  | s_LLM | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Commissioning |  |  |  | 0 |  |  | LLM | 0 | 0 | 0 |  |  |  | LLM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL LABOUR |  | 0 | 0 | 0 |  |  | s_LL | 0 | 0 | 0 | 0 | 0 |  | L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
SUPPLY & INSTALL
Supply & Install | type / quality |  |  | 0 |  |  | LS | 0 | 0 | 0 |  |  |  | LS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | LS | 0 | 0 | 0 |  |  |  | LS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | LS | 0 | 0 | 0 |  |  |  | LS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL SUPPLY & INSTALL |  | 0 | 0 | 0 |  |  | s_LS | 0 | 0 | 0 | 0 | 0 |  | L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
SUBTOTAL LINE (2) |  | 0 | 0 | 0 |  |  | LT | 0 | 0 | 0 | 0 | 0 |  | LT | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Line <Line#, Location - from substation to substation> | [10 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation>
MATERIALS
Foundations |  | 0 | 0 | 0 |  | Include: Concrete | s_LMF | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Screwpiles | quantity |  |  | 0 |  |  | LMF | 0 | 0 | 0 |  |  |  | LMF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Driven Piles | quantity |  |  | 0 |  |  | LMF | 0 | 0 | 0 |  |  |  | LMF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Caisson Piles | quantity |  |  | 0 |  |  | LMF | 0 | 0 | 0 |  |  |  | LMF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other type | quantity |  |  | 0 |  |  | LMF | 0 | 0 | 0 |  |  |  | LMF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other type | quantity |  |  | 0 |  |  | LMF | 0 | 0 | 0 |  |  |  | LMF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structures |  | 0 | 0 | 0 |  |  | s_LMS | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Structure Type | list all angles and quantities |  |  | 0 |  | Include Structure Type/Family (Lattice Tower, Steel Pole, Wood Pole, H-frame, etc.) | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structure Type | list all angles and quantities |  |  | 0 |  | Include Angle (Tangent, Light Angle, Dead end, etc.) | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structure Type | list all angles and quantities |  |  | 0 |  | Explain structure, family, breakdown. | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structure Type | list all angles and quantities |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structure Type | list all angles and quantities |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structure Type | list all angles and quantities |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Hardware |  | 0 | 0 | 0 |  |  | s_LMH | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Hardware |  |  |  | 0 |  |  | LMH | 0 | 0 | 0 |  |  |  | LMH | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Transmission Wires |  | 0 | 0 | 0 |  |  | s_LMW | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Conductor | type, size, bundle |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Conductor | type, size, bundle |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Shield Wire | type, size |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
OPGW | type, size |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL MATERIALS |  | 0 | 0 | 0 |  |  | s_LM | 0 | 0 | 0 | 0 | 0 |  | L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
LABOUR
Detailed Engineering |  | 0 | 0 | 0 |  |  | s_LLE | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Line |  |  |  | 0 |  |  | LLE | 0 | 0 | 0 |  |  |  | LLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Civil |  |  |  | 0 |  |  | LLE | 0 | 0 | 0 |  |  |  | LLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Geotechnical |  |  |  | 0 |  |  | LLE | 0 | 0 | 0 |  |  |  | LLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Survey |  | 0 | 0 | 0 |  |  | s_LLS | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Survey - ROW and structures |  |  |  | 0 |  |  | LLS | 0 | 0 | 0 |  |  |  | LLS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Right of Way |  | 0 | 0 | 0 |  |  | s_LLR | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Site Preparation | ha |  |  | 0 |  | Include: clearing, brushing, earthworks, grading | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Environment Management |  |  |  | 0 |  | Include: wash station, erosion control. May be included here or under Distributed Labour - Construction Management (Tab 5). | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Road(s) | km |  |  | 0 |  | Include: permanent and temporary roads | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Matting Rental | type, quantity, duration |  |  | 0 |  |  | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Matting Lay/Removal | hours |  |  | 0 |  |  | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Construction |  | 0 | 0 | 0 |  |  | s_LLC | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Foundation |  |  |  | 0 |  | Include soil type assumption | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structure Installation |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Stringing - Shieldwires & Conductor |  |  |  | 0 |  | Include: line conductors and OHSW & OPGW | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
AC Mitigation |  |  |  | 0 |  | Mitigation of a Transmission AC circuit (current) corroding a parallel metallic object; i.e. pipeline, railway | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Major Equipment Rental | type, number, duration |  |  | 0 |  | Include: only major or special type of rental; i.e. helicopter, large cranes | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Field Supervision |  |  |  | 0 |  | Include: field supervisors, managers. May be included here or in Distributed Labour - Construction Managmeent (Tab 5) | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Indirects |  |  |  | 0 |  | Includes: trailers, fences, water, porta potties, etc. May be included here or in Distributed Labour - Construction Managmeent (Tab 5). | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Mobilization / Demobilization | number and size |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Yards | number and size |  |  | 0 |  | Include: assembly, lay-down, fly, storage yards | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Camp Services & Catering | size and duration |  |  | 0 |  | Include: camp services, security, etc. | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Commissioning |  | 0 | 0 | 0 |  |  | s_LLM | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Commissioning |  |  |  | 0 |  |  | LLM | 0 | 0 | 0 |  |  |  | LLM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL LABOUR |  | 0 | 0 | 0 |  |  | s_LL | 0 | 0 | 0 | 0 | 0 |  | L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
SUPPLY & INSTALL
Supply & Install | type / quality |  |  | 0 |  |  | LS | 0 | 0 | 0 |  |  |  | LS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | LS | 0 | 0 | 0 |  |  |  | LS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | LS | 0 | 0 | 0 |  |  |  | LS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL SUPPLY & INSTALL |  | 0 | 0 | 0 |  |  | s_LS | 0 | 0 | 0 | 0 | 0 |  | L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
SUBTOTAL LINE (3) |  | 0 | 0 | 0 |  |  | LT | 0 | 0 | 0 | 0 | 0 |  | LT | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Line <Line#, Location - from substation to substation> | [10 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation>
MATERIALS
Foundations |  | 0 | 0 | 0 |  | Include: Concrete | s_LMF | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Screwpiles | quantity |  |  | 0 |  |  | LMF | 0 | 0 | 0 |  |  |  | LMF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Driven Piles | quantity |  |  | 0 |  |  | LMF | 0 | 0 | 0 |  |  |  | LMF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Caisson Piles | quantity |  |  | 0 |  |  | LMF | 0 | 0 | 0 |  |  |  | LMF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other type | quantity |  |  | 0 |  |  | LMF | 0 | 0 | 0 |  |  |  | LMF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other type | quantity |  |  | 0 |  |  | LMF | 0 | 0 | 0 |  |  |  | LMF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structures |  | 0 | 0 | 0 |  |  | s_LMS | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Structure Type | list all angles and quantities |  |  | 0 |  | Include Structure Type/Family (Lattice Tower, Steel Pole, Wood Pole, H-frame, etc.) | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structure Type | list all angles and quantities |  |  | 0 |  | Include Angle (Tangent, Light Angle, Dead end, etc.) | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structure Type | list all angles and quantities |  |  | 0 |  | Explain structure, family, breakdown. | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structure Type | list all angles and quantities |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structure Type | list all angles and quantities |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structure Type | list all angles and quantities |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Hardware |  | 0 | 0 | 0 |  |  | s_LMH | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Hardware |  |  |  | 0 |  |  | LMH | 0 | 0 | 0 |  |  |  | LMH | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Transmission Wires |  | 0 | 0 | 0 |  |  | s_LMW | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Conductor | type, size, bundle |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Conductor | type, size, bundle |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Shield Wire | type, size |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
OPGW | type, size |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL MATERIALS |  | 0 | 0 | 0 |  |  | s_LM | 0 | 0 | 0 | 0 | 0 |  | L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
LABOUR
Detailed Engineering |  | 0 | 0 | 0 |  |  | s_LLE | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Line |  |  |  | 0 |  |  | LLE | 0 | 0 | 0 |  |  |  | LLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Civil |  |  |  | 0 |  |  | LLE | 0 | 0 | 0 |  |  |  | LLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Geotechnical |  |  |  | 0 |  |  | LLE | 0 | 0 | 0 |  |  |  | LLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Survey |  | 0 | 0 | 0 |  |  | s_LLS | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Survey - ROW and structures |  |  |  | 0 |  |  | LLS | 0 | 0 | 0 |  |  |  | LLS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Right of Way |  | 0 | 0 | 0 |  |  | s_LLR | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Site Preparation | ha |  |  | 0 |  | Include: clearing, brushing, earthworks, grading | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Environment Management |  |  |  | 0 |  | Include: wash station, erosion control. May be included here or under Distributed Labour - Construction Management (Tab 5). | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Road(s) | km |  |  | 0 |  | Include: permanent and temporary roads | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Matting Rental | type, quantity, duration |  |  | 0 |  |  | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Matting Lay/Removal | hours |  |  | 0 |  |  | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Construction |  | 0 | 0 | 0 |  |  | s_LLC | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Foundation |  |  |  | 0 |  | Include soil type assumption | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structure Installation |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Stringing - Shieldwires & Conductor |  |  |  | 0 |  | Include: line conductors and OHSW & OPGW | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
AC Mitigation |  |  |  | 0 |  | Mitigation of a Transmission AC circuit (current) corroding a parallel metallic object; i.e. pipeline, railway | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Major Equipment Rental | type, number, duration |  |  | 0 |  | Include: only major or special type of rental; i.e. helicopter, large cranes | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Field Supervision |  |  |  | 0 |  | Include: field supervisors, managers. May be included here or in Distributed Labour - Construction Managmeent (Tab 5) | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Indirects |  |  |  | 0 |  | Includes: trailers, fences, water, porta potties, etc. May be included here or in Distributed Labour - Construction Managmeent (Tab 5). | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Mobilization / Demobilization | number and size |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Yards | number and size |  |  | 0 |  | Include: assembly, lay-down, fly, storage yards | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Camp Services & Catering | size and duration |  |  | 0 |  | Include: camp services, security, etc. | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Commissioning |  | 0 | 0 | 0 |  |  | s_LLM | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Commissioning |  |  |  | 0 |  |  | LLM | 0 | 0 | 0 |  |  |  | LLM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL LABOUR |  | 0 | 0 | 0 |  |  | s_LL | 0 | 0 | 0 | 0 | 0 |  | L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
SUPPLY & INSTALL
Supply & Install | type / quality |  |  | 0 |  |  | LS | 0 | 0 | 0 |  |  |  | LS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | LS | 0 | 0 | 0 |  |  |  | LS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | LS | 0 | 0 | 0 |  |  |  | LS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL SUPPLY & INSTALL |  | 0 | 0 | 0 |  |  | s_LS | 0 | 0 | 0 | 0 | 0 |  | L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
SUBTOTAL LINE (4) |  | 0 | 0 | 0 |  |  | LT | 0 | 0 | 0 | 0 | 0 |  | LT | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Line <Line#, Location - from substation to substation> | [10 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation>
MATERIALS
Foundations |  | 0 | 0 | 0 |  | Include: Concrete | s_LMF | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Screwpiles | quantity |  |  | 0 |  |  | LMF | 0 | 0 | 0 |  |  |  | LMF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Driven Piles | quantity |  |  | 0 |  |  | LMF | 0 | 0 | 0 |  |  |  | LMF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Caisson Piles | quantity |  |  | 0 |  |  | LMF | 0 | 0 | 0 |  |  |  | LMF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other type | quantity |  |  | 0 |  |  | LMF | 0 | 0 | 0 |  |  |  | LMF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other type | quantity |  |  | 0 |  |  | LMF | 0 | 0 | 0 |  |  |  | LMF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structures |  | 0 | 0 | 0 |  |  | s_LMS | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Structure Type | list all angles and quantities |  |  | 0 |  | Include Structure Type/Family (Lattice Tower, Steel Pole, Wood Pole, H-frame, etc.) | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structure Type | list all angles and quantities |  |  | 0 |  | Include Angle (Tangent, Light Angle, Dead end, etc.) | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structure Type | list all angles and quantities |  |  | 0 |  | Explain structure, family, breakdown. | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structure Type | list all angles and quantities |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structure Type | list all angles and quantities |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structure Type | list all angles and quantities |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Hardware |  | 0 | 0 | 0 |  |  | s_LMH | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Hardware |  |  |  | 0 |  |  | LMH | 0 | 0 | 0 |  |  |  | LMH | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Transmission Wires |  | 0 | 0 | 0 |  |  | s_LMW | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Conductor | type, size, bundle |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Conductor | type, size, bundle |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Shield Wire | type, size |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
OPGW | type, size |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL MATERIALS |  | 0 | 0 | 0 |  |  | s_LM | 0 | 0 | 0 | 0 | 0 |  | L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
LABOUR
Detailed Engineering |  | 0 | 0 | 0 |  |  | s_LLE | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Line |  |  |  | 0 |  |  | LLE | 0 | 0 | 0 |  |  |  | LLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Civil |  |  |  | 0 |  |  | LLE | 0 | 0 | 0 |  |  |  | LLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Geotechnical |  |  |  | 0 |  |  | LLE | 0 | 0 | 0 |  |  |  | LLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Survey |  | 0 | 0 | 0 |  |  | s_LLS | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Survey - ROW and structures |  |  |  | 0 |  |  | LLS | 0 | 0 | 0 |  |  |  | LLS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Right of Way |  | 0 | 0 | 0 |  |  | s_LLR | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Site Preparation | ha |  |  | 0 |  | Include: clearing, brushing, earthworks, grading | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Environment Management |  |  |  | 0 |  | Include: wash station, erosion control. May be included here or under Distributed Labour - Construction Management (Tab 5). | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Road(s) | km |  |  | 0 |  | Include: permanent and temporary roads | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Matting Rental | type, quantity, duration |  |  | 0 |  |  | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Matting Lay/Removal | hours |  |  | 0 |  |  | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Construction |  | 0 | 0 | 0 |  |  | s_LLC | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Foundation |  |  |  | 0 |  | Include soil type assumption | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structure Installation |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Stringing - Shieldwires & Conductor |  |  |  | 0 |  | Include: line conductors and OHSW & OPGW | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
AC Mitigation |  |  |  | 0 |  | Mitigation of a Transmission AC circuit (current) corroding a parallel metallic object; i.e. pipeline, railway | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Major Equipment Rental | type, number, duration |  |  | 0 |  | Include: only major or special type of rental; i.e. helicopter, large cranes | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Field Supervision |  |  |  | 0 |  | Include: field supervisors, managers. May be included here or in Distributed Labour - Construction Managmeent (Tab 5) | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Indirects |  |  |  | 0 |  | Includes: trailers, fences, water, porta potties, etc. May be included here or in Distributed Labour - Construction Managmeent (Tab 5). | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Mobilization / Demobilization | number and size |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Yards | number and size |  |  | 0 |  | Include: assembly, lay-down, fly, storage yards | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Camp Services & Catering | size and duration |  |  | 0 |  | Include: camp services, security, etc. | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Commissioning |  | 0 | 0 | 0 |  |  | s_LLM | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Commissioning |  |  |  | 0 |  |  | LLM | 0 | 0 | 0 |  |  |  | LLM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL LABOUR |  | 0 | 0 | 0 |  |  | s_LL | 0 | 0 | 0 | 0 | 0 |  | L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
SUPPLY & INSTALL
Supply & Install | type / quality |  |  | 0 |  |  | LS | 0 | 0 | 0 |  |  |  | LS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | LS | 0 | 0 | 0 |  |  |  | LS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | LS | 0 | 0 | 0 |  |  |  | LS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL SUPPLY & INSTALL |  | 0 | 0 | 0 |  |  | s_LS | 0 | 0 | 0 | 0 | 0 |  | L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
SUBTOTAL LINE (5) |  | 0 | 0 | 0 |  |  | LT | 0 | 0 | 0 | 0 | 0 |  | LT | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Line <Line#, Location - from substation to substation> | [10 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation>
MATERIALS
Foundations |  | 0 | 0 | 0 |  | Include: Concrete | s_LMF | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Screwpiles | quantity |  |  | 0 |  |  | LMF | 0 | 0 | 0 |  |  |  | LMF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Driven Piles | quantity |  |  | 0 |  |  | LMF | 0 | 0 | 0 |  |  |  | LMF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Caisson Piles | quantity |  |  | 0 |  |  | LMF | 0 | 0 | 0 |  |  |  | LMF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other type | quantity |  |  | 0 |  |  | LMF | 0 | 0 | 0 |  |  |  | LMF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other type | quantity |  |  | 0 |  |  | LMF | 0 | 0 | 0 |  |  |  | LMF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structures |  | 0 | 0 | 0 |  |  | s_LMS | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Structure Type | list all angles and quantities |  |  | 0 |  | Include Structure Type/Family (Lattice Tower, Steel Pole, Wood Pole, H-frame, etc.) | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structure Type | list all angles and quantities |  |  | 0 |  | Include Angle (Tangent, Light Angle, Dead end, etc.) | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structure Type | list all angles and quantities |  |  | 0 |  | Explain structure, family, breakdown. | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structure Type | list all angles and quantities |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structure Type | list all angles and quantities |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structure Type | list all angles and quantities |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Hardware |  | 0 | 0 | 0 |  |  | s_LMH | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Hardware |  |  |  | 0 |  |  | LMH | 0 | 0 | 0 |  |  |  | LMH | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Transmission Wires |  | 0 | 0 | 0 |  |  | s_LMW | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Conductor | type, size, bundle |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Conductor | type, size, bundle |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Shield Wire | type, size |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
OPGW | type, size |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL MATERIALS |  | 0 | 0 | 0 |  |  | s_LM | 0 | 0 | 0 | 0 | 0 |  | L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
LABOUR
Detailed Engineering |  | 0 | 0 | 0 |  |  | s_LLE | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Line |  |  |  | 0 |  |  | LLE | 0 | 0 | 0 |  |  |  | LLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Civil |  |  |  | 0 |  |  | LLE | 0 | 0 | 0 |  |  |  | LLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Geotechnical |  |  |  | 0 |  |  | LLE | 0 | 0 | 0 |  |  |  | LLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Survey |  | 0 | 0 | 0 |  |  | s_LLS | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Survey - ROW and structures |  |  |  | 0 |  |  | LLS | 0 | 0 | 0 |  |  |  | LLS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Right of Way |  | 0 | 0 | 0 |  |  | s_LLR | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Site Preparation | ha |  |  | 0 |  | Include: clearing, brushing, earthworks, grading | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Environment Management |  |  |  | 0 |  | Include: wash station, erosion control. May be included here or under Distributed Labour - Construction Management (Tab 5). | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Road(s) | km |  |  | 0 |  | Include: permanent and temporary roads | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Matting Rental | type, quantity, duration |  |  | 0 |  |  | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Matting Lay/Removal | hours |  |  | 0 |  |  | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Construction |  | 0 | 0 | 0 |  |  | s_LLC | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Foundation |  |  |  | 0 |  | Include soil type assumption | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structure Installation |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Stringing - Shieldwires & Conductor |  |  |  | 0 |  | Include: line conductors and OHSW & OPGW | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
AC Mitigation |  |  |  | 0 |  | Mitigation of a Transmission AC circuit (current) corroding a parallel metallic object; i.e. pipeline, railway | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Major Equipment Rental | type, number, duration |  |  | 0 |  | Include: only major or special type of rental; i.e. helicopter, large cranes | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Field Supervision |  |  |  | 0 |  | Include: field supervisors, managers. May be included here or in Distributed Labour - Construction Managmeent (Tab 5) | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Indirects |  |  |  | 0 |  | Includes: trailers, fences, water, porta potties, etc. May be included here or in Distributed Labour - Construction Managmeent (Tab 5). | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Mobilization / Demobilization | number and size |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Yards | number and size |  |  | 0 |  | Include: assembly, lay-down, fly, storage yards | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Camp Services & Catering | size and duration |  |  | 0 |  | Include: camp services, security, etc. | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Commissioning |  | 0 | 0 | 0 |  |  | s_LLM | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Commissioning |  |  |  | 0 |  |  | LLM | 0 | 0 | 0 |  |  |  | LLM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL LABOUR |  | 0 | 0 | 0 |  |  | s_LL | 0 | 0 | 0 | 0 | 0 |  | L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
SUPPLY & INSTALL
Supply & Install | type / quality |  |  | 0 |  |  | LS | 0 | 0 | 0 |  |  |  | LS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | LS | 0 | 0 | 0 |  |  |  | LS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | LS | 0 | 0 | 0 |  |  |  | LS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL SUPPLY & INSTALL |  | 0 | 0 | 0 |  |  | s_LS | 0 | 0 | 0 | 0 | 0 |  | L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
SUBTOTAL LINE (6) |  | 0 | 0 | 0 |  |  | LT | 0 | 0 | 0 | 0 | 0 |  | LT | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
TOTAL OH LINE MATERIAL |  | 0 | 0 | 0 |  |  | s_s_LM | 0 | 0 | 0 | 0 | 0 |  | s_L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
TOTAL OH LINE LABOUR |  | 0 | 0 | 0 |  |  | s_S_LL | 0 | 0 | 0 | 0 | 0 |  | S_L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
TOTAL OH LINE SUPPLY & INSTALL |  | 0 | 0 | 0 |  |  | s_s_LS | 0 | 0 | 0 | 0 | 0 |  | s_L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
TOTAL TRANSMISSION OH LINE |  | 0 | 0 | 0 |  |  | s_LT | 0 | 0 | 0 | 0 | 0 |  | L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0

## Line(UG) 2b
TRANSMISSION LINE UNDERGROUND SUMMARY | [6 empty] | 1 | PCP | PCP #1 | 0 | PCP # 1 |  |  | 2 | PCP | PCP #2 | 0 | PCP # 2 |  |  | 3 | PCP | PCP #3 | 0 | PCP # 3 |  |  | 4 | PCP | PCP #4 | 0 | PCP # 4 |  |  | 5 | PCP | PCP #5 | 0 | PCP # 5 |  |  | 6 | PCP | PCP #6 | 0 | PCP # 6 |  |  | 7 | PCP | PCP #7 | 0 | PCP # 7 |  |  | 8 | PCP | PCP #8 | 0 | PCP # 8 |  |  | 9 | PCP | PCP #9 | 0 | PCP # 9 |  |  | 10 | PCP | PCP #10 | 0 | PCP # 10 |  |  | 11 | PCP | PCP #11 | 0 | PCP # 11 |  |  | 12 | PCP | PCP #12 | 0 | PCP # 12 |  |  | 13 | Final Cost Report | Final Cost Report #13 | 0 | Final Cost Report # 13 |  |  | 14 | PCP | PCP #14 | 0 | PCP # 14 |  |  | 15 | PCP | PCP #15 | 0 | PCP # 15 |  |  | 16 | PCP | PCP #16 | 0 | PCP # 16 |  |  | 17 | PCP | PCP #17 | 0 | PCP # 17
|  | SYSTEM | PARTICIPANT | TOTAL | ASSUMPTIONS |  |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments
Line <Line#, Location - from substation to substation> | [9 empty] | 5 | Line <Line#, Location - from substation to substation> | [5 empty] | 11 | Line <Line#, Location - from substation to substation> | [5 empty] | 18 | Line <Line#, Location - from substation to substation> | [5 empty] | 25 | Line <Line#, Location - from substation to substation> | [5 empty] | 32 | Line <Line#, Location - from substation to substation> | [5 empty] | 39 | Line <Line#, Location - from substation to substation> | [5 empty] | 46 | Line <Line#, Location - from substation to substation> | [5 empty] | 53 | Line <Line#, Location - from substation to substation> | [5 empty] | 60 | Line <Line#, Location - from substation to substation> | [5 empty] | 67 | Line <Line#, Location - from substation to substation> | [5 empty] | 74 | Line <Line#, Location - from substation to substation> | [5 empty] | 81 | Line <Line#, Location - from substation to substation> | [5 empty] | 88 | Line <Line#, Location - from substation to substation> | [5 empty] | 95 | Line <Line#, Location - from substation to substation> | [5 empty] | 102 | Line <Line#, Location - from substation to substation> | [5 empty] | 109 | Line <Line#, Location - from substation to substation> | [5 empty] | 116 | Line <Line#, Location - from substation to substation>
MATERIALS
Civil Work |  | 0 | 0 | 0 |  |  | s_LMC | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Duct Bank | size, quantity |  |  | 0 |  |  | LMC | 0 | 0 | 0 |  |  |  | LMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Manhole | size, quantity |  |  | 0 |  |  | LMC | 0 | 0 | 0 |  |  |  | LMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cable Vault | size, quantity |  |  | 0 |  |  | LMC | 0 | 0 | 0 |  |  |  | LMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other (please specify) | size, quantity |  |  | 0 |  |  | LMC | 0 | 0 | 0 |  |  |  | LMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other (please specify) | size, quantity |  |  | 0 |  |  | LMC | 0 | 0 | 0 |  |  |  | LMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structures |  | 0 | 0 | 0 |  |  | s_LMS | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Riser Structure | quantity |  |  | 0 |  | Include structure type | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Pothead Structure | quantity |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cable Bridge | quantity |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other (please specify) | quantity |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other (please specify) | quantity |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Hardware |  | 0 | 0 | 0 |  |  | s_LMH | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Hardware |  |  |  | 0 |  |  | LMH | 0 | 0 | 0 |  |  |  | LMH | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Conductor |  | 0 | 0 | 0 |  |  | s_LMW | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Cable | type, size, bundle |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cable Splice | size, quantity |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Terminator | size, quantity |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL MATERIALS |  | 0 | 0 | 0 |  |  | s_LM | 0 | 0 | 0 | 0 | 0 |  | L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
LABOUR
Detailed Engineering |  | 0 | 0 | 0 |  |  | s_LLE | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Line |  |  |  | 0 |  |  | LLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Civil |  |  |  | 0 |  |  | LLE | 0 | 0 | 0 |  |  |  | LLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Geotechnical |  |  |  | 0 |  |  | LLE | 0 | 0 | 0 |  |  |  | LLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Survey |  | 0 | 0 | 0 |  |  | s_LLV | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Survey - ROW and structures |  |  |  | 0 |  |  | LLV | 0 | 0 | 0 |  |  |  | LLV | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Soil Thermal Resistivity Test |  |  |  | 0 |  |  | LLV | 0 | 0 | 0 |  |  |  | LLV | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Right of Way |  | 0 | 0 | 0 |  |  | s_LLR | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Site Preparation | ha |  |  | 0 |  | Include: clearing, brushing, earthworks, grading | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Environment Management |  |  |  | 0 |  | Include: wash station, erosion control. May be included here or under Distributed Labour - Construction Management (Tab 5). | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Road(s) | km |  |  | 0 |  | Include: permanent and temporary roads | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Matting Rental | type, quantity, duration |  |  | 0 |  |  | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Matting Lay/Removal | hours |  |  | 0 |  |  | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Regulatory Approvals/Permits |  |  |  | 0 |  |  | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Moving Existing Facilities |  |  |  | 0 |  |  | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Construction |  | 0 | 0 | 0 |  |  | s_LLC | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Trenching & Closing |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Directional Drilling |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Duct Bank |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Manhole/Vault | quantity |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Engineered Backfill | quantity |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Soil Removal and Landscaping | size, quantity |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cable Bridge |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cable Installation |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cable Splicing |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Termination |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Mobilization / Demobilization | number and size |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
AC Mitigation |  |  |  | 0 |  | Mitigation of a Transmission AC circuit (current) corroding a parallel metallic object; i.e. pipeline, railway | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Major Equipment Rental | size and duration |  |  | 0 |  | Include: only major or special type of rental; i.e. helicopter, large cranes | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Yards | number and size |  |  | 0 |  | Include: assembly, lay-down, fly, storage yards, security | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Shelter Facility |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Camp Services & Catering | size and duration |  |  | 0 |  | Include: camp services, security, etc. | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Field Supervision |  |  |  | 0 |  | Include: field supervisors, managers. May be included here or in Distributed Labour - Construction Managmeent (Tab 5) | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Indirects |  |  |  | 0 |  | Includes: trailers, fences, water, porta potties, etc. May be included here or under Distributed Labour - Construction Management (Tab 5). | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Commissioning |  | 0 | 0 | 0 |  |  | s_LLM | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Commissioning |  |  |  | 0 |  |  | LLM | 0 | 0 | 0 |  |  |  | LLM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL LABOUR |  | 0 | 0 | 0 |  |  | s_LL | 0 | 0 | 0 | 0 | 0 |  | L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
SUPPLY & INSTALL
Supply & Install | type / quality |  |  | 0 |  |  | LS | 0 | 0 | 0 |  |  |  | LS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | LS | 0 | 0 | 0 |  |  |  | LS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | LS | 0 | 0 | 0 |  |  |  | LS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL SUPPLY & INSTALL |  | 0 | 0 | 0 |  |  | s_LS | 0 | 0 | 0 | 0 | 0 |  | L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
SUBTOTAL LINE (1) |  | 0 | 0 | 0 |  |  | LT | 0 | 0 | 0 | 0 | 0 |  | LT | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Line <Line#, Location - from substation to substation> | [10 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation>
MATERIALS
Civil Work |  | 0 | 0 | 0 |  |  | s_LMC | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Duct Bank | size, quantity |  |  | 0 |  |  | LMC | 0 | 0 | 0 |  |  |  | LMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Manhole | size, quantity |  |  | 0 |  |  | LMC | 0 | 0 | 0 |  |  |  | LMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cable Vault | size, quantity |  |  | 0 |  |  | LMC | 0 | 0 | 0 |  |  |  | LMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other (please specify) | size, quantity |  |  | 0 |  |  | LMC | 0 | 0 | 0 |  |  |  | LMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other (please specify) | size, quantity |  |  | 0 |  |  | LMC | 0 | 0 | 0 |  |  |  | LMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structures |  | 0 | 0 | 0 |  |  | s_LMS | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Riser Structure | quantity |  |  | 0 |  | Include structure type | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Pothead Structure | quantity |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cable Bridge | quantity |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other (please specify) | quantity |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other (please specify) | quantity |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Hardware |  | 0 | 0 | 0 |  |  | s_LMH | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Hardware |  |  |  | 0 |  |  | LMH | 0 | 0 | 0 |  |  |  | LMH | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Conductor |  | 0 | 0 | 0 |  |  | s_LMW | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Cable | type, size, bundle |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cable Splice | size, quantity |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Terminator | size, quantity |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL MATERIALS |  | 0 | 0 | 0 |  |  | s_LM | 0 | 0 | 0 | 0 | 0 |  | L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
LABOUR
Detailed Engineering |  | 0 | 0 | 0 |  |  | s_LLE | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Line |  |  |  | 0 |  |  | LLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Civil |  |  |  | 0 |  |  | LLE | 0 | 0 | 0 |  |  |  | LLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Geotechnical |  |  |  | 0 |  |  | LLE | 0 | 0 | 0 |  |  |  | LLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Survey |  | 0 | 0 | 0 |  |  | s_LLV | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Survey - ROW and structures |  |  |  | 0 |  |  | LLV | 0 | 0 | 0 |  |  |  | LLV | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Soil Thermal Resistivity Test |  |  |  | 0 |  |  | LLV | 0 | 0 | 0 |  |  |  | LLV | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Right of Way |  | 0 | 0 | 0 |  |  | s_LLR | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Site Preparation | ha |  |  | 0 |  | Include: clearing, brushing, earthworks, grading | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Environment Management |  |  |  | 0 |  | Include: wash station, erosion control. May be included here or under Distributed Labour - Construction Management (Tab 5). | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Road(s) | km |  |  | 0 |  | Include: permanent and temporary roads | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Matting Rental | type, quantity, duration |  |  | 0 |  |  | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Matting Lay/Removal | hours |  |  | 0 |  |  | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Regulatory Approvals/Permits |  |  |  | 0 |  |  | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Moving Existing Facilities |  |  |  | 0 |  |  | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Construction |  | 0 | 0 | 0 |  |  | s_LLC | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Trenching & Closing |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Directional Drilling |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Duct Bank |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Manhole/Vault Installation | quantity |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Engineered backfill | quantity |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Soil Removal and Landscaping | size, quantity |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cable Bridge |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cable Installation |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cable Splicing |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Termination |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Mobilization / demobilization | number and size |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
AC Mitigation |  |  |  | 0 |  | Mitigation of a Transmission AC circuit (current) corroding a parallel metallic object; i.e. pipeline, railway | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Major Equipment Rental | size and duration |  |  | 0 |  | Include: only major or special type of rental; i.e. helicopter, large cranes | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Yards | number and size |  |  | 0 |  | Include: assembly, lay-down, fly, storage yards, security | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Shelter Facility |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Camp Services & Catering | size and duration |  |  | 0 |  | Include: camp services, security, etc. | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Field Supervision |  |  |  | 0 |  | Include: field supervisors, managers. May be included here or in Distributed Labour - Construction Managmeent (Tab 5) | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Indirects |  |  |  | 0 |  | Includes: trailers, fences, water, porta potties, etc. May be included here or under Distributed Labour - Construction Management (Tab 5). | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Commissioning |  | 0 | 0 | 0 |  |  | s_LLM | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Commissioning |  |  |  | 0 |  |  | LLM | 0 | 0 | 0 |  |  |  | LLM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL LABOUR |  | 0 | 0 | 0 |  |  | s_LL | 0 | 0 | 0 | 0 | 0 |  | L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
SUPPLY & INSTALL
Supply & Install | type / quality |  |  | 0 |  |  | LS | 0 | 0 | 0 |  |  |  | LS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | LS | 0 | 0 | 0 |  |  |  | LS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | LS | 0 | 0 | 0 |  |  |  | LS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL SUPPLY & INSTALL |  | 0 | 0 | 0 |  |  | s_LS | 0 | 0 | 0 | 0 | 0 |  | L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
SUBTOTAL LINE (2) |  | 0 | 0 | 0 |  |  | LT | 0 | 0 | 0 | 0 | 0 |  | LT | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Line <Line#, Location - from substation to substation> | [10 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation>
MATERIALS
Civil Work |  | 0 | 0 | 0 |  |  | s_LMC | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Duct Bank | size, quantity |  |  | 0 |  |  | LMC | 0 | 0 | 0 |  |  |  | LMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Manhole | size, quantity |  |  | 0 |  |  | LMC | 0 | 0 | 0 |  |  |  | LMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cable Vault | size, quantity |  |  | 0 |  |  | LMC | 0 | 0 | 0 |  |  |  | LMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other (please specify) | size, quantity |  |  | 0 |  |  | LMC | 0 | 0 | 0 |  |  |  | LMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other (please specify) | size, quantity |  |  | 0 |  |  | LMC | 0 | 0 | 0 |  |  |  | LMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structures |  | 0 | 0 | 0 |  |  | s_LMS | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Riser Structure | quantity |  |  | 0 |  | Include structure type | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Pothead Structure | quantity |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cable Bridge | quantity |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other (please specify) | quantity |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other (please specify) | quantity |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Hardware |  | 0 | 0 | 0 |  |  | s_LMH | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Hardware |  |  |  | 0 |  |  | LMH | 0 | 0 | 0 |  |  |  | LMH | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Conductor |  | 0 | 0 | 0 |  |  | s_LMW | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Cable | type, size, bundle |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cable Splice | size, quantity |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Terminator | size, quantity |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL MATERIALS |  | 0 | 0 | 0 |  |  | s_LM | 0 | 0 | 0 | 0 | 0 |  | L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
LABOUR
Detailed Engineering |  | 0 | 0 | 0 |  |  | s_LLE | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Line |  |  |  | 0 |  |  | LLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Civil |  |  |  | 0 |  |  | LLE | 0 | 0 | 0 |  |  |  | LLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Geotechnical |  |  |  | 0 |  |  | LLE | 0 | 0 | 0 |  |  |  | LLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Survey |  | 0 | 0 | 0 |  |  | s_LLV | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Survey - ROW and structures |  |  |  | 0 |  |  | LLV | 0 | 0 | 0 |  |  |  | LLV | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Soil Thermal Resistivity Test |  |  |  | 0 |  |  | LLV | 0 | 0 | 0 |  |  |  | LLV | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Right of Way |  | 0 | 0 | 0 |  |  | s_LLR | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Site Preparation | ha |  |  | 0 |  | Include: clearing, brushing, earthworks, grading | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Environment Management |  |  |  | 0 |  | Include: wash station, erosion control. May be included here or under Distributed Labour - Construction Management (Tab 5). | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Road(s) | km |  |  | 0 |  | Include: permanent and temporary roads | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Matting Rental | type, quantity, duration |  |  | 0 |  |  | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Matting Lay/Removal | hours |  |  | 0 |  |  | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Regulatory Approvals/Permits |  |  |  | 0 |  |  | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Moving Existing Facilities |  |  |  | 0 |  |  | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Construction |  | 0 | 0 | 0 |  |  | s_LLC | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Trenching & Closing |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Directional Drilling |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Duct Bank |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Manhole/Vault Installation | quantity |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Engineered backfill | quantity |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Soil Removal and Landscaping | size, quantity |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cable Bridge |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cable Installation |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cable Splicing |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Termination |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Mobilization / demobilization | number and size |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
AC Mitigation |  |  |  | 0 |  | Mitigation of a Transmission AC circuit (current) corroding a parallel metallic object; i.e. pipeline, railway | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Major Equipment Rental | size and duration |  |  | 0 |  | Include: only major or special type of rental; i.e. helicopter, large cranes | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Yards | number and size |  |  | 0 |  | Include: assembly, lay-down, fly, storage yards, security | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Shelter Facility |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Camp Services & Catering | size and duration |  |  | 0 |  | Include: camp services, security, etc. | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Field Supervision |  |  |  | 0 |  | Include: field supervisors, managers. May be included here or in Distributed Labour - Construction Managmeent (Tab 5) | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Indirects |  |  |  | 0 |  | Includes: trailers, fences, water, porta potties, etc. May be included here or under Distributed Labour - Construction Management (Tab 5). | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Commissioning |  | 0 | 0 | 0 |  |  | s_LLM | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Commissioning |  |  |  | 0 |  |  | LLM | 0 | 0 | 0 |  |  |  | LLM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL LABOUR |  | 0 | 0 | 0 |  |  | s_LL | 0 | 0 | 0 | 0 | 0 |  | L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
SUPPLY & INSTALL
Supply & Install | type / quality |  |  | 0 |  |  | LS | 0 | 0 | 0 |  |  |  | LS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | LS | 0 | 0 | 0 |  |  |  | LS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | LS | 0 | 0 | 0 |  |  |  | LS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL SUPPLY & INSTALL |  | 0 | 0 | 0 |  |  | s_LS | 0 | 0 | 0 | 0 | 0 |  | L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
SUBTOTAL LINE (3) |  | 0 | 0 | 0 |  |  | LT | 0 | 0 | 0 | 0 | 0 |  | LT | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Line <Line#, Location - from substation to substation> | [10 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation>
MATERIALS
Civil Work |  | 0 | 0 | 0 |  |  | s_LMC | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Duct Bank | size, quantity |  |  | 0 |  |  | LMC | 0 | 0 | 0 |  |  |  | LMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Manhole | size, quantity |  |  | 0 |  |  | LMC | 0 | 0 | 0 |  |  |  | LMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cable Vault | size, quantity |  |  | 0 |  |  | LMC | 0 | 0 | 0 |  |  |  | LMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other (please specify) | size, quantity |  |  | 0 |  |  | LMC | 0 | 0 | 0 |  |  |  | LMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other (please specify) | size, quantity |  |  | 0 |  |  | LMC | 0 | 0 | 0 |  |  |  | LMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structures |  | 0 | 0 | 0 |  |  | s_LMS | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Riser Structure | quantity |  |  | 0 |  | Include structure type | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Pothead Structure | quantity |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cable Bridge | quantity |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other (please specify) | quantity |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other (please specify) | quantity |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Hardware |  | 0 | 0 | 0 |  |  | s_LMH | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Hardware |  |  |  | 0 |  |  | LMH | 0 | 0 | 0 |  |  |  | LMH | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Conductor |  | 0 | 0 | 0 |  |  | s_LMW | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Cable | type, size, bundle |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cable Splice | size, quantity |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Terminator | size, quantity |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL MATERIALS |  | 0 | 0 | 0 |  |  | s_LM | 0 | 0 | 0 | 0 | 0 |  | L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
LABOUR
Detailed Engineering |  | 0 | 0 | 0 |  |  | s_LLE | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Line |  |  |  | 0 |  |  | LLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Civil |  |  |  | 0 |  |  | LLE | 0 | 0 | 0 |  |  |  | LLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Geotechnical |  |  |  | 0 |  |  | LLE | 0 | 0 | 0 |  |  |  | LLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Survey |  | 0 | 0 | 0 |  |  | s_LLV | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Survey - ROW and structures |  |  |  | 0 |  |  | LLV | 0 | 0 | 0 |  |  |  | LLV | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Soil Thermal Resistivity Test |  |  |  | 0 |  |  | LLV | 0 | 0 | 0 |  |  |  | LLV | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Right of Way |  | 0 | 0 | 0 |  |  | s_LLR | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Site Preparation | ha |  |  | 0 |  | Include: clearing, brushing, earthworks, grading | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Environment Management |  |  |  | 0 |  | Include: wash station, erosion control. May be included here or under Distributed Labour - Construction Management (Tab 5). | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Road(s) | km |  |  | 0 |  | Include: permanent and temporary roads | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Matting Rental | type, quantity, duration |  |  | 0 |  |  | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Matting Lay/Removal | hours |  |  | 0 |  |  | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Regulatory Approvals/Permits |  |  |  | 0 |  |  | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Moving Existing Facilities |  |  |  | 0 |  |  | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Construction |  | 0 | 0 | 0 |  |  | s_LLC | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Trenching & Closing |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Directional Drilling |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Duct Bank |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Manhole/Vault Installation | quantity |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Engineered backfill | quantity |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Soil Removal and Landscaping | size, quantity |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cable Bridge |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cable Installation |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cable Splicing |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Termination |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Mobilization / demobilization | number and size |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
AC Mitigation |  |  |  | 0 |  | Mitigation of a Transmission AC circuit (current) corroding a parallel metallic object; i.e. pipeline, railway | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Major Equipment Rental | size and duration |  |  | 0 |  | Include: only major or special type of rental; i.e. helicopter, large cranes | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Yards | number and size |  |  | 0 |  | Include: assembly, lay-down, fly, storage yards, security | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Shelter Facility |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Camp Services & Catering | size and duration |  |  | 0 |  | Include: camp services, security, etc. | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Field Supervision |  |  |  | 0 |  | Include: field supervisors, managers. May be included here or in Distributed Labour - Construction Managmeent (Tab 5) | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Indirects |  |  |  | 0 |  | Includes: trailers, fences, water, porta potties, etc. May be included here or under Distributed Labour - Construction Management (Tab 5). | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Commissioning |  | 0 | 0 | 0 |  |  | s_LLM | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Commissioning |  |  |  | 0 |  |  | LLM | 0 | 0 | 0 |  |  |  | LLM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL LABOUR |  | 0 | 0 | 0 |  |  | s_LL | 0 | 0 | 0 | 0 | 0 |  | L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
SUPPLY & INSTALL
Supply & Install | type / quality |  |  | 0 |  |  | LS | 0 | 0 | 0 |  |  |  | LS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | LS | 0 | 0 | 0 |  |  |  | LS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | LS | 0 | 0 | 0 |  |  |  | LS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL SUPPLY & INSTALL |  | 0 | 0 | 0 |  |  | s_LS | 0 | 0 | 0 | 0 | 0 |  | L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
SUBTOTAL LINE (4) |  | 0 | 0 | 0 |  |  | LT | 0 | 0 | 0 | 0 | 0 |  | LT | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Line <Line#, Location - from substation to substation> | [10 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation>
MATERIALS
Civil Work |  | 0 | 0 | 0 |  |  | s_LMC | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Duct Bank | size, quantity |  |  | 0 |  |  | LMC | 0 | 0 | 0 |  |  |  | LMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Manhole | size, quantity |  |  | 0 |  |  | LMC | 0 | 0 | 0 |  |  |  | LMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cable Vault | size, quantity |  |  | 0 |  |  | LMC | 0 | 0 | 0 |  |  |  | LMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other (please specify) | size, quantity |  |  | 0 |  |  | LMC | 0 | 0 | 0 |  |  |  | LMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other (please specify) | size, quantity |  |  | 0 |  |  | LMC | 0 | 0 | 0 |  |  |  | LMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structures |  | 0 | 0 | 0 |  |  | s_LMS | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Riser Structure | quantity |  |  | 0 |  | Include structure type | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Pothead Structure | quantity |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cable Bridge | quantity |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other (please specify) | quantity |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other (please specify) | quantity |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Hardware |  | 0 | 0 | 0 |  |  | s_LMH | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Hardware |  |  |  | 0 |  |  | LMH | 0 | 0 | 0 |  |  |  | LMH | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Conductor |  | 0 | 0 | 0 |  |  | s_LMW | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Cable | type, size, bundle |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cable Splice | size, quantity |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Terminator | size, quantity |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL MATERIALS |  | 0 | 0 | 0 |  |  | s_LM | 0 | 0 | 0 | 0 | 0 |  | L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
LABOUR
Detailed Engineering |  | 0 | 0 | 0 |  |  | s_LLE | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Line |  |  |  | 0 |  |  | LLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Civil |  |  |  | 0 |  |  | LLE | 0 | 0 | 0 |  |  |  | LLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Geotechnical |  |  |  | 0 |  |  | LLE | 0 | 0 | 0 |  |  |  | LLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Survey |  | 0 | 0 | 0 |  |  | s_LLV | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Survey - ROW and structures |  |  |  | 0 |  |  | LLV | 0 | 0 | 0 |  |  |  | LLV | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Soil Thermal Resistivity Test |  |  |  | 0 |  |  | LLV | 0 | 0 | 0 |  |  |  | LLV | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Right of Way |  | 0 | 0 | 0 |  |  | s_LLR | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Site Preparation | ha |  |  | 0 |  | Include: clearing, brushing, earthworks, grading | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Environment Management |  |  |  | 0 |  | Include: wash station, erosion control. May be included here or under Distributed Labour - Construction Management (Tab 5). | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Road(s) | km |  |  | 0 |  | Include: permanent and temporary roads | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Matting Rental | type, quantity, duration |  |  | 0 |  |  | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Matting Lay/Removal | hours |  |  | 0 |  |  | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Regulatory Approvals/Permits |  |  |  | 0 |  |  | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Moving Existing Facilities |  |  |  | 0 |  |  | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Construction |  | 0 | 0 | 0 |  |  | s_LLC | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Trenching & Closing |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Directional Drilling |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Duct Bank |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Manhole/Vault Installation | quantity |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Engineered backfill | quantity |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Soil Removal and Landscaping | size, quantity |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cable Bridge |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cable Installation |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cable Splicing |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Termination |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Mobilization / demobilization | number and size |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
AC Mitigation |  |  |  | 0 |  | Mitigation of a Transmission AC circuit (current) corroding a parallel metallic object; i.e. pipeline, railway | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Major Equipment Rental | size and duration |  |  | 0 |  | Include: only major or special type of rental; i.e. helicopter, large cranes | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Yards | number and size |  |  | 0 |  | Include: assembly, lay-down, fly, storage yards, security | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Shelter Facility |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Camp Services & Catering | size and duration |  |  | 0 |  | Include: camp services, security, etc. | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Field Supervision |  |  |  | 0 |  | Include: field supervisors, managers. May be included here or in Distributed Labour - Construction Managmeent (Tab 5) | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Indirects |  |  |  | 0 |  | Includes: trailers, fences, water, porta potties, etc. May be included here or under Distributed Labour - Construction Management (Tab 5). | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Commissioning |  | 0 | 0 | 0 |  |  | s_LLM | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Commissioning |  |  |  | 0 |  |  | LLM | 0 | 0 | 0 |  |  |  | LLM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL LABOUR |  | 0 | 0 | 0 |  |  | s_LL | 0 | 0 | 0 | 0 | 0 |  | L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
SUPPLY & INSTALL
Supply & Install | type / quality |  |  | 0 |  |  | LS | 0 | 0 | 0 |  |  |  | LS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | LS | 0 | 0 | 0 |  |  |  | LS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | LS | 0 | 0 | 0 |  |  |  | LS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL SUPPLY & INSTALL |  | 0 | 0 | 0 |  |  | s_LS | 0 | 0 | 0 | 0 | 0 |  | L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
SUBTOTAL LINE (5) |  | 0 | 0 | 0 |  |  | LT | 0 | 0 | 0 | 0 | 0 |  | LT | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Line <Line#, Location - from substation to substation> | [10 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation> | [6 empty] | Line <Line#, Location - from substation to substation>
MATERIALS
Civil Work |  | 0 | 0 | 0 |  |  | s_LMC | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Duct Bank | size, quantity |  |  | 0 |  |  | LMC | 0 | 0 | 0 |  |  |  | LMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Manhole | size, quantity |  |  | 0 |  |  | LMC | 0 | 0 | 0 |  |  |  | LMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cable Vault | size, quantity |  |  | 0 |  |  | LMC | 0 | 0 | 0 |  |  |  | LMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other (please specify) | size, quantity |  |  | 0 |  |  | LMC | 0 | 0 | 0 |  |  |  | LMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other (please specify) | size, quantity |  |  | 0 |  |  | LMC | 0 | 0 | 0 |  |  |  | LMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Structures |  | 0 | 0 | 0 |  |  | s_LMS | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Riser Structure | quantity |  |  | 0 |  | Include structure type | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Pothead Structure | quantity |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cable Bridge | quantity |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other (please specify) | quantity |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other (please specify) | quantity |  |  | 0 |  |  | LMS | 0 | 0 | 0 |  |  |  | LMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Hardware |  | 0 | 0 | 0 |  |  | s_LMH | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Hardware |  |  |  | 0 |  |  | LMH | 0 | 0 | 0 |  |  |  | LMH | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Conductor |  | 0 | 0 | 0 |  |  | s_LMW | 0 | 0 | 0 | 0 | 0 |  | LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Cable | type, size, bundle |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cable Splice | size, quantity |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Terminator | size, quantity |  |  | 0 |  |  | LMW | 0 | 0 | 0 |  |  |  | LMW | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL MATERIALS |  | 0 | 0 | 0 |  |  | s_LM | 0 | 0 | 0 | 0 | 0 |  | L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
LABOUR
Detailed Engineering |  | 0 | 0 | 0 |  |  | s_LLE | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Line |  |  |  | 0 |  |  | LLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Civil |  |  |  | 0 |  |  | LLE | 0 | 0 | 0 |  |  |  | LLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Geotechnical |  |  |  | 0 |  |  | LLE | 0 | 0 | 0 |  |  |  | LLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Survey |  | 0 | 0 | 0 |  |  | s_LLV | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Survey - ROW and structures |  |  |  | 0 |  |  | LLV | 0 | 0 | 0 |  |  |  | LLV | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Soil Thermal Resistivity Test |  |  |  | 0 |  |  | LLV | 0 | 0 | 0 |  |  |  | LLV | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Right of Way |  | 0 | 0 | 0 |  |  | s_LLR | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Site Preparation | ha |  |  | 0 |  | Include: clearing, brushing, earthworks, grading | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Environment Management |  |  |  | 0 |  | Include: wash station, erosion control. May be included here or under Distributed Labour - Construction Management (Tab 5). | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Road(s) | km |  |  | 0 |  | Include: permanent and temporary roads | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Matting Rental | type, quantity, duration |  |  | 0 |  |  | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Matting Lay/Removal | hours |  |  | 0 |  |  | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Regulatory Approvals/Permits |  |  |  | 0 |  |  | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Moving Existing Facilities |  |  |  | 0 |  |  | LLR | 0 | 0 | 0 |  |  |  | LLR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Construction |  | 0 | 0 | 0 |  |  | s_LLC | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Trenching & Closing |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Directional Drilling |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Duct Bank |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Manhole/Vault Installation | quantity |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Engineered backfill | quantity |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Soil Removal and Landscaping | size, quantity |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cable Bridge |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cable Installation |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cable Splicing |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Termination |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Mobilization / demobilization | number and size |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
AC Mitigation |  |  |  | 0 |  | Mitigation of a Transmission AC circuit (current) corroding a parallel metallic object; i.e. pipeline, railway | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Major Equipment Rental | size and duration |  |  | 0 |  | Include: only major or special type of rental; i.e. helicopter, large cranes | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Yards | number and size |  |  | 0 |  | Include: assembly, lay-down, fly, storage yards, security | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Shelter Facility |  |  |  | 0 |  |  | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Camp Services & Catering | size and duration |  |  | 0 |  | Include: camp services, security, etc. | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Field Supervision |  |  |  | 0 |  | Include: field supervisors, managers. May be included here or in Distributed Labour - Construction Managmeent (Tab 5) | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Indirects |  |  |  | 0 |  | Includes: trailers, fences, water, porta potties, etc. May be included here or under Distributed Labour - Construction Management (Tab 5). | LLC | 0 | 0 | 0 |  |  |  | LLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Commissioning |  | 0 | 0 | 0 |  |  | s_LLM | 0 | 0 | 0 | 0 | 0 |  | LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Commissioning |  |  |  | 0 |  |  | LLM | 0 | 0 | 0 |  |  |  | LLM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL LABOUR |  | 0 | 0 | 0 |  |  | s_LL | 0 | 0 | 0 | 0 | 0 |  | L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
SUPPLY & INSTALL
Supply & Install | type / quality |  |  | 0 |  |  | LS | 0 | 0 | 0 |  |  |  | LS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | LS | 0 | 0 | 0 |  |  |  | LS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | LS | 0 | 0 | 0 |  |  |  | LS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL SUPPLY & INSTALL |  | 0 | 0 | 0 |  |  | s_LS | 0 | 0 | 0 | 0 | 0 |  | L | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
SUBTOTAL LINE (6) |  | 0 | 0 | 0 |  |  | LT | 0 | 0 | 0 | 0 | 0 |  | LT | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
TOTAL OH LINE MATERIAL |  | 0 | 0 | 0 |  |  | s_s_LM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
TOTAL OH LINE LABOUR |  | 0 | 0 | 0 |  |  | s_S_LL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
TOTAL OH LINE SUPPLY & INSTALL |  | 0 | 0 | 0 |  |  | s_s_LS | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
TOTAL TRANSMISSION UG LINE |  | 0 | 0 | 0 |  |  | s_LT | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0

## Subs 3
SUBSTATION SUMMARY | [6 empty] | 1 | PCP | PCP #1 | 0 | PCP # 1 |  |  | 2 | PCP | PCP #2 | 0 | PCP # 2 |  |  | 3 | PCP | PCP #3 | 0 | PCP # 3 |  |  | 4 | PCP | PCP #4 | 0 | PCP # 4 |  |  | 5 | PCP | PCP #5 | 0 | PCP # 5 |  |  | 6 | PCP | PCP #6 | 0 | PCP # 6 |  |  | 7 | PCP | PCP #7 | 0 | PCP # 7 |  |  | 8 | PCP | PCP #8 | 0 | PCP # 8 |  |  | 9 | PCP | PCP #9 | 0 | PCP # 9 |  |  | 10 | PCP | PCP #10 | 0 | PCP # 10 |  |  | 11 | PCP | PCP #11 | 0 | PCP # 11 |  |  | 12 | PCP | PCP #12 | 0 | PCP # 12 |  |  | 13 | Final Cost Report | Final Cost Report #13 | 0 | Final Cost Report # 13 |  |  | 14 | PCP | PCP #14 | 0 | PCP # 14 |  |  | 15 | PCP | PCP #15 | 0 | PCP # 15 |  |  | 16 | PCP | PCP #16 | 0 | PCP # 16 |  |  | 17 | PCP | PCP #17 | 0 | PCP # 17
|  | SYSTEM | PARTICIPANT | TOTAL | ASSUMPTIONS |  |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments
Substation < Name, # > | [10 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # >
MATERIALS
Major Equipment |  | 0 | 0 | 0 |  |  | s_SME | 0 | 0 | 0 | 0 | 0 |  | SM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Transformer | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Transformer | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Circuit Breaker | *quantity, voltage, type <AIS, GIS, Metal Clad> |  |  | 0 |  | AIS: air insulated switchgear, GIS: gas insulated switchgear, Metal Clad: indoor switchgear and building | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Circuit Breaker | *quantity, voltage, type <AIS, GIS, Metal Clad> |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Circuit Breaker | *quantity, voltage, type <AIS, GIS, Metal Clad> |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Capacitor Bank | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Reactor bank | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SVS (Static VAR System) | quantity, voltage, rating, type |  |  | 0 |  | Includes: SVC (Static VAR Compensator) | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Current Transformer | quantity, voltage |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Current Transformer | quantity, voltage |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Potential Transformer | quantity, voltage |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Potential Transformer | quantity, voltage |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other major equipment | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other major equipment | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other major equipment | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Switchyard |  | 0 | 0 | 0 |  |  | s_SMS | 0 | 0 | 0 | 0 | 0 |  | SM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Foundations | quantity, type |  |  | 0 |  | Include: steel, concrete | SMS | 0 | 0 | 0 |  |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Bus Structure and Network |  |  |  | 0 |  | Include: support structures, bus pipe, connectors, bus (rigid & flex), surge arresters and all junction boxes | SMS | 0 | 0 | 0 |  |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Disconnect Switch | quantity, voltage, type |  |  | 0 |  |  | SMS | 0 | 0 | 0 |  |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Disconnect Switch | quantity, voltage, type |  |  | 0 |  |  | SMS | 0 | 0 | 0 |  |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Disconnect Switch | quantity, voltage, type |  |  | 0 |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cabling |  |  |  | 0 |  | Include: power and control cables, trenching and closing | SMS | 0 | 0 | 0 |  |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Station Service |  |  |  | 0 |  | Include: transmission (i.e. power transformer), transfer switch, AC/DC supply, distribution supply from distribution company. | SMS | 0 | 0 | 0 |  |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Control Building |  | 0 | 0 | 0 |  |  | s_SMC | 0 | 0 | 0 | 0 | 0 |  | SM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Structure | type, size |  |  | 0 |  |  | SMC | 0 | 0 | 0 |  |  |  | SMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Protection, Control, Metering | number of modules |  |  | 0 |  |  | SMC | 0 | 0 | 0 |  |  |  | SMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SCADA |  |  |  | 0 |  |  | SMC | 0 | 0 | 0 |  |  |  | SMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other | quality, type, description |  |  | 0 |  |  | SMC | 0 | 0 | 0 |  |  |  | SMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL MATERIALS |  | 0 | 0 | 0 |  |  | s_SM | 0 | 0 | 0 | 0 | 0 |  | S | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
LABOUR
Detailed Engineering |  | 0 | 0 | 0 |  |  | s_SLE | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Civil |  |  |  | 0 |  | Civil: site prep. & grading, foundations, structures and fencing | SLE | 0 | 0 | 0 |  |  |  | SLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Electric |  |  |  | 0 |  | Electric: electrical equipment and structures installation | SLE | 0 | 0 | 0 |  |  |  | SLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Geotechnical |  |  |  | 0 |  |  | SLE | 0 | 0 | 0 |  |  |  | SLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
P&C |  |  |  | 0 |  | P&C: relays and control modules, control wiring and layout | SLE | 0 | 0 | 0 |  |  |  | SLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SCADA |  |  |  | 0 |  | SCADA: all required SCADA engineering | SLE | 0 | 0 | 0 |  |  |  | SLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Construction |  | 0 | 0 | 0 |  |  | s_SLC | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Survey |  |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Site Preparation |  |  |  | 0 |  | Include: clearing, brushing, earthworks, grading, grounding conductor/rod/structure material | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Clearing |  |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Road |  |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Matting Rental | type, quantity, duration |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Matting Lay/Removal | hours |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Mobilization / demobilization | number and size |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
AC Mitigation |  |  |  | 0 |  | Mitigation of a Transmission AC circuit (current) corroding a parallel metallic object; i.e. pipeline, railway | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Regulatory Approvals / Permits |  |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Environment Management |  |  |  | 0 |  | Include: wash station, erosion control. May be included here or under Distributed Labour - Construction Management (Tab 5). | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Major Equipment Rental | type, number, duration |  |  | 0 |  | Include: only major or special type of rental; i.e. helicopter, large cranes | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Yards |  |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Shelter Facility |  |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Camp Services & Catering |  |  |  | 0 |  | Include: camp services and site security | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Field Supervision |  |  |  | 0 |  | Include: field supervisors, managers. May be included here or in Distributed Labour - Construction Managmeent (Tab 5) | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Indirects |  |  |  | 0 |  | Includes: trailers, fences, water, porta potties, etc. May be included here or under Distributed Labour - Construction Management (Tab 5). | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Foundations |  | 0 | 0 | 0 |  |  | s_SLF | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Helical Piles & Caps |  |  |  | 0 |  |  | SLF | 0 | 0 | 0 |  |  |  | SLF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Pipe Piles & Caps |  |  |  | 0 |  |  | SLF | 0 | 0 | 0 |  |  |  | SLF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Caission Piles & bolt cage |  |  |  | 0 |  |  | SLF | 0 | 0 | 0 |  |  |  | SLF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Electric |  | 0 | 0 | 0 |  |  | s_SLL | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Structure & Bus Work Installation |  |  |  | 0 |  |  | SLL | 0 | 0 | 0 |  |  |  | SLL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Installation of equipment |  |  |  | 0 |  | Include: Cabling, Cable Terminations, Ground and related switchyard facilities. | SLL | 0 | 0 | 0 |  |  |  | SLL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
P&C and SCADA |  | 0 | 0 | 0 |  |  | s_SLP | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
P&C and SCADA |  |  |  | 0 |  |  | SLP | 0 | 0 | 0 |  |  |  | SLP | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Commissioning |  | 0 | 0 | 0 |  |  | s_SLM | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Commissioning |  |  |  | 0 |  |  | SLM | 0 | 0 | 0 |  |  |  | SLM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL LABOUR |  | 0 | 0 | 0 |  |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | S | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
SUPPLY & INSTALL | [13 empty] | 0
Supply & Install 1 | type / quality |  |  | 0 |  |  | SLS | 0 | 0 | 0 |  |  |  | SLS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install 2 | type / quality |  |  | 0 |  |  | SLS | 0 | 0 | 0 |  |  |  | SLS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install 3 | type / quality |  |  | 0 |  |  | SLS | 0 | 0 | 0 |  |  |  | SLS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL SUPPLY & INSTALL |  | 0 | 0 | 0 |  |  | s_SLS | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
TOTAL SUBSTATION (1) |  | 0 | 0 | 0 |  |  | ST | 0 | 0 | 0 | 0 | 0 |  | ST | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Substation < Name, # > | [10 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # >
MATERIALS
Major Equipment |  | 0 | 0 | 0 |  |  | s_SME | 0 | 0 | 0 | 0 | 0 |  | SM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Transformer | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Transformer | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Circuit Breaker | *quantity, voltage, type <AIS, GIS, Metal Clad> |  |  | 0 |  | AIS: air insulated switchgear, GIS: gas insulated switchgear, Metal Clad: indoor switchgear and building | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Circuit Breaker | *quantity, voltage, type <AIS, GIS, Metal Clad> |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Circuit Breaker | *quantity, voltage, type <AIS, GIS, Metal Clad> |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Capacitor Bank | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Reactor bank | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SVS (Static VAR System) | quantity, voltage, rating, type |  |  | 0 |  | Includes: SVC (Static VAR Compensator) | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Current Transformer | quantity, voltage |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Current Transformer | quantity, voltage |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Potential Transformer | quantity, voltage |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Potential Transformer | quantity, voltage |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other major equipment | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other major equipment | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other major equipment | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Switchyard |  | 0 | 0 | 0 |  |  | s_SMS | 0 | 0 | 0 | 0 | 0 |  | SM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Foundations | quantity, type |  |  | 0 |  | Include: steel, concrete | SMS | 0 | 0 | 0 |  |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Bus Structure and Network |  |  |  | 0 |  | Include: support structures, bus pipe, connectors, bus (rigid & flex), surge arresters and all junction boxes | SMS | 0 | 0 | 0 |  |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Disconnect Switch | quantity, voltage, type |  |  | 0 |  |  | SMS | 0 | 0 | 0 |  |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Disconnect Switch | quantity, voltage, type |  |  | 0 |  |  | SMS | 0 | 0 | 0 |  |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Disconnect Switch | quantity, voltage, type |  |  | 0 |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cabling |  |  |  | 0 |  | Include: power and control cables, trenching and closing | SMS | 0 | 0 | 0 |  |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Station Service |  |  |  | 0 |  | Include: transmission (i.e. power transformer), transfer switch, AC/DC supply, distribution supply from distribution company. | SMS | 0 | 0 | 0 |  |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Control Building |  | 0 | 0 | 0 |  |  | s_SMC | 0 | 0 | 0 | 0 | 0 |  | SM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Structure | type, size |  |  | 0 |  |  | SMC | 0 | 0 | 0 |  |  |  | SMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Protection, Control, Metering | number of modules |  |  | 0 |  |  | SMC | 0 | 0 | 0 |  |  |  | SMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SCADA |  |  |  | 0 |  |  | SMC | 0 | 0 | 0 |  |  |  | SMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other | quality, type, description |  |  | 0 |  |  | SMC | 0 | 0 | 0 |  |  |  | SMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL MATERIALS |  | 0 | 0 | 0 |  |  | s_SM | 0 | 0 | 0 | 0 | 0 |  | S | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
LABOUR
Detailed Engineering |  | 0 | 0 | 0 |  |  | s_SLE | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Civil |  |  |  | 0 |  | Civil: site prep. & grading, foundations, structures and fencing | SLE | 0 | 0 | 0 |  |  |  | SLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Electric |  |  |  | 0 |  | Electric: electrical equipment and structures installation | SLE | 0 | 0 | 0 |  |  |  | SLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Geotechnical |  |  |  | 0 |  |  | SLE | 0 | 0 | 0 |  |  |  | SLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
P&C |  |  |  | 0 |  | P&C: relays and control modules, control wiring and layout | SLE | 0 | 0 | 0 |  |  |  | SLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SCADA |  |  |  | 0 |  | SCADA: all required SCADA engineering | SLE | 0 | 0 | 0 |  |  |  | SLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Construction |  | 0 | 0 | 0 |  |  | s_SLC | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Survey |  |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Site Preparation |  |  |  | 0 |  | Include: clearing, brushing, earthworks, grading, grounding conductor/rod/structure material | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Clearing |  |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Road |  |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Matting Rental | type, quantity, duration |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Matting Lay/Removal | hours |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Mobilization / demobilization | number and size |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
AC Mitigation |  |  |  | 0 |  | Mitigation of a Transmission AC circuit (current) corroding a parallel metallic object; i.e. pipeline, railway | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Regulatory Approvals / Permits |  |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Environment Management |  |  |  | 0 |  | Include: wash station, erosion control. May be included here or under Distributed Labour - Construction Management (Tab 5). | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Major Equipment Rental | type, number, duration |  |  | 0 |  | Include: only major or special type of rental; i.e. helicopter, large cranes | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Yards |  |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Shelter Facility |  |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Camp Services & Catering |  |  |  | 0 |  | Include: camp services and site security | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Field Supervision |  |  |  | 0 |  | Include: field supervisors, managers. May be included here or in Distributed Labour - Construction Managmeent (Tab 5) | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Indirects |  |  |  | 0 |  | Includes: trailers, fences, water, porta potties, etc. May be included here or under Distributed Labour - Construction Management (Tab 5). | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Foundations |  | 0 | 0 | 0 |  |  | s_SLF | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Helical Piles & Caps |  |  |  | 0 |  |  | SLF | 0 | 0 | 0 |  |  |  | SLF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Pipe Piles & Caps |  |  |  | 0 |  |  | SLF | 0 | 0 | 0 |  |  |  | SLF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Caission Piles & bolt cage |  |  |  | 0 |  |  | SLF | 0 | 0 | 0 |  |  |  | SLF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Electric |  | 0 | 0 | 0 |  |  | s_SLL | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Structure & Bus Work Installation |  |  |  | 0 |  |  | SLL | 0 | 0 | 0 |  |  |  | SLL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Installation of equipment |  |  |  | 0 |  | Include: Cabling, Cable Terminations, Ground and related switchyard facilities. | SLL | 0 | 0 | 0 |  |  |  | SLL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
P&C and SCADA |  | 0 | 0 | 0 |  |  | s_SLP | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
P&C and SCADA |  |  |  | 0 |  |  | SLP | 0 | 0 | 0 |  |  |  | SLP | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Commissioning |  | 0 | 0 | 0 |  |  | s_SLM | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Commissioning |  |  |  | 0 |  |  | SLM | 0 | 0 | 0 |  |  |  | SLM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL LABOUR |  | 0 | 0 | 0 |  |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | S | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
SUPPLY & INSTALL | [13 empty] | 0
Supply & Install 1 | type / quality |  |  | 0 |  |  | SLS | 0 | 0 | 0 |  |  |  | SLS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install 2 | type / quality |  |  | 0 |  |  | SLS | 0 | 0 | 0 |  |  |  | SLS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install 3 | type / quality |  |  | 0 |  |  | SLS | 0 | 0 | 0 |  |  |  | SLS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL SUPPLY & INSTALL |  | 0 | 0 | 0 |  |  | s_SLS | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
TOTAL SUBSTATION (2) |  | 0 | 0 | 0 |  |  | ST | 0 | 0 | 0 | 0 | 0 |  | ST | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Substation < Name, # > | [10 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # >
MATERIALS
Major Equipment |  | 0 | 0 | 0 |  |  | s_SME | 0 | 0 | 0 | 0 | 0 |  | SM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Transformer | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Transformer | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Circuit Breaker | *quantity, voltage, type <AIS, GIS, Metal Clad> |  |  | 0 |  | AIS: air insulated switchgear, GIS: gas insulated switchgear, Metal Clad: indoor switchgear and building | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Circuit Breaker | *quantity, voltage, type <AIS, GIS, Metal Clad> |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Circuit Breaker | *quantity, voltage, type <AIS, GIS, Metal Clad> |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Capacitor Bank | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Reactor bank | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SVS (Static VAR System) | quantity, voltage, rating, type |  |  | 0 |  | Includes: SVC (Static VAR Compensator) | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Current Transformer | quantity, voltage |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Current Transformer | quantity, voltage |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Potential Transformer | quantity, voltage |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Potential Transformer | quantity, voltage |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other major equipment | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other major equipment | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other major equipment | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Switchyard |  | 0 | 0 | 0 |  |  | s_SMS | 0 | 0 | 0 | 0 | 0 |  | SM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Foundations | quantity, type |  |  | 0 |  | Include: steel, concrete | SMS | 0 | 0 | 0 |  |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Bus Structure and Network |  |  |  | 0 |  | Include: support structures, bus pipe, connectors, bus (rigid & flex), surge arresters and all junction boxes | SMS | 0 | 0 | 0 |  |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Disconnect Switch | quantity, voltage, type |  |  | 0 |  |  | SMS | 0 | 0 | 0 |  |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Disconnect Switch | quantity, voltage, type |  |  | 0 |  |  | SMS | 0 | 0 | 0 |  |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Disconnect Switch | quantity, voltage, type |  |  | 0 |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cabling |  |  |  | 0 |  | Include: power and control cables, trenching and closing | SMS | 0 | 0 | 0 |  |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Station Service |  |  |  | 0 |  | Include: transmission (i.e. power transformer), transfer switch, AC/DC supply, distribution supply from distribution company. | SMS | 0 | 0 | 0 |  |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Control Building |  | 0 | 0 | 0 |  |  | s_SMC | 0 | 0 | 0 | 0 | 0 |  | SM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Structure | type, size |  |  | 0 |  |  | SMC | 0 | 0 | 0 |  |  |  | SMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Protection, Control, Metering | number of modules |  |  | 0 |  |  | SMC | 0 | 0 | 0 |  |  |  | SMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SCADA |  |  |  | 0 |  |  | SMC | 0 | 0 | 0 |  |  |  | SMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other | quality, type, description |  |  | 0 |  |  | SMC | 0 | 0 | 0 |  |  |  | SMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL MATERIALS |  | 0 | 0 | 0 |  |  | s_SM | 0 | 0 | 0 | 0 | 0 |  | S | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
LABOUR
Detailed Engineering |  | 0 | 0 | 0 |  |  | s_SLE | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Civil |  |  |  | 0 |  | Civil: site prep. & grading, foundations, structures and fencing | SLE | 0 | 0 | 0 |  |  |  | SLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Electric |  |  |  | 0 |  | Electric: electrical equipment and structures installation | SLE | 0 | 0 | 0 |  |  |  | SLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Geotechnical |  |  |  | 0 |  |  | SLE | 0 | 0 | 0 |  |  |  | SLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
P&C |  |  |  | 0 |  | P&C: relays and control modules, control wiring and layout | SLE | 0 | 0 | 0 |  |  |  | SLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SCADA |  |  |  | 0 |  | SCADA: all required SCADA engineering | SLE | 0 | 0 | 0 |  |  |  | SLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Construction |  | 0 | 0 | 0 |  |  | s_SLC | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Survey |  |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Site Preparation |  |  |  | 0 |  | Include: clearing, brushing, earthworks, grading, grounding conductor/rod/structure material | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Clearing |  |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Road |  |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Matting Rental | type, quantity, duration |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Matting Lay/Removal | hours |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Mobilization / demobilization | number and size |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
AC Mitigation |  |  |  | 0 |  | Mitigation of a Transmission AC circuit (current) corroding a parallel metallic object; i.e. pipeline, railway | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Regulatory Approvals / Permits |  |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Environment Management |  |  |  | 0 |  | Include: wash station, erosion control. May be included here or under Distributed Labour - Construction Management (Tab 5). | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Major Equipment Rental | type, number, duration |  |  | 0 |  | Include: only major or special type of rental; i.e. helicopter, large cranes | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Yards |  |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Shelter Facility |  |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Camp Services & Catering |  |  |  | 0 |  | Include: camp services and site security | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Field Supervision |  |  |  | 0 |  | Include: field supervisors, managers. May be included here or in Distributed Labour - Construction Managmeent (Tab 5) | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Indirects |  |  |  | 0 |  | Includes: trailers, fences, water, porta potties, etc. May be included here or under Distributed Labour - Construction Management (Tab 5). | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Foundations |  | 0 | 0 | 0 |  |  | s_SLF | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Helical Piles & Caps |  |  |  | 0 |  |  | SLF | 0 | 0 | 0 |  |  |  | SLF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Pipe Piles & Caps |  |  |  | 0 |  |  | SLF | 0 | 0 | 0 |  |  |  | SLF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Caission Piles & bolt cage |  |  |  | 0 |  |  | SLF | 0 | 0 | 0 |  |  |  | SLF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Electric |  | 0 | 0 | 0 |  |  | s_SLL | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Structure & Bus Work Installation |  |  |  | 0 |  |  | SLL | 0 | 0 | 0 |  |  |  | SLL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Installation of equipment |  |  |  | 0 |  | Include: Cabling, Cable Terminations, Ground and related switchyard facilities. | SLL | 0 | 0 | 0 |  |  |  | SLL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
P&C and SCADA |  | 0 | 0 | 0 |  |  | s_SLP | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
P&C and SCADA |  |  |  | 0 |  |  | SLP | 0 | 0 | 0 |  |  |  | SLP | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Commissioning |  | 0 | 0 | 0 |  |  | s_SLM | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Commissioning |  |  |  | 0 |  |  | SLM | 0 | 0 | 0 |  |  |  | SLM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL LABOUR |  | 0 | 0 | 0 |  |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | S | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
SUPPLY & INSTALL | [13 empty] | 0
Supply & Install 1 | type / quality |  |  | 0 |  |  | SLS | 0 | 0 | 0 |  |  |  | SLS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install 2 | type / quality |  |  | 0 |  |  | SLS | 0 | 0 | 0 |  |  |  | SLS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install 3 | type / quality |  |  | 0 |  |  | SLS | 0 | 0 | 0 |  |  |  | SLS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL SUPPLY & INSTALL |  | 0 | 0 | 0 |  |  | s_SLS | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
TOTAL SUBSTATION (3) |  | 0 | 0 | 0 |  |  | ST | 0 | 0 | 0 | 0 | 0 |  | ST | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Substation < Name, # > | [10 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # >
MATERIALS
Major Equipment |  | 0 | 0 | 0 |  |  | s_SME | 0 | 0 | 0 | 0 | 0 |  | SM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Transformer | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Transformer | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Circuit Breaker | *quantity, voltage, type <AIS, GIS, Metal Clad> |  |  | 0 |  | AIS: air insulated switchgear, GIS: gas insulated switchgear, Metal Clad: indoor switchgear and building | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Circuit Breaker | *quantity, voltage, type <AIS, GIS, Metal Clad> |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Circuit Breaker | *quantity, voltage, type <AIS, GIS, Metal Clad> |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Capacitor Bank | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Reactor bank | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SVS (Static VAR System) | quantity, voltage, rating, type |  |  | 0 |  | Includes: SVC (Static VAR Compensator) | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Current Transformer | quantity, voltage |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Current Transformer | quantity, voltage |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Potential Transformer | quantity, voltage |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Potential Transformer | quantity, voltage |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other major equipment | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other major equipment | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other major equipment | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Switchyard |  | 0 | 0 | 0 |  |  | s_SMS | 0 | 0 | 0 | 0 | 0 |  | SM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Foundations | quantity, type |  |  | 0 |  | Include: steel, concrete | SMS | 0 | 0 | 0 |  |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Bus Structure and Network |  |  |  | 0 |  | Include: support structures, bus pipe, connectors, bus (rigid & flex), surge arresters and all junction boxes | SMS | 0 | 0 | 0 |  |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Disconnect Switch | quantity, voltage, type |  |  | 0 |  |  | SMS | 0 | 0 | 0 |  |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Disconnect Switch | quantity, voltage, type |  |  | 0 |  |  | SMS | 0 | 0 | 0 |  |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Disconnect Switch | quantity, voltage, type |  |  | 0 |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cabling |  |  |  | 0 |  | Include: power and control cables, trenching and closing | SMS | 0 | 0 | 0 |  |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Station Service |  |  |  | 0 |  | Include: transmission (i.e. power transformer), transfer switch, AC/DC supply, distribution supply from distribution company. | SMS | 0 | 0 | 0 |  |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Control Building |  | 0 | 0 | 0 |  |  | s_SMC | 0 | 0 | 0 | 0 | 0 |  | SM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Structure | type, size |  |  | 0 |  |  | SMC | 0 | 0 | 0 |  |  |  | SMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Protection, Control, Metering | number of modules |  |  | 0 |  |  | SMC | 0 | 0 | 0 |  |  |  | SMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SCADA |  |  |  | 0 |  |  | SMC | 0 | 0 | 0 |  |  |  | SMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other | quality, type, description |  |  | 0 |  |  | SMC | 0 | 0 | 0 |  |  |  | SMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL MATERIALS |  | 0 | 0 | 0 |  |  | s_SM | 0 | 0 | 0 | 0 | 0 |  | S | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
LABOUR
Detailed Engineering |  | 0 | 0 | 0 |  |  | s_SLE | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Civil |  |  |  | 0 |  | Civil: site prep. & grading, foundations, structures and fencing | SLE | 0 | 0 | 0 |  |  |  | SLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Electric |  |  |  | 0 |  | Electric: electrical equipment and structures installation | SLE | 0 | 0 | 0 |  |  |  | SLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Geotechnical |  |  |  | 0 |  |  | SLE | 0 | 0 | 0 |  |  |  | SLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
P&C |  |  |  | 0 |  | P&C: relays and control modules, control wiring and layout | SLE | 0 | 0 | 0 |  |  |  | SLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SCADA |  |  |  | 0 |  | SCADA: all required SCADA engineering | SLE | 0 | 0 | 0 |  |  |  | SLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Construction |  | 0 | 0 | 0 |  |  | s_SLC | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Survey |  |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Site Preparation |  |  |  | 0 |  | Include: clearing, brushing, earthworks, grading, grounding conductor/rod/structure material | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Clearing |  |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Road |  |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Matting Rental | type, quantity, duration |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Matting Lay/Removal | hours |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Mobilization / demobilization | number and size |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
AC Mitigation |  |  |  | 0 |  | Mitigation of a Transmission AC circuit (current) corroding a parallel metallic object; i.e. pipeline, railway | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Regulatory Approvals / Permits |  |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Environment Management |  |  |  | 0 |  | Include: wash station, erosion control. May be included here or under Distributed Labour - Construction Management (Tab 5). | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Major Equipment Rental | type, number, duration |  |  | 0 |  | Include: only major or special type of rental; i.e. helicopter, large cranes | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Yards |  |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Shelter Facility |  |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Camp Services & Catering |  |  |  | 0 |  | Include: camp services and site security | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Field Supervision |  |  |  | 0 |  | Include: field supervisors, managers. May be included here or in Distributed Labour - Construction Managmeent (Tab 5) | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Indirects |  |  |  | 0 |  | Includes: trailers, fences, water, porta potties, etc. May be included here or under Distributed Labour - Construction Management (Tab 5). | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Foundations |  | 0 | 0 | 0 |  |  | s_SLF | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Helical Piles & Caps |  |  |  | 0 |  |  | SLF | 0 | 0 | 0 |  |  |  | SLF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Pipe Piles & Caps |  |  |  | 0 |  |  | SLF | 0 | 0 | 0 |  |  |  | SLF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Caission Piles & bolt cage |  |  |  | 0 |  |  | SLF | 0 | 0 | 0 |  |  |  | SLF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Electric |  | 0 | 0 | 0 |  |  | s_SLL | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Structure & Bus Work Installation |  |  |  | 0 |  |  | SLL | 0 | 0 | 0 |  |  |  | SLL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Installation of equipment |  |  |  | 0 |  | Include: Cabling, Cable Terminations, Ground and related switchyard facilities. | SLL | 0 | 0 | 0 |  |  |  | SLL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
P&C and SCADA |  | 0 | 0 | 0 |  |  | s_SLP | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
P&C and SCADA |  |  |  | 0 |  |  | SLP | 0 | 0 | 0 |  |  |  | SLP | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Commissioning |  | 0 | 0 | 0 |  |  | s_SLM | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Commissioning |  |  |  | 0 |  |  | SLM | 0 | 0 | 0 |  |  |  | SLM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL LABOUR |  | 0 | 0 | 0 |  |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | S | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
SUPPLY & INSTALL | [13 empty] | 0
Supply & Install 1 | type / quality |  |  | 0 |  |  | SLS | 0 | 0 | 0 |  |  |  | SLS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install 2 | type / quality |  |  | 0 |  |  | SLS | 0 | 0 | 0 |  |  |  | SLS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install 3 | type / quality |  |  | 0 |  |  | SLS | 0 | 0 | 0 |  |  |  | SLS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL SUPPLY & INSTALL |  | 0 | 0 | 0 |  |  | s_SLS | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
TOTAL SUBSTATION (4) |  | 0 | 0 | 0 |  |  | ST | 0 | 0 | 0 | 0 | 0 |  | ST | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Substation < Name, # > | [10 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # >
MATERIALS
Major Equipment |  | 0 | 0 | 0 |  |  | s_SME | 0 | 0 | 0 | 0 | 0 |  | SM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Transformer | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Transformer | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Circuit Breaker | *quantity, voltage, type <AIS, GIS, Metal Clad> |  |  | 0 |  | AIS: air insulated switchgear, GIS: gas insulated switchgear, Metal Clad: indoor switchgear and building | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Circuit Breaker | *quantity, voltage, type <AIS, GIS, Metal Clad> |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Circuit Breaker | *quantity, voltage, type <AIS, GIS, Metal Clad> |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Capacitor Bank | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Reactor bank | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SVS (Static VAR System) | quantity, voltage, rating, type |  |  | 0 |  | Includes: SVC (Static VAR Compensator) | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Current Transformer | quantity, voltage |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Current Transformer | quantity, voltage |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Potential Transformer | quantity, voltage |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Potential Transformer | quantity, voltage |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other major equipment | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other major equipment | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other major equipment | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Switchyard |  | 0 | 0 | 0 |  |  | s_SMS | 0 | 0 | 0 | 0 | 0 |  | SM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Foundations | quantity, type |  |  | 0 |  | Include: steel, concrete | SMS | 0 | 0 | 0 |  |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Bus Structure and Network |  |  |  | 0 |  | Include: support structures, bus pipe, connectors, bus (rigid & flex), surge arresters and all junction boxes | SMS | 0 | 0 | 0 |  |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Disconnect Switch | quantity, voltage, type |  |  | 0 |  |  | SMS | 0 | 0 | 0 |  |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Disconnect Switch | quantity, voltage, type |  |  | 0 |  |  | SMS | 0 | 0 | 0 |  |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Disconnect Switch | quantity, voltage, type |  |  | 0 |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cabling |  |  |  | 0 |  | Include: power and control cables, trenching and closing | SMS | 0 | 0 | 0 |  |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Station Service |  |  |  | 0 |  | Include: transmission (i.e. power transformer), transfer switch, AC/DC supply, distribution supply from distribution company. | SMS | 0 | 0 | 0 |  |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Control Building |  | 0 | 0 | 0 |  |  | s_SMC | 0 | 0 | 0 | 0 | 0 |  | SM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Structure | type, size |  |  | 0 |  |  | SMC | 0 | 0 | 0 |  |  |  | SMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Protection, Control, Metering | number of modules |  |  | 0 |  |  | SMC | 0 | 0 | 0 |  |  |  | SMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SCADA |  |  |  | 0 |  |  | SMC | 0 | 0 | 0 |  |  |  | SMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other | quality, type, description |  |  | 0 |  |  | SMC | 0 | 0 | 0 |  |  |  | SMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL MATERIALS |  | 0 | 0 | 0 |  |  | s_SM | 0 | 0 | 0 | 0 | 0 |  | S | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
LABOUR
Detailed Engineering |  | 0 | 0 | 0 |  |  | s_SLE | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Civil |  |  |  | 0 |  | Civil: site prep. & grading, foundations, structures and fencing | SLE | 0 | 0 | 0 |  |  |  | SLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Electric |  |  |  | 0 |  | Electric: electrical equipment and structures installation | SLE | 0 | 0 | 0 |  |  |  | SLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Geotechnical |  |  |  | 0 |  |  | SLE | 0 | 0 | 0 |  |  |  | SLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
P&C |  |  |  | 0 |  | P&C: relays and control modules, control wiring and layout | SLE | 0 | 0 | 0 |  |  |  | SLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SCADA |  |  |  | 0 |  | SCADA: all required SCADA engineering | SLE | 0 | 0 | 0 |  |  |  | SLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Construction |  | 0 | 0 | 0 |  |  | s_SLC | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Survey |  |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Site Preparation |  |  |  | 0 |  | Include: clearing, brushing, earthworks, grading, grounding conductor/rod/structure material | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Clearing |  |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Road |  |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Matting Rental | type, quantity, duration |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Matting Lay/Removal | hours |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Mobilization / demobilization | number and size |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
AC Mitigation |  |  |  | 0 |  | Mitigation of a Transmission AC circuit (current) corroding a parallel metallic object; i.e. pipeline, railway | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Regulatory Approvals / Permits |  |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Environment Management |  |  |  | 0 |  | Include: wash station, erosion control. May be included here or under Distributed Labour - Construction Management (Tab 5). | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Major Equipment Rental | type, number, duration |  |  | 0 |  | Include: only major or special type of rental; i.e. helicopter, large cranes | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Yards |  |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Shelter Facility |  |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Camp Services & Catering |  |  |  | 0 |  | Include: camp services and site security | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Field Supervision |  |  |  | 0 |  | Include: field supervisors, managers. May be included here or in Distributed Labour - Construction Managmeent (Tab 5) | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Indirects |  |  |  | 0 |  | Includes: trailers, fences, water, porta potties, etc. May be included here or under Distributed Labour - Construction Management (Tab 5). | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Foundations |  | 0 | 0 | 0 |  |  | s_SLF | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Helical Piles & Caps |  |  |  | 0 |  |  | SLF | 0 | 0 | 0 |  |  |  | SLF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Pipe Piles & Caps |  |  |  | 0 |  |  | SLF | 0 | 0 | 0 |  |  |  | SLF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Caission Piles & bolt cage |  |  |  | 0 |  |  | SLF | 0 | 0 | 0 |  |  |  | SLF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Electric |  | 0 | 0 | 0 |  |  | s_SLL | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Structure & Bus Work Installation |  |  |  | 0 |  |  | SLL | 0 | 0 | 0 |  |  |  | SLL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Installation of equipment |  |  |  | 0 |  | Include: Cabling, Cable Terminations, Ground and related switchyard facilities. | SLL | 0 | 0 | 0 |  |  |  | SLL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
P&C and SCADA |  | 0 | 0 | 0 |  |  | s_SLP | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
P&C and SCADA |  |  |  | 0 |  |  | SLP | 0 | 0 | 0 |  |  |  | SLP | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Commissioning |  | 0 | 0 | 0 |  |  | s_SLM | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Commissioning |  |  |  | 0 |  |  | SLM | 0 | 0 | 0 |  |  |  | SLM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL LABOUR |  | 0 | 0 | 0 |  |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | S | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
SUPPLY & INSTALL | [13 empty] | 0
Supply & Install 1 | type / quality |  |  | 0 |  |  | SLS | 0 | 0 | 0 |  |  |  | SLS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install 2 | type / quality |  |  | 0 |  |  | SLS | 0 | 0 | 0 |  |  |  | SLS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install 3 | type / quality |  |  | 0 |  |  | SLS | 0 | 0 | 0 |  |  |  | SLS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL SUPPLY & INSTALL |  | 0 | 0 | 0 |  |  | s_SLS | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
TOTAL SUBSTATION (5) |  | 0 | 0 | 0 |  |  | ST | 0 | 0 | 0 | 0 | 0 |  | ST | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Substation < Name, # > | [10 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # > | [6 empty] | Substation < Name, # >
MATERIALS
Major Equipment |  | 0 | 0 | 0 |  |  | s_SME | 0 | 0 | 0 | 0 | 0 |  | SM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Transformer | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Transformer | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Circuit Breaker | *quantity, voltage, type <AIS, GIS, Metal Clad> |  |  | 0 |  | AIS: air insulated switchgear, GIS: gas insulated switchgear, Metal Clad: indoor switchgear and building | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Circuit Breaker | *quantity, voltage, type <AIS, GIS, Metal Clad> |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Circuit Breaker | *quantity, voltage, type <AIS, GIS, Metal Clad> |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Capacitor Bank | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Reactor bank | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SVS (Static VAR System) | quantity, voltage, rating, type |  |  | 0 |  | Includes: SVC (Static VAR Compensator) | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Current Transformer | quantity, voltage |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Current Transformer | quantity, voltage |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Potential Transformer | quantity, voltage |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Potential Transformer | quantity, voltage |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other major equipment | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other major equipment | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other major equipment | quantity, voltage, rating |  |  | 0 |  |  | SME | 0 | 0 | 0 |  |  |  | SME | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Switchyard |  | 0 | 0 | 0 |  |  | s_SMS | 0 | 0 | 0 | 0 | 0 |  | SM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Foundations | quantity, type |  |  | 0 |  | Include: steel, concrete | SMS | 0 | 0 | 0 |  |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Bus Structure and Network |  |  |  | 0 |  | Include: support structures, bus pipe, connectors, bus (rigid & flex), surge arresters and all junction boxes | SMS | 0 | 0 | 0 |  |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Disconnect Switch | quantity, voltage, type |  |  | 0 |  |  | SMS | 0 | 0 | 0 |  |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Disconnect Switch | quantity, voltage, type |  |  | 0 |  |  | SMS | 0 | 0 | 0 |  |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Disconnect Switch | quantity, voltage, type |  |  | 0 |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Cabling |  |  |  | 0 |  | Include: power and control cables, trenching and closing | SMS | 0 | 0 | 0 |  |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Station Service |  |  |  | 0 |  | Include: transmission (i.e. power transformer), transfer switch, AC/DC supply, distribution supply from distribution company. | SMS | 0 | 0 | 0 |  |  |  | SMS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Control Building |  | 0 | 0 | 0 |  |  | s_SMC | 0 | 0 | 0 | 0 | 0 |  | SM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Structure | type, size |  |  | 0 |  |  | SMC | 0 | 0 | 0 |  |  |  | SMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Protection, Control, Metering | number of modules |  |  | 0 |  |  | SMC | 0 | 0 | 0 |  |  |  | SMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SCADA |  |  |  | 0 |  |  | SMC | 0 | 0 | 0 |  |  |  | SMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other | quality, type, description |  |  | 0 |  |  | SMC | 0 | 0 | 0 |  |  |  | SMC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL MATERIALS |  | 0 | 0 | 0 |  |  | s_SM | 0 | 0 | 0 | 0 | 0 |  | S | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
LABOUR
Detailed Engineering |  | 0 | 0 | 0 |  |  | s_SLE | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Civil |  |  |  | 0 |  | Civil: site prep. & grading, foundations, structures and fencing | SLE | 0 | 0 | 0 |  |  |  | SLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Electric |  |  |  | 0 |  | Electric: electrical equipment and structures installation | SLE | 0 | 0 | 0 |  |  |  | SLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Geotechnical |  |  |  | 0 |  |  | SLE | 0 | 0 | 0 |  |  |  | SLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
P&C |  |  |  | 0 |  | P&C: relays and control modules, control wiring and layout | SLE | 0 | 0 | 0 |  |  |  | SLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SCADA |  |  |  | 0 |  | SCADA: all required SCADA engineering | SLE | 0 | 0 | 0 |  |  |  | SLE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Construction |  | 0 | 0 | 0 |  |  | s_SLC | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Survey |  |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Site Preparation |  |  |  | 0 |  | Include: clearing, brushing, earthworks, grading, grounding conductor/rod/structure material | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Clearing |  |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Road |  |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Matting Rental | type, quantity, duration |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Access Matting Lay/Removal | hours |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Mobilization / demobilization | number and size |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
AC Mitigation |  |  |  | 0 |  | Mitigation of a Transmission AC circuit (current) corroding a parallel metallic object; i.e. pipeline, railway | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Regulatory Approvals / Permits |  |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Environment Management |  |  |  | 0 |  | Include: wash station, erosion control. May be included here or under Distributed Labour - Construction Management (Tab 5). | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Major Equipment Rental | type, number, duration |  |  | 0 |  | Include: only major or special type of rental; i.e. helicopter, large cranes | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Yards |  |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Shelter Facility |  |  |  | 0 |  |  | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Camp Services & Catering |  |  |  | 0 |  | Include: camp services and site security | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Field Supervision |  |  |  | 0 |  | Include: field supervisors, managers. May be included here or in Distributed Labour - Construction Managmeent (Tab 5) | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Indirects |  |  |  | 0 |  | Includes: trailers, fences, water, porta potties, etc. May be included here or under Distributed Labour - Construction Management (Tab 5). | SLC | 0 | 0 | 0 |  |  |  | SLC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Foundations |  | 0 | 0 | 0 |  |  | s_SLF | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Helical Piles & Caps |  |  |  | 0 |  |  | SLF | 0 | 0 | 0 |  |  |  | SLF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Pipe Piles & Caps |  |  |  | 0 |  |  | SLF | 0 | 0 | 0 |  |  |  | SLF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Caission Piles & bolt cage |  |  |  | 0 |  |  | SLF | 0 | 0 | 0 |  |  |  | SLF | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Electric |  | 0 | 0 | 0 |  |  | s_SLL | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Structure & Bus Work Installation |  |  |  | 0 |  |  | SLL | 0 | 0 | 0 |  |  |  | SLL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Installation of equipment |  |  |  | 0 |  | Include: Cabling, Cable Terminations, Ground and related switchyard facilities. | SLL | 0 | 0 | 0 |  |  |  | SLL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
P&C and SCADA |  | 0 | 0 | 0 |  |  | s_SLP | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
P&C and SCADA |  |  |  | 0 |  |  | SLP | 0 | 0 | 0 |  |  |  | SLP | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Commissioning |  | 0 | 0 | 0 |  |  | s_SLM | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Commissioning |  |  |  | 0 |  |  | SLM | 0 | 0 | 0 |  |  |  | SLM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL LABOUR |  | 0 | 0 | 0 |  |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | S | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
SUPPLY & INSTALL | [13 empty] | 0
Supply & Install 1 | type / quality |  |  | 0 |  |  | SLS | 0 | 0 | 0 |  |  |  | SLS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install 2 | type / quality |  |  | 0 |  |  | SLS | 0 | 0 | 0 |  |  |  | SLS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install 3 | type / quality |  |  | 0 |  |  | SLS | 0 | 0 | 0 |  |  |  | SLS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL SUPPLY & INSTALL |  | 0 | 0 | 0 |  |  | s_SLS | 0 | 0 | 0 | 0 | 0 |  | SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
TOTAL SUBSTATION (6) |  | 0 | 0 | 0 |  |  | ST | 0 | 0 | 0 | 0 | 0 |  | ST | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
TOTAL SUBSTATION MATERIAL |  | 0 | 0 | 0 |  |  | s_s_SM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
TOTAL SUBSTATION LABOUR |  | 0 | 0 | 0 |  |  | s_S_SL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
TOTAL SUBSTATION SUPPLY & INSTALL |  | 0 | 0 | 0 |  |  | s_s_SLS | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
TOTAL SUBSTATION |  | 0 | 0 | 0 |  |  | s_ST | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0

## Tcom 4
TELECOMMUNICATIONS SUMMARY | [6 empty] | 1 | PCP | PCP #1 | 0 | PCP # 1 |  |  | 2 | PCP | PCP #2 | 0 | PCP # 2 |  |  | 3 | PCP | PCP #3 | 0 | PCP # 3 |  |  | 4 | PCP | PCP #4 | 0 | PCP # 4 |  |  | 5 | PCP | PCP #5 | 0 | PCP # 5 |  |  | 6 | PCP | PCP #6 | 0 | PCP # 6 |  |  | 7 | PCP | PCP #7 | 0 | PCP # 7 |  |  | 8 | PCP | PCP #8 | 0 | PCP # 8 |  |  | 9 | PCP | PCP #9 | 0 | PCP # 9 |  |  | 10 | PCP | PCP #10 | 0 | PCP # 10 |  |  | 11 | PCP | PCP #11 | 0 | PCP # 11 |  |  | 12 | PCP | PCP #12 | 0 | PCP # 12 |  |  | 13 | Final Cost Report | Final Cost Report #13 | 0 | Final Cost Report # 13 |  |  | 14 | PCP | PCP #14 | 0 | PCP # 14 |  |  | 15 | PCP | PCP #15 | 0 | PCP # 15 |  |  | 16 | PCP | PCP #16 | 0 | PCP # 16 |  |  | 17 | PCP | PCP #17 | 0 | PCP # 17
|  | SYSTEM | PARTICIPANT | TOTAL | ASSUMPTIONS |  |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments
Telecommunication Site < Name, Location > | [10 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [20 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location >
MATERIALS | [5 empty] | Include: concrete
Tower | height |  |  | 0 |  | Include antennas and other | TM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Radio Equipment |  |  |  | 0 |  |  | TM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Building | size |  |  | 0 |  | Include if substation building not utilized | TM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Fibre | km, type |  |  | 0 |  |  | TM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Duct Banks | size, quantity |  |  | 0 |  |  | TM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other | Type / quality / description |  |  | 0 |  |  | TM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL MATERIALS |  | 0 | 0 | 0 |  |  | s_TM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
LABOUR
Detailed Engineering |  |  |  | 0 |  | Include: telecom, engineering services, geotechnical | TL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Site Construction |  |  |  | 0 |  | Include: clearing, brushing, earthworks, grading, surveys, foundations, access roads, permits, mtigations, equipment rental, mob/demob,yards,shelters, camps,site supervisions,indirects | TL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Tower Construction |  |  |  | 0 |  | Include: assembly, erecdtion and tower equipment installation | TL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Building & Equipment |  |  |  | 0 |  | Include: fabrication,transport and equipment installation | TL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Building & Equipment |  |  |  | 0 |  |  | TL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other | Type / quality |  |  | 0 |  | Describe: other in the assumptions field | TL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL LABOUR |  | 0 | 0 | 0 |  |  | s_TL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | TS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | TS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | TS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL SUPPLY & INSTALL |  | 0 | 0 | 0 |  |  | s_TS | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
TELECOM SITE (1) |  | 0 | 0 | 0 |  |  | TT | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Telecommunication Site < Name, Location > | [10 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [20 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location >
MATERIALS | [5 empty] | Include: concrete
Tower | height |  |  | 0 |  | Include antennas and other | TM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Radio Equipment |  |  |  | 0 |  |  | TM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Building | size |  |  | 0 |  | Include if substation building not utilized | TM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Fibre | km, type |  |  | 0 |  |  | TM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Duct Banks | size, quantity |  |  | 0 |  |  | TM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other | Type / quality / description |  |  | 0 |  |  | TM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL MATERIALS |  | 0 | 0 | 0 |  |  | s_TM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
LABOUR
Detailed Engineering |  |  |  | 0 |  | Include: telecom, engineering services, geotechnical | TL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Site Construction |  |  |  | 0 |  | Include: clearing, brushing, earthworks, grading, surveys, foundations, access roads, permits, mtigations, equipment rental, mob/demob,yards,shelters, camps,site supervisions,indirects | TL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Tower Construction |  |  |  | 0 |  | Include: assembly, erecdtion and tower equipment installation | TL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Building & Equipment |  |  |  | 0 |  | Include: fabrication,transport and equipment installation | TL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Commissioning |  |  |  | 0 |  |  | TL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other | Type / quality |  |  | 0 |  | Describe: other in the assumptions field | TL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL LABOUR |  | 0 | 0 | 0 |  |  | s_TL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | TS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | TS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | TS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL SUPPLY & INSTALL |  | 0 | 0 | 0 |  |  | s_TS | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
TELECOM SITE (2) |  | 0 | 0 | 0 |  |  | TT | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Telecommunication Site < Name, Location > | [10 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [20 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location >
MATERIALS | [5 empty] | Include: concrete
Tower | height |  |  | 0 |  | Include antennas and other | TM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Radio Equipment |  |  |  | 0 |  |  | TM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Building | size |  |  | 0 |  | Include if substation building not utilized | TM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Fibre | km, type |  |  | 0 |  |  | TM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Duct Banks | size, quantity |  |  | 0 |  |  | TM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other | Type / quality / description |  |  | 0 |  |  | TM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL MATERIALS |  | 0 | 0 | 0 |  |  | s_TM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
LABOUR
Detailed Engineering |  |  |  | 0 |  | Include: telecom, engineering services, geotechnical | TL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Site Construction |  |  |  | 0 |  | Include: clearing, brushing, earthworks, grading, surveys, foundations, access roads, permits, mtigations, equipment rental, mob/demob,yards,shelters, camps,site supervisions,indirects | TL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Tower Construction |  |  |  | 0 |  | Include: assembly, erecdtion and tower equipment installation | TL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Building & Equipment |  |  |  | 0 |  | Include: fabrication,transport and equipment installation | TL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Commissioning |  |  |  | 0 |  |  | TL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other | Type / quality |  |  | 0 |  | Describe: other in the assumptions field | TL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL LABOUR |  | 0 | 0 | 0 |  |  | s_TL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | TS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | TS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | TS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL SUPPLY & INSTALL |  | 0 | 0 | 0 |  |  | s_TS | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
TELECOM SITE (3) |  | 0 | 0 | 0 |  |  | TT | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Telecommunication Site < Name, Location > | [10 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [20 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location >
MATERIALS | [5 empty] | Include: concrete
Tower | height |  |  | 0 |  | Include antennas and other | TM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Radio Equipment |  |  |  | 0 |  |  | TM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Building | size |  |  | 0 |  | Include if substation building not utilized | TM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Fibre | km, type |  |  | 0 |  |  | TM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Duct Banks | size, quantity |  |  | 0 |  |  | TM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other | Type / quality / description |  |  | 0 |  |  | TM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL MATERIALS |  | 0 | 0 | 0 |  |  | s_TM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
LABOUR
Detailed Engineering |  |  |  | 0 |  | Include: telecom, engineering services, geotechnical | TL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Site Construction |  |  |  | 0 |  | Include: clearing, brushing, earthworks, grading, surveys, foundations, access roads, permits, mtigations, equipment rental, mob/demob,yards,shelters, camps,site supervisions,indirects | TL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Tower Construction |  |  |  | 0 |  | Include: assembly, erecdtion and tower equipment installation | TL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Building & Equipment |  |  |  | 0 |  | Include: fabrication,transport and equipment installation | TL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Commissioning |  |  |  | 0 |  |  | TL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other | Type / quality |  |  | 0 |  | Describe: other in the assumptions field | TL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL LABOUR |  | 0 | 0 | 0 |  |  | s_TL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | TS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | TS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | TS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL SUPPLY & INSTALL |  | 0 | 0 | 0 |  |  | s_TS | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
TELECOM SITE (4) |  | 0 | 0 | 0 |  |  | TT | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Telecommunication Site < Name, Location > | [10 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [20 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location >
MATERIALS | [5 empty] | Include: concrete
Tower | height |  |  | 0 |  | Include antennas and other | TM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Radio Equipment |  |  |  | 0 |  |  | TM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Building | size |  |  | 0 |  | Include if substation building not utilized | TM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Fibre | km, type |  |  | 0 |  |  | TM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Duct Banks | size, quantity |  |  | 0 |  |  | TM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other | Type / quality / description |  |  | 0 |  |  | TM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL MATERIALS |  | 0 | 0 | 0 |  |  | s_TM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
LABOUR
Detailed Engineering |  |  |  | 0 |  | Include: telecom, engineering services, geotechnical | TL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Site Construction |  |  |  | 0 |  | Include: clearing, brushing, earthworks, grading, surveys, foundations, access roads, permits, mtigations, equipment rental, mob/demob,yards,shelters, camps,site supervisions,indirects | TL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Tower Construction |  |  |  | 0 |  | Include: assembly, erecdtion and tower equipment installation | TL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Building & Equipment |  |  |  | 0 |  | Include: fabrication,transport and equipment installation | TL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Commissioning |  |  |  | 0 |  |  | TL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other | Type / quality |  |  | 0 |  | Describe: other in the assumptions field | TL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL LABOUR |  | 0 | 0 | 0 |  |  | s_TL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | TS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | TS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | TS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL SUPPLY & INSTALL |  | 0 | 0 | 0 |  |  | s_TS | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
TELECOM SITE (5) |  | 0 | 0 | 0 |  |  | TT | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Telecommunication Site < Name, Location > | [10 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [20 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location > | [6 empty] | Telecommunication Site < Name, Location >
MATERIALS | [5 empty] | Include: concrete
Tower | height |  |  | 0 |  | Include antennas and other | TM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Radio Equipment |  |  |  | 0 |  |  | TM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Building | size |  |  | 0 |  | Include if substation building not utilized | TM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Fibre | km, type |  |  | 0 |  |  | TM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Duct Banks | size, quantity |  |  | 0 |  |  | TM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other | Type / quality / description |  |  | 0 |  |  | TM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL MATERIALS |  | 0 | 0 | 0 |  |  | s_TM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
LABOUR
Detailed Engineering |  |  |  | 0 |  | Include: telecom, engineering services, geotechnical | TL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Site Construction |  |  |  | 0 |  | Include: clearing, brushing, earthworks, grading, surveys, foundations, access roads, permits, mtigations, equipment rental, mob/demob,yards,shelters, camps,site supervisions,indirects | TL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Tower Construction |  |  |  | 0 |  | Include: assembly, erecdtion and tower equipment installation | TL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Building & Equipment |  |  |  | 0 |  | Include: fabrication,transport and equipment installation | TL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Commissioning |  |  |  | 0 |  |  | TL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Other | Type / quality |  |  | 0 |  | Describe: other in the assumptions field | TL | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL LABOUR |  | 0 | 0 | 0 |  |  | s_TL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | TS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | TS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Supply & Install | type / quality |  |  | 0 |  |  | TS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
SUBTOTAL SUPPLY & INSTALL |  | 0 | 0 | 0 |  |  | s_TS | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
TELECOM SITE (6) |  | 0 | 0 | 0 |  |  | TT | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
TOTAL TELECOM MATERIAL |  | 0 | 0 | 0 |  |  | s_s_TM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
TOTAL TELECOM LABOUR |  | 0 | 0 | 0 |  |  | s_s_TL | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
TOTAL TELECOM SUPPLY & INSTALL |  | 0 | 0 | 0 |  |  | s_s_TS | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
TOTAL TELECOMMUNICATIONS |  | 0 | 0 | 0 |  |  | s_TT | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0

## Owrs 5
OWNERS SUMMARY |  |  |  |  | 1 | PCP | PCP #1 | 0 | PCP # 1 |  |  | 2 | PCP | PCP #2 | 0 | PCP # 2 |  |  | 3 | PCP | PCP #3 | 0 | PCP # 3 |  |  | 4 | PCP | PCP #4 | 0 | PCP # 4 |  |  | 5 | PCP | PCP #5 | 0 | PCP # 5 |  |  | 6 | PCP | PCP #6 | 0 | PCP # 6 |  |  | 7 | PCP | PCP #7 | 0 | PCP # 7 |  |  | 8 | PCP | PCP #8 | 0 | PCP # 8 |  |  | 9 | PCP | PCP #9 | 0 | PCP # 9 |  |  | 10 | PCP | PCP #10 | 0 | PCP # 10 |  |  | 11 | PCP | PCP #11 | 0 | PCP # 11 |  |  | 12 | PCP | PCP #12 | 0 | PCP # 12 |  |  | 13 | Final Cost Report | Final Cost Report #13 | 0 | Final Cost Report # 13 |  |  | 14 | PCP | PCP #14 | 0 | PCP # 14 |  |  | 15 | PCP | PCP #15 | 0 | PCP # 15 |  |  | 16 | PCP | PCP #16 | 0 | PCP # 16 |  |  | 17 | PCP | PCP #17 | 0 | PCP # 17
| SYSTEM | PARTICIPANT | TOTAL | ASSUMPTIONS |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments
PRE-SP
Pre-SP Cost |  |  | 0 |  | PS | 0 | 0 | 0 |  |  |  | PS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | PS | 0 | 0 | 0 |  |  |  | PS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | PS | 0 | 0 | 0 |  |  |  | PS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | PS | 0 | 0 | 0 |  |  |  | PS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | PS | 0 | 0 | 0 |  |  |  | PS | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
TOTAL PRE-SP | 0 | 0 | 0 | Total used in Sum-Tab 1 | s_PS | 0 | 0 | 0 | 0 | 0 |  | s_PS | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
SERVICE PROPOSAL
Service Proposal |  |  | 0 |  | SP | 0 | 0 | 0 |  |  |  | SP | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | SP | 0 | 0 | 0 |  |  |  | SP | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | SP | 0 | 0 | 0 |  |  |  | SP | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | SP | 0 | 0 | 0 |  |  |  | SP | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | SP | 0 | 0 | 0 |  |  |  | SP | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
TOTAL SERVICE PROPOSAL | 0 | 0 | 0 | Total used in Sum-Tab 1 | s_SP | 0 | 0 | 0 | 0 | 0 |  | s_SP | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
FACILITY APPLICATION
Facility Application |  |  | 0 |  | FA | 0 | 0 | 0 |  |  |  | FA | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | FA | 0 | 0 | 0 |  |  |  | FA | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | FA | 0 | 0 | 0 |  |  |  | FA | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | FA | 0 | 0 | 0 |  |  |  | FA | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | FA | 0 | 0 | 0 |  |  |  | FA | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
TOTAL FACILITY APPLICATION | 0 | 0 | 0 | Total used in Sum-Tab 1 | s_FA | 0 | 0 | 0 | 0 | 0 |  | s_FA | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
REGULATORY & COMPLIANCE
Regulatory & Compliance |  |  | 0 |  | RC | 0 | 0 | 0 |  |  |  | RC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | RC | 0 | 0 | 0 |  |  |  | RC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | RC | 0 | 0 | 0 |  |  |  | RC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | RC | 0 | 0 | 0 |  |  |  | RC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | RC | 0 | 0 | 0 |  |  |  | RC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
TOTAL REGULATORY & COMPLIANCE | 0 | 0 | 0 | Total used in Sum-Tab 1 | s_RC | 0 | 0 | 0 | 0 | 0 |  | s_RC | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
LAND RIGHTS -EASEMENTS
Land Rights - Easements |  |  | 0 |  | LE | 0 | 0 | 0 |  |  |  | LE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | LE | 0 | 0 | 0 |  |  |  | LE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | LE | 0 | 0 | 0 |  |  |  | LE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | LE | 0 | 0 | 0 |  |  |  | LE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | LE | 0 | 0 | 0 |  |  |  | LE | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
TOTAL RIGHTS -EASEMENTS | 0 | 0 | 0 | Total used in Sum-Tab 1 | s_LE | 0 | 0 | 0 | 0 | 0 |  | s_LE | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
LAND - DAMAGE CLAIMS
Land - Damage Claims |  |  | 0 |  | LDC | 0 | 0 | 0 |  |  |  | LDC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | LDC | 0 | 0 | 0 |  |  |  | LDC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | LDC | 0 | 0 | 0 |  |  |  | LDC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | LDC | 0 | 0 | 0 |  |  |  | LDC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | LDC | 0 | 0 | 0 |  |  |  | LDC | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
TOTAL LAND - DAMAGE CLAIMS | 0 | 0 | 0 | Total used in Sum-Tab 1 | s_LDC | 0 | 0 | 0 | 0 | 0 |  | s_LDC | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
LAND ACQUISITIONS
Land - Acquisitions |  |  | 0 |  | LA | 0 | 0 | 0 |  |  |  | LA | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | LA | 0 | 0 | 0 |  |  |  | LA | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | LA | 0 | 0 | 0 |  |  |  | LA | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | LA | 0 | 0 | 0 |  |  |  | LA | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | LA | 0 | 0 | 0 |  |  |  | LA | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
TOTAL Land - Acquisitions | 0 | 0 | 0 | Total used in Sum-Tab 1 | s_LA | 0 | 0 | 0 | 0 | 0 |  | s_LA | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
LAND - OTHER
Land - Other |  |  | 0 |  | LO | 0 | 0 | 0 |  |  |  | LO | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | LO | 0 | 0 | 0 |  |  |  | LO | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | LO | 0 | 0 | 0 |  |  |  | LO | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | LO | 0 | 0 | 0 |  |  |  | LO | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | LO | 0 | 0 | 0 |  |  |  | LO | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
TOTAL LAND - OTHER | 0 | 0 | 0 | Total used in Sum-Tab 1 | s_LO | 0 | 0 | 0 | 0 | 0 |  | s_LO | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
TOTAL | 0 | 0 | 0 | Total of Owners |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0

## Labor 6
DISTRIBUTED LABOUR SUMMARY | [5 empty] | 1 | PCP | PCP #1 | 0 | PCP # 1 |  |  | 2 | PCP | PCP #2 | 0 | PCP # 2 |  |  | 3 | PCP | PCP #3 | 0 | PCP # 3 |  |  | 4 | PCP | PCP #4 | 0 | PCP # 4 |  |  | 5 | PCP | PCP #5 | 0 | PCP # 5 |  |  | 6 | PCP | PCP #6 | 0 | PCP # 6 |  |  | 7 | PCP | PCP #7 | 0 | PCP # 7 |  |  | 8 | PCP | PCP #8 | 0 | PCP # 8 |  |  | 9 | PCP | PCP #9 | 0 | PCP # 9 |  |  | 10 | PCP | PCP #10 | 0 | PCP # 10 |  |  | 11 | PCP | PCP #11 | 0 | PCP # 11 |  |  | 12 | PCP | PCP #12 | 0 | PCP # 12 |  |  | 13 | Final Cost Report | Final Cost Report #13 | 0 | Final Cost Report # 13 |  |  | 14 | PCP | PCP #14 | 0 | PCP # 14 |  |  | 15 | PCP | PCP #15 | 0 | PCP # 15 |  |  | 16 | PCP | PCP #16 | 0 | PCP # 16 |  |  | 17 | PCP | PCP #17 | 0 | PCP # 17
| SYSTEM | PARTICIPANT | TOTAL | ASSUMPTIONS |  |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | TOTAL | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments
PROCUREMENT
Procurement Management |  |  | 0 |  | Include: assumptions made for number of resources, days or hours of effort | PR | 0 | 0 | 0 |  |  |  | PR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | Include: assumptions made for number of resources, days or hours of effort | PR | 0 | 0 | 0 |  |  |  | PR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | Include: assumptions made for number of resources, days or hours of effort | PR | 0 | 0 | 0 |  |  |  | PR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other costs> |  |  | 0 |  | Include: assumptions made for number of resources, days or hours of effort | PR | 0 | 0 | 0 |  |  |  | PR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other costs> |  |  | 0 |  | Include: assumptions made for number of resources, days or hours of effort | PR | 0 | 0 | 0 |  |  |  | PR | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
TOTAL PROCUREMENT | 0 | 0 | 0 | Total used in Sum-Tab 1 |  | s_PR | 0 | 0 | 0 | 0 | 0 |  | s_PR | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
PROJECT MANAGEMENT
Project Management |  |  | 0 |  | Include: assumptions made for number of resources, days or hours of effort | PM | 0 | 0 | 0 |  |  |  | PM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Project Management Office |  |  | 0 |  | Include: assumptions made for number of resources, days or hours of effort | PM | 0 | 0 | 0 |  |  |  | PM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Projects and Controls |  |  | 0 |  | Include: assumptions made for number of resources, days or hours of effort | PM | 0 | 0 | 0 |  |  |  | PM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | Include: assumptions made for number of resources, days or hours of effort | PM | 0 | 0 | 0 |  |  |  | PM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | Include: assumptions made for number of resources, days or hours of effort | PM | 0 | 0 | 0 |  |  |  | PM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | Include: assumptions made for number of resources, days or hours of effort | PM | 0 | 0 | 0 |  |  |  | PM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | Include: assumptions made for number of resources, days or hours of effort | PM | 0 | 0 | 0 |  |  |  | PM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | Include: assumptions made for number of resources, days or hours of effort | PM | 0 | 0 | 0 |  |  |  | PM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | Include: assumptions made for number of resources, days or hours of effort | PM | 0 | 0 | 0 |  |  |  | PM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
TOTAL PROJECT MANAGEMENT | 0 | 0 | 0 | Total used in Sum-Tab 1 |  | s_PM | 0 | 0 | 0 | 0 | 0 |  | s_PM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
CONSTRUCTION
Construction Management |  |  | 0 |  | Include: assumptions made for number of resources, days or hours of effort. Field supervision may be included here or in Tabs 2,3,4. | CM | 0 | 0 | 0 |  |  |  | CM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Environment Management |  |  | 0 |  | Include: assumptions made for number of resources, days or hours of effort. May be included here or in Tabs 2,3,4. | CM | 0 | 0 | 0 |  |  |  | CM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Indirects |  |  | 0 |  | Includes: trailers, fences, water, porta potties, etc. May be included here or in Tabs 2,3,4. | CM | 0 | 0 | 0 |  |  |  | CM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | Include: assumptions made for number of resources, days or hours of effort | CM | 0 | 0 | 0 |  |  |  | CM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | Include: assumptions made for number of resources, days or hours of effort | CM | 0 | 0 | 0 |  |  |  | CM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | Include: assumptions made for number of resources, days or hours of effort | CM | 0 | 0 | 0 |  |  |  | CM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
<Other resource> |  |  | 0 |  | Include: assumptions made for number of resources, days or hours of effort | CM | 0 | 0 | 0 |  |  |  | CM | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
TOTAL CONSTRUCTION | 0 | 0 | 0 | Total used in SuM-Tab 1 |  | s_CM | 0 | 0 | 0 | 0 | 0 |  | s_CM | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
TOTAL | 0 | 0 | 0 | Total of Procurement, Project and Construction management |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0

## Cont (Sys) 7a
| SYSTEM CONTINGENCY & RISK SUMMARY | [8 empty] | 1 | PCP | PCP #1 | 2 | PCP | PCP #2 | 3 | PCP | PCP #3 | 4 | PCP | PCP #4 | 5 | PCP | PCP #5 | 6 | PCP | PCP #6 | 7 | PCP | PCP #7 | 8 | PCP | PCP #8 | 9 | PCP | PCP #9 | 10 | PCP | PCP #10 | 11 | PCP | PCP #11 | 12 | PCP | PCP #12 | 13 | Final Cost Report | Final Cost Report #13 | 14 | PCP | PCP #14 | 15 | PCP | PCP #15 | 16 | PCP | PCP #16 | 17 | PCP | PCP #17
| RISK | DESCRIPTION | IMPACT | PROB | COST IMPACT | CONTINGENCY | ACTION | RESPONSE STRATEGY |  | 0 | CHANGE | CHANGE COMMENT | 0 | CHANGE | CHANGE COMMENT | 0 | CHANGE | CHANGE COMMENT | 0 | CHANGE | CHANGE COMMENT | 0 | CHANGE | CHANGE COMMENT | 0 | CHANGE | CHANGE COMMENT | 0 | CHANGE | CHANGE COMMENT | 0 | CHANGE | CHANGE COMMENT | 0 | CHANGE | CHANGE COMMENT | 0 | CHANGE | CHANGE COMMENT | 0 | CHANGE | CHANGE COMMENT | 0 | CHANGE | CHANGE COMMENT | 0 | CHANGE | CHANGE COMMENT | 0 | CHANGE | CHANGE COMMENT | 0 | CHANGE | CHANGE COMMENT | 0 | CHANGE | CHANGE COMMENT | 0 | CHANGE | CHANGE COMMENT
[6 empty] | 0 |  |  | Significant known risks are factored into the contingency calculation. Measures of these risks are generally known even at the earliest stages of project definition. As such, contingency can be viewed as an allowance for known risks, which are likely to occur. while the estimate accuracy range is an allowance for unknown” risks or systemetic risk; thus, should not be included in Contingency.
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
|  |  | CONTINGENCY |  |  | 0 |  | Total used in Summary-Tab 1 | Use this total if NOT using Risk Simulations totals below |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Risk Simulation Use Only (below)
|  |  | CONTINGENCY P50 |  |  |  |  | Total used in Summary-Tab 1 | Use either the P50 or P70 Total on the summary sheet if using Risk Simulation results |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | CONTINGENCY P70 |  |  |  |  | Total used in Summary-Tab 1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
INSERT RISK SIMULATION TABLE OR GRAPH HERE
[6 empty] | 0 |  |  |  | 1 |  |  | 2 |  |  | 3 |  |  | 4 |  |  | 5 |  |  | 6 |  |  | 7 |  |  | 8 |  |  | 9 |  |  | 10 |  |  | 11 |  |  | 12 |  |  | 13 |  |  | 14 |  |  | 15 |  |  | 16 |  |  | 17
[10 empty] | 7 |  |  | 15 |  |  | 23 |  |  | 31 |  |  | 39 |  |  | 47 |  |  | 55 |  |  | 63 |  |  | 71 |  |  | 79 |  |  | 87 |  |  | 95 |  |  | 103 |  |  | 111 |  |  | 119 |  |  | 127 |  |  | 135

## Cont (Part) 7b
| PARTICIPANT CONTINGENCY & RISK SUMMARY | [8 empty] | 1 | PCP | PCP #1 | 2 | PCP | PCP #2 | 3 | PCP | PCP #3 | 4 | PCP | PCP #4 | 5 | PCP | PCP #5 | 6 | PCP | PCP #6 | 7 | PCP | PCP #7 | 8 | PCP | PCP #8 | 9 | PCP | PCP #9 | 10 | PCP | PCP #10 | 11 | PCP | PCP #11 | 12 | PCP | PCP #12 | 13 | Final Cost Report | Final Cost Report #13 | 14 | PCP | PCP #14 | 15 | PCP | PCP #15 | 16 | PCP | PCP #16 | 17 | PCP | PCP #17
| RISK | DESCRIPTION | IMPACT | PROB | COST IMPACT | CONTINGENCY | ACTION | RESPONSE STRATEGY |  | 0 | CHANGE | CHANGE COMMENT | 0 | CHANGE | CHANGE COMMENT | 0 | CHANGE | CHANGE COMMENT | 0 | CHANGE | CHANGE COMMENT | 0 | CHANGE | CHANGE COMMENT | 0 | CHANGE | CHANGE COMMENT | 0 | CHANGE | CHANGE COMMENT | 0 | CHANGE | CHANGE COMMENT | 0 | CHANGE | CHANGE COMMENT | 0 | CHANGE | CHANGE COMMENT | 0 | CHANGE | CHANGE COMMENT | 0 | CHANGE | CHANGE COMMENT | 0 | CHANGE | CHANGE COMMENT | 0 | CHANGE | CHANGE COMMENT | 0 | CHANGE | CHANGE COMMENT | 0 | CHANGE | CHANGE COMMENT | 0 | CHANGE | CHANGE COMMENT
[6 empty] | 0 |  |  | Significant known risks are factored into the contingency calculation. Measures of these risks are generally known even at the earliest stages of project definition. As such, contingency can be viewed as an allowance for known risks, which are likely to occur while yhe estimate accuracy range is an allowance for unknown” risks or systemetic risk; thus, should not be included in Contingency.
0
0
0
0
0
0
0
0
0
0
0
0
0
0
[6 empty] | 0 |  |  | Typically, users should populate the “known” risks section and use the accuracy range for “unknown” risks. However, if the Facility Owner feels it necessary to identify additional contingency for “unknown” risks in addition to the accuracy range, the user may utilize the “unknown” risks line on the Contingency / Risk.Register, along with reasoning.
0
0
0
0
|  |  | CONTINGENCY |  |  | 0 |  | Total used in Summary-Tab 1 | Use this total if NOT using Risk Simulations totals below |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Risk Simulation Use Only (below)
|  |  | CONTINGENCY P50 |  |  |  |  | Total used in Summary-Tab 1 | Use either the P50 or P70 Total on the summary sheet if using Risk Simulation results |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | CONTINGENCY P70 |  |  |  |  | Total used in Summary-Tab 1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
INSERT RISK SIMULATION TABLE OR GRAPH HERE
[6 empty] | 0 |  |  |  | 1 |  |  | 2 |  |  | 3 |  |  | 4 |  |  | 5 |  |  | 6 |  |  | 7 |  |  | 8 |  |  | 9 |  |  | 10 |  |  | 11 |  |  | 12 |  |  | 13 |  |  | 14 |  |  | 15 |  |  | 16 |  |  | 17
[10 empty] | 7 |  |  | 15 |  |  | 23 |  |  | 31 |  |  | 39 |  |  | 47 |  |  | 55 |  |  | 63 |  |  | 71 |  |  | 79 |  |  | 87 |  |  | 95 |  |  | 103 |  |  | 111 |  |  | 119 |  |  | 127 |  |  | 135

## Escn 8
ESCALATION SUMMARY |  |  |  |  | 1 | PCP | PCP #1 | 0 | PCP # 1 |  |  | 2 | PCP | PCP #2 | 0 | PCP # 2 |  |  | 3 | PCP | PCP #3 | 0 | PCP # 3 |  |  | 4 | PCP | PCP #4 | 0 | PCP # 4 |  |  | 5 | PCP | PCP #5 | 0 | PCP # 5 |  |  | 6 | PCP | PCP #6 | 0 | PCP # 6 |  |  | 7 | PCP | PCP #7 | 0 | PCP # 7 |  |  | 8 | PCP | PCP #8 | 0 | PCP # 8 |  |  | 9 | PCP | PCP #9 | 0 | PCP # 9 |  |  | 10 | PCP | PCP #10 | 0 | PCP # 10 |  |  | 11 | PCP | PCP #11 | 0 | PCP # 11 |  |  | 12 | PCP | PCP #12 | 0 | PCP # 12 |  |  | 13 | Final Cost Report | Final Cost Report #13 | 0 | Final Cost Report # 13 |  |  | 14 | PCP | PCP #14 | 0 | PCP # 14 |  |  | 15 | PCP | PCP #15 | 0 | PCP # 15 |  |  | 16 | PCP | PCP #16 | 0 | PCP # 16 |  |  | 17 | PCP | PCP #17 | 0 | PCP # 17
| SYSTEM | PARTICIPANT | ESCALATION | ASSUMPTIONS |  | SYSTEM | PARTICIPANT | ESCALATION | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | ESCALATION | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | ESCALATION | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | ESCALATION | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | ESCALATION | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | ESCALATION | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | ESCALATION | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | ESCALATION | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | ESCALATION | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | ESCALATION | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | ESCALATION | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | ESCALATION | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | ESCALATION | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | ESCALATION | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | ESCALATION | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | ESCALATION | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | ESCALATION | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments
TRANSMISSION LINE
Material |  |  | 0 |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0
Labour |  |  | 0 |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0
Supply and Install |  |  | 0 |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0 |  |  |  | EL | 0 | 0 | 0
TOTAL TRANSMISSION | 0 | 0 | 0 |  | s_EL | 0 | 0 | 0 | 0 | 0 |  | s_EL | 0 | 0 | 0 | 0 | 0 |  | s_EL | 0 | 0 | 0 | 0 | 0 |  | s_EL | 0 | 0 | 0 | 0 | 0 |  | s_EL | 0 | 0 | 0 | 0 | 0 |  | s_EL | 0 | 0 | 0 | 0 | 0 |  | s_EL | 0 | 0 | 0 | 0 | 0 |  | s_EL | 0 | 0 | 0 | 0 | 0 |  | s_EL | 0 | 0 | 0 | 0 | 0 |  | s_EL | 0 | 0 | 0 | 0 | 0 |  | s_EL | 0 | 0 | 0 | 0 | 0 |  | s_EL | 0 | 0 | 0 | 0 | 0 |  | s_EL | 0 | 0 | 0 | 0 | 0 |  | s_EL | 0 | 0 | 0 | 0 | 0 |  | s_EL | 0 | 0 | 0 | 0 | 0 |  | s_EL | 0 | 0 | 0 | 0 | 0 |  | s_EL | 0 | 0 | 0 | 0 | 0
SUBSTATION
Material |  |  | 0 |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0
Labour |  |  | 0 |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0
Supply and Install |  |  | 0 |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0 |  |  |  | ES | 0 | 0 | 0
TOTAL SUBSTATION | 0 | 0 | 0 |  | s_ES | 0 | 0 | 0 | 0 | 0 |  | s_ES | 0 | 0 | 0 | 0 | 0 |  | s_ES | 0 | 0 | 0 | 0 | 0 |  | s_ES | 0 | 0 | 0 | 0 | 0 |  | s_ES | 0 | 0 | 0 | 0 | 0 |  | s_ES | 0 | 0 | 0 | 0 | 0 |  | s_ES | 0 | 0 | 0 | 0 | 0 |  | s_ES | 0 | 0 | 0 | 0 | 0 |  | s_ES | 0 | 0 | 0 | 0 | 0 |  | s_ES | 0 | 0 | 0 | 0 | 0 |  | s_ES | 0 | 0 | 0 | 0 | 0 |  | s_ES | 0 | 0 | 0 | 0 | 0 |  | s_ES | 0 | 0 | 0 | 0 | 0 |  | s_ES | 0 | 0 | 0 | 0 | 0 |  | s_ES | 0 | 0 | 0 | 0 | 0 |  | s_ES | 0 | 0 | 0 | 0 | 0 |  | s_ES | 0 | 0 | 0 | 0 | 0
TELECOMMUNICATIONS
Material |  |  | 0 |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0
Labour |  |  | 0 |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0
Supply and Install |  |  | 0 |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0 |  |  |  | ET | 0 | 0 | 0
TOTAL TELECOMMUNICATIONS | 0 | 0 | 0 |  | s_ET | 0 | 0 | 0 | 0 | 0 |  | s_ET | 0 | 0 | 0 | 0 | 0 |  | s_ET | 0 | 0 | 0 | 0 | 0 |  | s_ET | 0 | 0 | 0 | 0 | 0 |  | s_ET | 0 | 0 | 0 | 0 | 0 |  | s_ET | 0 | 0 | 0 | 0 | 0 |  | s_ET | 0 | 0 | 0 | 0 | 0 |  | s_ET | 0 | 0 | 0 | 0 | 0 |  | s_ET | 0 | 0 | 0 | 0 | 0 |  | s_ET | 0 | 0 | 0 | 0 | 0 |  | s_ET | 0 | 0 | 0 | 0 | 0 |  | s_ET | 0 | 0 | 0 | 0 | 0 |  | s_ET | 0 | 0 | 0 | 0 | 0 |  | s_ET | 0 | 0 | 0 | 0 | 0 |  | s_ET | 0 | 0 | 0 | 0 | 0 |  | s_ET | 0 | 0 | 0 | 0 | 0 |  | s_ET | 0 | 0 | 0 | 0 | 0
OWNERS
Pre-SP Cost |  |  | 0 |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0
Proposal to Provide Service |  |  | 0 |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0
Facility Applications |  |  | 0 |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0
Regulatory & Compliance |  |  | 0 |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0
Land Rights - Easements |  |  | 0 |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0
Land - Damage Claims |  |  | 0 |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0
Land - Acquisitions |  |  | 0 |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0
Land - Other |  |  | 0 |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0 |  |  |  | EO | 0 | 0 | 0
TOTAL OWNERS | 0 | 0 | 0 |  | s_EO | 0 | 0 | 0 | 0 | 0 |  | s_EO | 0 | 0 | 0 | 0 | 0 |  | s_EO | 0 | 0 | 0 | 0 | 0 |  | s_EO | 0 | 0 | 0 | 0 | 0 |  | s_EO | 0 | 0 | 0 | 0 | 0 |  | s_EO | 0 | 0 | 0 | 0 | 0 |  | s_EO | 0 | 0 | 0 | 0 | 0 |  | s_EO | 0 | 0 | 0 | 0 | 0 |  | s_EO | 0 | 0 | 0 | 0 | 0 |  | s_EO | 0 | 0 | 0 | 0 | 0 |  | s_EO | 0 | 0 | 0 | 0 | 0 |  | s_EO | 0 | 0 | 0 | 0 | 0 |  | s_EO | 0 | 0 | 0 | 0 | 0 |  | s_EO | 0 | 0 | 0 | 0 | 0 |  | s_EO | 0 | 0 | 0 | 0 | 0 |  | s_EO | 0 | 0 | 0 | 0 | 0 |  | s_EO | 0 | 0 | 0 | 0 | 0
DISTRIBUTED
Procurement |  |  | 0 |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0
Project Management |  |  | 0 |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0
Construction Management |  |  | 0 |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0 |  |  |  | ED | 0 | 0 | 0
TOTAL DISTRIBUTED | 0 | 0 | 0 |  | s_ED | 0 | 0 | 0 | 0 | 0 |  | s_ED | 0 | 0 | 0 | 0 | 0 |  | s_ED | 0 | 0 | 0 | 0 | 0 |  | s_ED | 0 | 0 | 0 | 0 | 0 |  | s_ED | 0 | 0 | 0 | 0 | 0 |  | s_ED | 0 | 0 | 0 | 0 | 0 |  | s_ED | 0 | 0 | 0 | 0 | 0 |  | s_ED | 0 | 0 | 0 | 0 | 0 |  | s_ED | 0 | 0 | 0 | 0 | 0 |  | s_ED | 0 | 0 | 0 | 0 | 0 |  | s_ED | 0 | 0 | 0 | 0 | 0 |  | s_ED | 0 | 0 | 0 | 0 | 0 |  | s_ED | 0 | 0 | 0 | 0 | 0 |  | s_ED | 0 | 0 | 0 | 0 | 0 |  | s_ED | 0 | 0 | 0 | 0 | 0 |  | s_ED | 0 | 0 | 0 | 0 | 0 |  | s_ED | 0 | 0 | 0 | 0 | 0
SALVAGE
Transmission Line Labour |  |  | 0 |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0
Substation Labour |  |  | 0 |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0
Land Remediation and Reclamation |  |  | 0 |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0 |  |  |  | EV | 0 | 0 | 0
TOTAL SALVAGE | 0 | 0 | 0 |  | s_EV | 0 | 0 | 0 | 0 | 0 |  | s_EV | 0 | 0 | 0 | 0 | 0 |  | s_EV | 0 | 0 | 0 | 0 | 0 |  | s_EV | 0 | 0 | 0 | 0 | 0 |  | s_EV | 0 | 0 | 0 | 0 | 0 |  | s_EV | 0 | 0 | 0 | 0 | 0 |  | s_EV | 0 | 0 | 0 | 0 | 0 |  | s_EV | 0 | 0 | 0 | 0 | 0 |  | s_EV | 0 | 0 | 0 | 0 | 0 |  | s_EV | 0 | 0 | 0 | 0 | 0 |  | s_EV | 0 | 0 | 0 | 0 | 0 |  | s_EV | 0 | 0 | 0 | 0 | 0 |  | s_EV | 0 | 0 | 0 | 0 | 0 |  | s_EV | 0 | 0 | 0 | 0 | 0 |  | s_EV | 0 | 0 | 0 | 0 | 0 |  | s_EV | 0 | 0 | 0 | 0 | 0 |  | s_EV | 0 | 0 | 0 | 0 | 0
OTHER
AFUDC |  |  | 0 |  | ER | 0 | 0 | 0 |  |  |  | ER | 0 | 0 | 0 |  |  |  | ER | 0 | 0 | 0 |  |  |  | ER | 0 | 0 | 0 |  |  |  | ER | 0 | 0 | 0 |  |  |  | ER | 0 | 0 | 0 |  |  |  | ER | 0 | 0 | 0 |  |  |  | ER | 0 | 0 | 0 |  |  |  | ER | 0 | 0 | 0 |  |  |  | ER | 0 | 0 | 0 |  |  |  | ER | 0 | 0 | 0 |  |  |  | ER | 0 | 0 | 0 |  |  |  | ER | 0 | 0 | 0 |  |  |  | ER | 0 | 0 | 0 |  |  |  | ER | 0 | 0 | 0 |  |  |  | ER | 0 | 0 | 0 |  |  |  | ER | 0 | 0 | 0
E&S |  |  | 0 |  | ER | 0 | 0 | 0 |  |  |  | ER | 0 | 0 | 0 |  |  |  | ER | 0 | 0 | 0 |  |  |  | ER | 0 | 0 | 0 |  |  |  | ER | 0 | 0 | 0 |  |  |  | ER | 0 | 0 | 0 |  |  |  | ER | 0 | 0 | 0 |  |  |  | ER | 0 | 0 | 0 |  |  |  | ER | 0 | 0 | 0 |  |  |  | ER | 0 | 0 | 0 |  |  |  | ER | 0 | 0 | 0 |  |  |  | ER | 0 | 0 | 0 |  |  |  | ER | 0 | 0 | 0 |  |  |  | ER | 0 | 0 | 0 |  |  |  | ER | 0 | 0 | 0 |  |  |  | ER | 0 | 0 | 0 |  |  |  | ER | 0 | 0 | 0
TOTAL OTHER | 0 | 0 | 0 |  | s_ER | 0 | 0 | 0 | 0 | 0 |  | s_ER | 0 | 0 | 0 | 0 | 0 |  | s_ER | 0 | 0 | 0 | 0 | 0 |  | s_ER | 0 | 0 | 0 | 0 | 0 |  | s_ER | 0 | 0 | 0 | 0 | 0 |  | s_ER | 0 | 0 | 0 | 0 | 0 |  | s_ER | 0 | 0 | 0 | 0 | 0 |  | s_ER | 0 | 0 | 0 | 0 | 0 |  | s_ER | 0 | 0 | 0 | 0 | 0 |  | s_ER | 0 | 0 | 0 | 0 | 0 |  | s_ER | 0 | 0 | 0 | 0 | 0 |  | s_ER | 0 | 0 | 0 | 0 | 0 |  | s_ER | 0 | 0 | 0 | 0 | 0 |  | s_ER | 0 | 0 | 0 | 0 | 0 |  | s_ER | 0 | 0 | 0 | 0 | 0 |  | s_ER | 0 | 0 | 0 | 0 | 0 |  | s_ER | 0 | 0 | 0 | 0 | 0
TOTAL ESCALATION | 0 | 0 | 0 | Totals used in Summary-Tab 1 | EE | 0 | 0 | 0 | 0 | 0 |  | EE | 0 | 0 | 0 | 0 | 0 |  | EE | 0 | 0 | 0 | 0 | 0 |  | EE | 0 | 0 | 0 | 0 | 0 |  | EE | 0 | 0 | 0 | 0 | 0 |  | EE | 0 | 0 | 0 | 0 | 0 |  | EE | 0 | 0 | 0 | 0 | 0 |  | EE | 0 | 0 | 0 | 0 | 0 |  | EE | 0 | 0 | 0 | 0 | 0 |  | EE | 0 | 0 | 0 | 0 | 0 |  | EE | 0 | 0 | 0 | 0 | 0 |  | EE | 0 | 0 | 0 | 0 | 0 |  | EE | 0 | 0 | 0 | 0 | 0 |  | EE | 0 | 0 | 0 | 0 | 0 |  | EE | 0 | 0 | 0 | 0 | 0 |  | EE | 0 | 0 | 0 | 0 | 0 |  | EE | 0 | 0 | 0 | 0 | 0

## config (hidden)
for Version tracking |  | 17
1000 | PCP | PCP #1 | 9 | 6
| SP 180 | PCP #2 | 17 | 6
| SP update | PCP #3 | 25 | 6 | Accepted | 1 | Jan | 2015
| Final Cost Estimate | PCP #4 | 33 | 6 | Rejected | 2 | Feb | 2016
| Final Cost Report | PCP #5 | 41 | 6 | Pending | 3 | Mar | 2017
|  | PCP #6 | 49 | 6 | Current | 4 | Apr | 2018
|  | PCP #7 | 57 | 6 |  | 5 | May | 2019
|  | PCP #8 | 65 | 6 |  | 6 | Jun | 2020
|  | PCP #9 | 73 | 6 |  | 7 | Jul | 2021
|  | PCP #10 | 81 | 7 |  | 8 | Aug | 2022
|  | PCP #11 | 89 | 7 |  | 9 | Sep | 2023
|  | PCP #12 | 97 | 7 |  | 10 | Oct | 2024
|  | Final Cost Report #13 | 105 | 21 |  | 11 | Nov | 2025
|  | PCP #14 | 113 | 7 |  | 12 | Dec
|  | PCP #15 | 121 | 7 |  | 13
|  | PCP #16 | 129 | 7 |  | 14
|  | PCP #17 | 137 | 7 |  | 15
|  | 0 | 145 | 1 |  | 16
|  | 0 | 153 | 1 |  | 17
|  | 0 | 161 | 1 |  | 18
|  | 0 | 169 | 1 |  | 19
|  | 0 | 177 | 1 |  | 20
|  | 0 | 185 | 1 |  | 21
|  | 0 | 193 | 1 |  | 22
|  | 0 | 201 | 1 |  | 23
|  | 0 | 209 | 1 |  | 24
|  | 0 | 217 | 1 |  | 25
|  | 0 | 225 | 1 |  | 26
|  | 0 | 233 | 1 |  | 27
|  | 0 | 241 | 1 |  | 28
29
30
31

## Salv 9
SALVAGE SUMMARY |  |  |  |  | 1 | PCP | PCP #1 | 0 | PCP # 1 |  |  | 2 | PCP | PCP #2 | 0 | PCP # 2 |  |  | 3 | PCP | PCP #3 | 0 | PCP # 3 |  |  | 4 | PCP | PCP #4 | 0 | PCP # 4 |  |  | 5 | PCP | PCP #5 | 0 | PCP # 5 |  |  | 6 | PCP | PCP #6 | 0 | PCP # 6 |  |  | 7 | PCP | PCP #7 | 0 | PCP # 7 |  |  | 8 | PCP | PCP #8 | 0 | PCP # 8 |  |  | 9 | PCP | PCP #9 | 0 | PCP # 9 |  |  | 10 | PCP | PCP #10 | 0 | PCP # 10 |  |  | 11 | PCP | PCP #11 | 0 | PCP # 11 |  |  | 12 | PCP | PCP #12 | 0 | PCP # 12 |  |  | 13 | Final Cost Report | Final Cost Report #13 | 0 | Final Cost Report # 13 |  |  | 14 | PCP | PCP #14 | 0 | PCP # 14 |  |  | 15 | PCP | PCP #15 | 0 | PCP # 15 |  |  | 16 | PCP | PCP #16 | 0 | PCP # 16 |  |  | 17 | PCP | PCP #17 | 0 | PCP # 17
| SYSTEM | PARTICIPANT | SALVAGE | ASSUMPTIONS |  | SYSTEM | PARTICIPANT | SALVAGE | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | SALVAGE | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | SALVAGE | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | SALVAGE | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | SALVAGE | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | SALVAGE | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | SALVAGE | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | SALVAGE | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | SALVAGE | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | SALVAGE | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | SALVAGE | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | SALVAGE | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | SALVAGE | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | SALVAGE | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | SALVAGE | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | SALVAGE | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments |  | SYSTEM | PARTICIPANT | SALVAGE | SYSTEM CHANGE | PARTICIPANT CHANGE | Assumption Changes or Comments
TRANSMISSION LINE <Line#, Location - from substation to substation> | [8 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation>
Conductor Salvage |  |  | 0 |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0
Structure Salvage |  |  | 0 |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0
Hazardous Removal |  |  | 0 |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0
TOTAL TRANSMISSION LINE (1) | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0
TRANSMISSION LINE <Line#, Location - from substation to substation> | [8 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation>
Conductor Salvage |  |  | 0 |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0
Structure Salvage |  |  | 0 |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0
Hazardous Removal |  |  | 0 |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0
TOTAL TRANSMISSION LINE (2) | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0
TRANSMISSION LINE <Line#, Location - from substation to substation> | [8 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation>
Conductor Salvage |  |  | 0 |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0
Structure Salvage |  |  | 0 |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0
Hazardous Removal |  |  | 0 |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0
TOTAL TRANSMISSION LINE (3) | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0
TRANSMISSION LINE <Line#, Location - from substation to substation> | [8 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation>
Conductor Salvage |  |  | 0 |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0
Structure Salvage |  |  | 0 |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0
Hazardous Removal |  |  | 0 |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0
TOTAL TRANSMISSION LINE (4) | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0
TRANSMISSION LINE <Line#, Location - from substation to substation> | [8 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation> | [6 empty] | TRANSMISSION LINE <Line#, Location - from substation to substation>
Conductor Salvage |  |  | 0 |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0
Structure Salvage |  |  | 0 |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0
Hazardous Removal |  |  | 0 |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0 |  |  |  | SL | 0 | 0 | 0
TOTAL TRANSMISSION LINE (5) | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0 |  | s_SL | 0 | 0 | 0 | 0 | 0
TOTAL TRANSMISSION LINE SALVAGE | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
SUBSTATION <Name,#> | [8 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#>
Transformer Salvage |  |  | 0 |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0
Other Major Equipment Salvage |  |  | 0 |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0
Hazardous Removal |  |  | 0 |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0
TOTAL SUBSTATION (1) | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0
SUBSTATION <Name,#> | [8 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#>
Transformer Salvage |  |  | 0 |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0
Other Major Equipment Salvage |  |  | 0 |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0
Hazardous Removal |  |  | 0 |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0
TOTAL SUBSTATION (2) | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0
SUBSTATION <Name,#> | [8 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#>
Transformer Salvage |  |  | 0 |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0
Other Major Equipment Salvage |  |  | 0 |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0
Hazardous Removal |  |  | 0 |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0
TOTAL SUBSTATION (3) | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0
SUBSTATION <Name,#> | [8 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#>
Transformer Salvage |  |  | 0 |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0
Other Major Equipment Salvage |  |  | 0 |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0
Hazardous Removal |  |  | 0 |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0
TOTAL SUBSTATION (4) | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0
SUBSTATION <Name,#> | [8 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#> | [6 empty] | SUBSTATION <Name,#>
Transformer Salvage |  |  | 0 |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0
Other Major Equipment Salvage |  |  | 0 |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0
Hazardous Removal |  |  | 0 |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0 |  |  |  | SS | 0 | 0 | 0
TOTAL SUBSTATION (5) | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0 |  | s_SS | 0 | 0 | 0 | 0 | 0
TOTAL SUBSTATION SALVAGE | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
TELECOMMUNICATIONS < Name, Location > | [8 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location >
Tower Salvage |  |  | 0 |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0
Equipment Salvage |  |  | 0 |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0
Hazardous Removal |  |  | 0 |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0
TOTAL TELECOMMUNICATIONS (1) | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0
TELECOMMUNICATIONS < Name, Location > | [8 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location >
Tower Salvage |  |  | 0 |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0
Equipment Salvage |  |  | 0 |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0
Hazardous Removal |  |  | 0 |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0
TOTAL TELECOMMUNICATIONS (2) | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0
TELECOMMUNICATIONS < Name, Location > | [8 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location >
Tower Salvage |  |  | 0 |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0
Equipment Salvage |  |  | 0 |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0
Hazardous Removal |  |  | 0 |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0
TOTAL TELECOMMUNICATIONS (3) | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0
TELECOMMUNICATIONS < Name, Location > | [8 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location >
Tower Salvage |  |  | 0 |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0
Equipment Salvage |  |  | 0 |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0
Hazardous Removal |  |  | 0 |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0
TOTAL TELECOMMUNICATIONS (4) | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0
TELECOMMUNICATIONS < Name, Location > | [8 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location > | [6 empty] | TELECOMMUNICATIONS < Name, Location >
Tower Salvage |  |  | 0 |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0
Equipment Salvage |  |  | 0 |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0
Hazardous Removal |  |  | 0 |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0 |  |  |  | ST | 0 | 0 | 0
TOTAL TELECOMMUNICATIONS (5) | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0 |  | s_ST | 0 | 0 | 0 | 0 | 0
TOTAL TELECOMMUNICATIONS SALVAGE | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
TOTAL TRANSMISSION LINE SALVAGE | 0 | 0 | 0 |  | s_s_SL | 0 | 0 | 0 | 0 | 0 |  | s_s_SL | 0 | 0 | 0 | 0 | 0 |  | s_s_SL | 0 | 0 | 0 | 0 | 0 |  | s_s_SL | 0 | 0 | 0 | 0 | 0 |  | s_s_SL | 0 | 0 | 0 | 0 | 0 |  | s_s_SL | 0 | 0 | 0 | 0 | 0 |  | s_s_SL | 0 | 0 | 0 | 0 | 0 |  | s_s_SL | 0 | 0 | 0 | 0 | 0 |  | s_s_SL | 0 | 0 | 0 | 0 | 0 |  | s_s_SL | 0 | 0 | 0 | 0 | 0 |  | s_s_SL | 0 | 0 | 0 | 0 | 0 |  | s_s_SL | 0 | 0 | 0 | 0 | 0 |  | s_s_SL | 0 | 0 | 0 | 0 | 0 |  | s_s_SL | 0 | 0 | 0 | 0 | 0 |  | s_s_SL | 0 | 0 | 0 | 0 | 0 |  | s_s_SL | 0 | 0 | 0 | 0 | 0 |  | s_s_SL | 0 | 0 | 0 | 0 | 0
TOTAL SUBSTATION SALVAGE | 0 | 0 | 0 |  | s_s_SS | 0 | 0 | 0 | 0 | 0 |  | s_s_SS | 0 | 0 | 0 | 0 | 0 |  | s_s_SS | 0 | 0 | 0 | 0 | 0 |  | s_s_SS | 0 | 0 | 0 | 0 | 0 |  | s_s_SS | 0 | 0 | 0 | 0 | 0 |  | s_s_SS | 0 | 0 | 0 | 0 | 0 |  | s_s_SS | 0 | 0 | 0 | 0 | 0 |  | s_s_SS | 0 | 0 | 0 | 0 | 0 |  | s_s_SS | 0 | 0 | 0 | 0 | 0 |  | s_s_SS | 0 | 0 | 0 | 0 | 0 |  | s_s_SS | 0 | 0 | 0 | 0 | 0 |  | s_s_SS | 0 | 0 | 0 | 0 | 0 |  | s_s_SS | 0 | 0 | 0 | 0 | 0 |  | s_s_SS | 0 | 0 | 0 | 0 | 0 |  | s_s_SS | 0 | 0 | 0 | 0 | 0 |  | s_s_SS | 0 | 0 | 0 | 0 | 0 |  | s_s_SS | 0 | 0 | 0 | 0 | 0
TOTAL TELECOMMUNICATIONS SALVAGE | 0 | 0 | 0 |  | s_s_ST | 0 | 0 | 0 | 0 | 0 |  | s_s_ST | 0 | 0 | 0 | 0 | 0 |  | s_s_ST | 0 | 0 | 0 | 0 | 0 |  | s_s_ST | 0 | 0 | 0 | 0 | 0 |  | s_s_ST | 0 | 0 | 0 | 0 | 0 |  | s_s_ST | 0 | 0 | 0 | 0 | 0 |  | s_s_ST | 0 | 0 | 0 | 0 | 0 |  | s_s_ST | 0 | 0 | 0 | 0 | 0 |  | s_s_ST | 0 | 0 | 0 | 0 | 0 |  | s_s_ST | 0 | 0 | 0 | 0 | 0 |  | s_s_ST | 0 | 0 | 0 | 0 | 0 |  | s_s_ST | 0 | 0 | 0 | 0 | 0 |  | s_s_ST | 0 | 0 | 0 | 0 | 0 |  | s_s_ST | 0 | 0 | 0 | 0 | 0 |  | s_s_ST | 0 | 0 | 0 | 0 | 0 |  | s_s_ST | 0 | 0 | 0 | 0 | 0 |  | s_s_ST | 0 | 0 | 0 | 0 | 0
TOTAL SALVAGE | 0 | 0 | 0 | Totals used in Summary-Tab 1 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0

## Proc 10
PROCUREMENT SUMMARY
| SOLE SOURCED | % | COMPETITIVE BIDS | % | TOTAL | Total
TRANSMISSION LINES
Materials |  | -- |  | -- | 0
Labour |  | -- |  | -- | 0
Supply & Install |  | -- |  | -- | 0
TOTAL TRANSMISSION LINES | 0 | -- | 0 | -- | 0
SUBSTATIONS
Materials |  | -- |  | -- | 0
Labour |  | -- |  | -- | 0
Supply & Install |  | -- | 0 | -- | 0
TOTAL SUBSTATIONS | 0 | -- | 0 | -- | 0
TELECOM
Materials |  | -- |  | -- | 0
Labour |  | -- |  | -- | 0
Supply & Install |  | -- |  | -- | 0
TOTAL TELECOM | 0 | -- | 0 | -- | 0
TOTAL PROJECT
List procurements in accordance with ISO Rule 9.1.5.10.

## Capital Mtnc 11
Capital Maintenance
TRANSMISSION LINE
Material
Labour
Supply & Install
TOTAL TRANSMISSION LINE | 0
SUBSTATION
Material
Labour
Supply & Install
TOTAL SUBSTATION | 0
TELECOMMUNICATION
Material
Labour
Supply & Install
TOTAL TELECOMMUNCATIONS | 0
OWNERS
Pre-SP Cost
Service Proposal
Facility Applications
Regulatory & Compliance
Land Rights - Easements
Land - Damage Claims
Land - Acquisitions
Land - Other
TOTAL OWNERS COST | 0
DISTRIBUTED
Procurement Management
Project Management
Construction Management
Contingency
Escalation
TOTAL DISTRIBUTED | 0
SALVAGE
Transmission Line Labour
Substation Labour
Telecom Labour
Land Remediation and Reclamation
TOTAL SALVAGE | 0
OTHER COSTS
AFUDC
E&S
TOTAL OTHER | 0
TOTAL PROJECT | 0

## ISO Tariff 12
AESO Project Name & No. | XX UPGRADE |  | PXXXX
Prepared by:
AACE Class: |  | Estimate Basis
High Range |  | Low Range
Date of Estimate: |  | Base Year $
In Service Date |  | In Service Year $
Category Item | Substation Equipment | RCN or Additional Cost For Tariff CCD | Book Value or Actual (For PPS) | Additional Cost (Transfer to Summary Page
Replacement Cost New | 138 kV Transformer |  |  | 0
Additional Participant Related Costs | Breaker and a half |  |  | 0
Other Connection |  |  |  | 0
Total Project Cost (From SUM1 Tab) |  |  |  | 0
Total CCD Cost |  |  |  | 0 | TRUE
Replacement Cost New (ISO Tariff 12 Tab) Usage and Instructions
Replacement Cost New (RCN)
The actual project costs for a connection project are not necessarily what is ultimately paid by an MP. As an example, an MP doesn’t pay book value for a used transformer. The ISO Tariff tab is used for calculating additional costs arising from the application of the ISO tariff regarding the following to be charged to the MP as a construction contribution:
1. Replacement Cost New (RCN). The tariff dictates that the connection project costs must be based on the RCN value of equipment, which is the current cost of similar new equipment.
2. Breaker and a half schemes. When there are two breakers at an existing substation and a new project proposes to add one breaker for an MP, the additional cost of half of a breaker (installed) is charged to the MP.
3. Any other costs as deemed appropriate by the AESO.
4. Enter the RCN and Book Value in the appropriate tabs, ensure the book value costs are the same as in the main estimate tabs (Line(OH) / Subs).
5. These are manual entries for RCN and Book Value columns, the total additional costs are calculated.

## SP_FCR Prnt 13
AESO Project Name & No. | XX UPGRADE | 0 | PXXXX | AESO Project Name & No. | XX UPGRADE | PCP #1 | PXXXX
Prepared by: |  | 0 | 0 | Prepared by:
AACE Class: |  | Estimate Basis | Service Proposal | AACE Class: |  | Estimate Basis | Final Cost Report
High Range |  | Low Range |  | High Range |  | Low Range
Date of Estimate: |  | Base Year $ |  | Date of Estimate: |  | Base Year $
In Service Date |  | In Service Year $ |  | In Service Date |  | In Service Year $
| Service Proposal |  |  |  | Final Cost Report
| SYSTEM | PARTICIPANT | TOTAL |  | SYSTEM | PARTICIPANT | TOTAL
TRANSMISSION LINE |  |  |  | TRANSMISSION LINE
Material | 0 | 0 | 0 | Material | 0 | 0 | 0
Labour | 0 | 0 | 0 | Labour | 0 | 0 | 0
Supply & Install | 0 | 0 | 0 | Supply & Install | 0 | 0 | 0
TOTAL TRANSMISSION LINE | 0 | 0 | 0 | TOTAL TRANSMISSION LINE | 0 | 0 | 0
SUBSTATION |  |  |  | SUBSTATION
Material | 0 | 0 | 0 | Material | 0 | 0 | 0
Labour | 0 | 0 | 0 | Labour | 0 | 0 | 0
Supply & Install | 0 | 0 | 0 | Supply & Install | 0 | 0 | 0
TOTAL SUBSTATION | 0 | 0 | 0 | TOTAL SUBSTATION | 0 | 0 | 0
TELECOMMUNICATION |  |  |  | TELECOMMUNICATION
Material | 0 | 0 | 0 | Material | 0 | 0 | 0
Labour | 0 | 0 | 0 | Labour | 0 | 0 | 0
Supply & Install | 0 | 0 | 0 | Supply & Install | 0 | 0 | 0
TOTAL TELECOMMUNCATIONS | 0 | 0 | 0 | TOTAL TELECOMMUNCATIONS | 0 | 0 | 0
OWNERS |  |  |  | OWNERS
Pre-SP Cost | 0 | 0 | 0 | Pre-SP Cost | 0 | 0 | 0
Service Proposal | 0 | 0 | 0 | Service Proposal | 0 | 0 | 0
Facility Applications | 0 | 0 | 0 | Facility Applications | 0 | 0 | 0
Regulatory & Compliance | 0 | 0 | 0 | Regulatory & Compliance | 0 | 0 | 0
Land Rights - Easements | 0 | 0 | 0 | Land Rights - Easements | 0 | 0 | 0
Land - Damage Claims | 0 | 0 | 0 | Land - Damage Claims | 0 | 0 | 0
Land - Acquisitions | 0 | 0 | 0 | Land - Acquisitions | 0 | 0 | 0
Land - Other | 0 | 0 | 0 | Land - Other | 0 | 0 | 0
TOTAL OWNERS COST | 0 | 0 | 0 | TOTAL OWNERS COST | 0 | 0 | 0
DISTRIBUTED |  |  |  | DISTRIBUTED
Procurement Management | 0 | 0 | 0 | Procurement Management | 0 | 0 | 0
Project Management | 0 | 0 | 0 | Project Management | 0 | 0 | 0
Construction Management | 0 | 0 | 0 | Construction Management | 0 | 0 | 0
Contingency | 0 | 0 | 0 | Contingency | 0 | 0 | 0
Escalation | 0 | 0 | 0 | Escalation | 0 | 0 | 0
TOTAL DISTRIBUTED | 0 | 0 | 0 | TOTAL DISTRIBUTED | 0 | 0 | 0
SALVAGE |  |  |  | SALVAGE
Transmission Line Labour | 0 | 0 | 0 | Transmission Line Labour | 0 | 0 | 0
Substation Labour | 0 | 0 | 0 | Substation Labour | 0 | 0 | 0
Telecom Labour | 0 | 0 | 0 | Telecom Labour | 0 | 0 | 0
Land Remediation and Reclamation | 0 | 0 | 0 | Land Remediation and Reclamation | 0 | 0 | 0
TOTAL SALVAGE | 0 | 0 | 0 | TOTAL SALVAGE | 0 | 0 | 0
OTHER COSTS |  |  |  | OTHER COSTS
AFUDC | 0 | 0 | 0 | AFUDC | 0 | 0 | 0
E&S | 0 | 0 | 0 | E&S | 0 | 0 | 0
TOTAL OTHER | 0 | 0 | 0 | TOTAL OTHER | 0 | 0 | 0
TOTAL PROJECT | 0 | 0 | 0 | TOTAL PROJECT | 0 | 0 | 0